## Sheet1
Upgrade Id | Region | Description | Project Type | Voltage | Cost Estimate | Required Date | Transmission Owner | Proposal IDs | Schedule12 Location | (Non-Load Ratio Share) Cost Allocation Percent | (Load Ratio Share) Cost Allocation Percent | State | Location | Equipment | Task | Status | TEAC Cost | Driver | Projected In Service Date | Actual In Service Date | Immediate Need | Initial TEAC Date | Latest TEAC Date | Percent Complete | ISA In-Service Date | Revised In-Service Date | TEAC Materials | __parsed_Initial TEAC Date__
b3326 | PJM MA | Rebuild the 13707 Vienna-Nelson 138 kV line | Baseline | 138 | 60.5 |  | DPL |  | Appendix A | DPL:100 |  | DE | Vienna - Nelson |  | Rebuild | IS | 38.5 |  | 12/18/2024 | 12/18/2024 | No | 8/10/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-10
b3327 | PJM MA | Upgrade the disconnect switch (6784-L1) at Kent | Baseline | 69 | 0.25 |  | DPL |  | Appendix A | DPL:100 |  | DE | Vaughn |  | Upgrade | IS | 0.25 |  | 12/8/2023 | 12/15/2023 | No | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3328 | PJM MA | Upgrade the disconnect switch (13710-L1) and CT at Vienna | Baseline | 138 | 0.08 |  | DPL |  | Appendix A | DPL:100 |  | MD | Vienna |  | Upgrade | IS | 0.25 |  | 11/17/2023 | 11/17/2023 | No | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3329 | PJM MA | Rerate the 13773 Farmview-Milford 138 kV line | Baseline | 138 | 0.56 |  | DPL |  | Appendix A | DPL:100 |  | DE | Farmview - Milford |  | Rebuild | IS | 0.3 |  | 11/22/2023 | 2/6/2024 | No | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3332 | PJM MA | Rerate the 23076 Steel-Milford 230 kV line | Baseline | 230 | 7.2 |  | DPL |  | Appendix A | DPL:100 |  | DE | Steel - Milford |  | Rebuild | IS | 0.6 |  | 7/31/2024 | 9/17/2024 | Yes | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3775.2 | PJM WEST | Reconductor NEET’s section of Crete(IN/IL border)-St. John 345 kV line (6.95 miles). | Baseline | 345 | 7.24 |  | NEET | 2022_MD-644 (modified) | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ ComEd:100_x000D_ |  | IL | Crete-St. John |  | Reconductor | IS | 1.99 |  | 12/1/2026 | 5/9/2023 | No | 1/10/2023 | 1/10/2023 | 100 |  |  |  | 2023-01-10
b2779.6 | PJM WEST | Construct a 345 kV ring bus at Dunton Lake to serve SDI load at 345 kV via two circuits | Baseline | 345 | 23.4 | 6/1/2016 | AEP |  | Appendix A | AEP:100 |  | IN | Dunton Lake, SDI Varner |  | Construct | IS | 23.4 |  | 11/15/2021 | 11/3/2021 | Yes | 12/1/2020 | 12/1/2020 | 100 |  |  |  | 2020-12-01
b2779.7 | PJM WEST | Retire Collingwood 345 kV station | Baseline | 345 | 1.4 | 6/1/2016 | AEP |  | Appendix A | AEP:100 |  | IN | Collingwood |  | Retire | IS | 1.4 |  | 12/15/2021 | 11/29/2021 | Yes | 12/1/2020 | 12/1/2020 | 100 |  |  |  | 2020-12-01
b2604.1 | PJM WEST | Remove approximately 11.32 miles of the 69 kV line between Millbrook Park and Franklin Furnace. | Baseline | 69 | 1.13 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Millbrook Park-Franklin Furnace |  | Remove | EP | 1.13 |  | 11/9/2027 |  | No | 2/17/2021 | 2/17/2021 | 50 |  |  |  | 2021-02-17
b2604.10 | PJM WEST | Build a new station (Althea) with a 138/69 kV, 90 MVA transformer. The 138 kV side will have a single 2000 A 40 kA circuit breaker and the 69 kV side will be a 2000 A 40 kA three breaker ring bus. | Baseline | 138/69 | 11.07 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | (Althea) |  | Build | EP | 11.07 |  | 6/2/2028 |  | No | 2/17/2021 | 2/17/2021 | 50 |  |  |  | 2021-02-17
b2604.11 | PJM WEST | Remote end work at Hanging Rock, East Wheelersburg and North Haverhill 138 kV. | Baseline | 138 | 0.06 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Hanging Rock, East Wheelersburg, North Haverhill |  | Modify | EP | 0.06 |  | 6/2/2028 |  | No | 2/17/2021 | 2/17/2021 | 50 |  |  |  | 2021-02-17
b2604.2 | PJM WEST | At Millbrook Park station, add a new 138/69 kV transformer #2 (90 MVA) with 3000 A 40 kA breakers on the high and low side. Replace the 600 A MOAB Switch and add a 3000 A circuit switcher on the high side of transformer #1. | Baseline | 138/69 | 3.05 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Millbrook Park |  | Install | EP | 3.05 |  | 3/14/2028 |  | No | 2/17/2021 | 2/17/2021 | 50 |  |  |  | 2021-02-17
b2604.3 | PJM WEST | Replace Sciotoville 69 kV station with a new 138/12 kV in-out station (Cottrell) with 2000A line MOABs facing Millbrook Park and East Wheelersburg 138 kV. | Baseline | 138/12 | 1.4 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Sciotoville, Cottrell |  | Replace | EP | 1.4 |  | 10/7/2027 |  | No | 2/17/2021 | 2/17/2021 | 75 |  |  |  | 2021-02-17
b2604.4 | PJM WEST | Tie Cottrell switch into the Millbrook Park-East Wheelersburg 138 kV circuit by constructing 0.50 miles of line using 795 ACSR 26/7 Drake (SE 359 MVA). | Baseline | 138 | 1.96 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Cottrell, Millbrook Park-East Wheelersburg |  | Modify | EP | 1.96 |  | 10/7/2027 |  | No | 2/17/2021 | 2/17/2021 | 75 |  |  |  | 2021-02-17
b2604.5 | PJM WEST | Install a new 2000 A 3-way POP Switch outside of Texas Eastern 138 kV substation (Sadiq Switch). | Baseline | 138 | 1.08 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Sadiq Switch |  | Install | EP | 1.08 |  | 10/27/2027 |  | No | 2/17/2021 | 2/17/2021 | 50 |  |  |  | 2021-02-17
b2604.6 | PJM WEST | Replace the Wheelersburg 69 kV station with a new 138/12 kV in-out station (Sweetgum) with a 3000 A 40 kA breaker facing Sadiq Switch and a 2000 A 138 kV MOAB facing Althea. | Baseline | 138/12 | 2.16 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Wheelersburg, Sweetgum |  | Replace | EP | 2.16 |  | 12/9/2027 |  | No | 2/17/2021 | 2/17/2021 | 50 |  |  |  | 2021-02-17
b2604.7 | PJM WEST | Build approximately 1.4 miles of new 138 kV line using 795 ACSR 26/7 Drake (SE 359 MVA) between the new Sadiq Switch and the new Sweetgum 138 kV stations. | Baseline | 138 | 3.41 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Sadiq Switch-Sweetgum |  | Build | EP | 3.41 |  | 12/7/2027 |  | No | 2/17/2021 | 2/17/2021 | 50 |  |  |  | 2021-02-17
b2604.8 | PJM WEST | Remove the existing 69 kV Hayport Road Switch. | Baseline | 69 | 0.1 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Hayport Road Switch |  | Remove | EP | 0.1 |  | 11/9/2027 |  | No | 2/17/2021 | 2/17/2021 | 50 |  |  |  | 2021-02-17
b2604.9 | PJM WEST | Rebuild approximately 2.3 miles along existing ROW from Sweetgum to the Hayport Rd switch 69 kV location as 138 kV single circuit and rebuild approximately 2.0 miles from the Hayport Road switch to Althea 69 kV with double circuit 138 kV construction, one side operated at 69 kV to continue service to K.O. Wheelersburg, using 795 ACSR 26/7 Drake (SE 359 MVA). | Baseline | 138/69 | 10.76 | 6/1/2019 | AEP | 2014-2-2L | Appendix A | AEP:100 |  | OH | Sweetgum-Hayport Rd Switch-Althea |  | Rebuild | EP | 10.76 |  | 6/2/2028 |  | No | 2/17/2021 | 2/17/2021 | 50 |  |  |  | 2021-02-17
b3098.1 | PJM SOUTH | Rebuild Balcony Falls Substation | Baseline | 115 | 9 | 6/1/2019 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Rebuild | UC | 9 |  | 5/30/2025 |  | No | 5/21/2020 | 5/21/2020 | 40 |  |  |  | 2020-05-21
b3212 | PJM WEST | The Crescent 138 kV oil-type breaker “2-5 TIE” is found to be over duty following a model review and correction to short circuit base case. | Baseline | 138 | 0.35 | 1/31/2020 | DL |  | Appendix A | DL:100 |  | PA | Crescent Sub |  | Replace | IS | 0.35 |  | 1/31/2020 | 1/31/2020 | No | 2/21/2020 | 3/19/2020 | 100 |  |  |  | 2020-02-21
b2668.1 | PJM WEST | Replace the bus/risers at Dequine 345 kV station | Baseline | 345 | 2.3 | 6/1/2020 | AEP |  | Appendix A | AEP:100 |  | IN | Dequine |  | Replace | IS | 2.3 |  | 3/20/2023 | 3/20/2023 | No | 11/2/2021 | 11/2/2021 | 100 |  |  |  | 2021-11-02
b3261 | PJM WEST | Upgrade Circuit breaker 'R1' at Tanners Creek 345kV - Install TRV capacitor to increase the rating from 50kA to 63kA | Baseline | 345 | 0.05 | 12/31/2020 | AEP |  | Appendix A | AEP:100 |  | IN | Tanners Creek |  | Upgrade | IS | 0.05 |  | 12/31/2020 | 11/21/2020 | Yes | 11/4/2020 | 11/4/2020 | 100 |  |  |  | 2020-11-04
b3011.8 | PJM WEST | Upgrade 138 kV breaker “Z-78 Logans” at Dravosburg. | Baseline | 138 | 0.65 | 6/1/2021 | DL |  | Appendix A | DL:100 |  | PA | Dravosburg |  | Upgrade | IS | 0.9 |  | 11/30/2020 | 1/6/2021 | No | 1/17/2020 | 2/21/2020 | 100 |  |  |  | 2020-01-17
b3012.4 | PJM WEST | Establish the new tie line in place of the existing Elarama - Mitchell 138 kV line | Baseline | 138 | 1 | 6/1/2021 | DL |  | Appendix A | DL:100 |  | PA | Elrama, Mitchell |  | Build | Cancelled | 1 |  | 6/1/2021 |  | No | 7/13/2021 | 7/13/2021 | 0 |  |  |  | 2021-07-13
b3215 | PJM WEST | Upgrade terminal equipment at Yukon to increase rating on Yukon – AA2-161 (Robbins) 138 kV line | Baseline | 138 | 0.4 | 6/1/2021 | APS |  | Appendix A | APS:100 |  | PA |  |  | Upgrade | IS | 0.4 |  | 6/1/2021 | 4/22/2021 | No | 5/12/2020 | 6/2/2020 | 100 |  |  |  | 2020-05-12
b3216 | PJM WEST | Upgrade terminal equipment at Yukon to increase rating on Yukon – AA2-161 (Wycoff jct) 138 kV line | Baseline | 138 | 1.4 | 6/1/2021 | APS |  | Appendix A | APS:100 |  | PA |  |  | Upgrade | IS | 0.5 |  | 6/1/2021 | 6/4/2021 | No | 5/12/2020 | 6/2/2020 | 100 |  |  |  | 2020-05-12
b3217 | PJM WEST | Reconductor Wilson to Mitchell 138 kV line - DL portion. 4.2 miles total. 2x795 ACSS/TW 20/7 | Baseline | 138 | 7.5 | 6/1/2021 | DL |  | Appendix A | DL:100 |  | PA |  |  | Reconductor | IS | 7.5 |  | 6/1/2021 | 9/17/2020 | No | 5/12/2020 | 6/2/2020 | 100 |  |  |  | 2020-05-12
b3277 | PJM WEST | Replace the existing East Akron 138 kV breaker B-22 with 3000A continuous, 40 KA momentary current interrupting rating circuit breaker. | Baseline | 138 | 0.55 | 6/1/2021 | ATSI |  | Appendix A | ATSI:100 |  | OH |  |  | Replace | IS | 0.55 |  | 6/1/2021 | 5/15/2021 | No | 5/22/2020 | 11/20/2020 | 100 |  |  |  | 2020-05-22
b3260 | PJM WEST | Replace the existing breaker 501-B-251 with a new 69 kV breaker with a higher (40 kA) interrupting capability | Baseline | 69 | 0 | 12/1/2021 | ATSI |  | Appendix A | ATSI:100 |  | OH |  |  | Replace | IS | 0.86 |  | 12/1/2021 | 12/3/2021 | No | 12/18/2020 | 1/15/2021 | 100 |  |  |  | 2020-12-18
b3266 | PJM WEST | Upgrade the metering CT associated with the Clay Village-Clay Village T 69 kV line section to increase the line ratings. | Baseline | 69 | 0.03 | 12/1/2021 | EKPC |  | Appendix A | EKPC:100 |  | KY | Clay Village-Clay Village T |  | Replace | IS | 0.03 |  | 12/1/2021 | 12/1/2021 | No | 12/18/2020 | 12/18/2020 | 100 |  |  |  | 2020-12-18
b3267 | PJM WEST | Rebuild the 4/0 ACSR Norwood-Shopville 69 kV line section using 556 ACSR/TW. | Baseline | 69 | 4.72 | 12/1/2021 | EKPC |  | Appendix A | EKPC:100 |  | KY | Norwood-Shopville |  | Rebuild | EP | 3.79 |  | 5/29/2026 |  | No | 12/18/2020 | 12/18/2020 | 8 |  |  |  | 2020-12-18
b3110.3 | PJM SOUTH | Replace the Clifton 230kV breakers “201182” and “XT2011” with 63kA breakers | Baseline | 230 | 0.93 | 12/31/2021 | Dominion |  | Appendix A | Dominion:100 |  | VA | Clifton |  | Upgrade | IS | 0.93 |  | 12/31/2021 | 12/20/2021 | No | 8/4/2020 | 9/1/2020 | 100 |  |  |  | 2020-08-04
b3311 | PJM MA | Install a 120.75 kV 79.4 MVAR capacitor bank at Yorkana 115 kV | Baseline | 115 | 2.2 | 5/31/2022 | ME |  | Appendix A | ME:100 |  | PA | Yorkana |  | Install | IS | 2.2 |  | 5/31/2022 | 2/2/2023 | No | 1/6/2021 | 2/9/2021 | 100 |  |  |  | 2021-01-06
b3214 | PJM WEST | Reconductor the Yukon – Smithton – Shepler Hill Jct 138 kV Line. Upgrade terminal equipment at Yukon and replace line relaying at Mitchell and Charleroi | Baseline | 138 | 24.5 | 6/1/2022 | APS |  | Appendix A | DL:100 |  | PA |  |  | Reconductor | IS | 21.4 |  | 12/30/2022 | 12/22/2022 | No | 5/12/2020 | 10/5/2021 | 100 |  |  |  | 2020-05-12
b3214.1 | PJM WEST | Reconductor the Yukon – Smithton 138 kV Line. Upgrade terminal equipmet at Yukon and replace line relaying at Michell and Charleroi. | Baseline | 138 | 24.5 | 6/1/2022 | APS |  | Appendix A | APS:5.95,DL:94.05 |  | PA |  |  | Reconductor | IS | 10.7 |  | 6/1/2023 | 12/22/2022 | No | 5/12/2020 | 10/5/2021 | 100 |  |  |  | 2020-05-12
b3214.2 | PJM WEST | Reconductor the Smithton – Shepler Hill Jct 138 kV Line | Baseline | 138 | 0 | 6/1/2022 | APS |  | Appendix A | APS:8.38,DL:91.62 |  | PA |  |  | Reconductor | IS | 10.7 |  | 6/1/2023 | 12/22/2022 | No | 5/12/2020 | 10/5/2021 | 100 |  |  |  | 2020-05-12
b3318 | PJM WEST | Reconductor the Shanor Manor - Butler 138 kV line with an upgraded circuit breaker at Butler | Baseline | 138 | 2.18 | 6/1/2022 | APS |  | Appendix A | APS:100 |  | PA | Shanor Manor - Butler |  | Reconductor | IS | 1.5 |  | 10/31/2022 | 9/30/2022 | No | 8/10/2021 | 8/31/2021 | 100 |  |  |  | 2021-08-10
b3319 | PJM WEST | Add forced cooling to increase the normal rating of the Brunot Island-Carson (302) 345 kV High Pressure Fluid Filled (HPFF) underground cable circuit | Baseline | 138 | 22.5 | 6/1/2022 | DL |  | Appendix A | DL:100 |  | PA | Brunot Island - Carson |  | Install | IS | 22 |  | 4/30/2024 | 4/12/2024 | Yes | 8/10/2021 | 8/10/2021 | 100 |  |  |  | 2021-08-10
b3320 | PJM WEST | Replace the CT at Don Marquis 345 kV | Baseline | 345 | 0.08 | 6/1/2022 | AEP |  | Appendix A | AEP:100 |  | OH | Marquis |  | Replace | IS | 0.08 |  | 6/1/2022 | 8/15/2022 | Yes | 8/10/2021 | 8/31/2021 | 100 |  |  |  | 2021-08-10
b3321 | PJM SOUTH | Rebuild Cranes Corner-Stafford 230 kV line | Baseline | 230 | 28.9 | 6/1/2022 | Dominion |  | Appendix A | Dominion:100 |  | VA | Stafford |  | Rebuild | EP | 19.6 |  | 9/11/2026 |  | Yes | 8/10/2021 | 8/31/2021 | 20 |  |  |  | 2021-08-10
b3324 | PJM WEST | Replace the bus section at Olive | Baseline | 138 | 0.1 | 6/1/2022 | AEP |  | Appendix A | AEP:100 |  | IN | Olive |  | Replace | IS | 0.1 |  | 12/31/2022 | 11/18/2022 | No | 8/10/2021 | 8/10/2021 | 100 |  |  |  | 2021-08-10
b3325 | PJM WEST | Reconductor the Charleroi-Union 138 kV line and upgrade terminal equipment at Charleroi | Baseline | 138 | 11 | 6/1/2022 | APS |  | Appendix A | APS:100 |  | PA | Charleroi - Union |  | Reconductor | IS | 11 |  | 6/1/2023 | 5/31/2023 | No | 8/10/2021 | 8/31/2021 | 100 |  |  |  | 2021-08-10
b3330 | PJM MA | Rerate the 13774 Farmview-S. Harrington 138 kV line | Baseline | 138 | 0.77 | 6/1/2022 | DPL |  | Appendix A | DPL:100 |  | DE | Farmview - S. Harrington |  | Rebuild | IS | 0.25 |  | 12/31/2023 | 10/27/2023 | No | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3331 | PJM MA | Upgrade bus conductor and relay at Seaford 138 kV | Baseline | 138 | 0.5 | 6/1/2022 | DPL |  | Appendix A | DPL:100 |  | DE | S. Harrington |  | Upgrade | IS | 0.5 |  | 12/31/2023 | 9/18/2023 | No | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3334 | PJM WEST | Rebuild the section of Miami Fort-Hebron Tab 138 kV | Baseline | 138 | 27.2 | 6/1/2022 | DEOK |  | Appendix A | DEOK:100 |  | KY | Miami Fort - Hebron |  | Rebuild | IS | 44.3 |  | 5/22/2025 | 5/23/2025 | No | 11/2/2021 | 11/2/2021 | 100 |  |  |  | 2021-11-02
b3335 | PJM MA | Reconductor a 0.76 mile portion of the Croydon-Burlington 230 kV line | Baseline | 230 | 1.56 | 6/1/2022 | PECO | Proposal #2021_1-88 | Appendix A | PECO:100 |  | PA | Croydon - Burlington |  | Reconductor | IS | 0.79 |  | 12/15/2023 | 12/16/2023 | Yes | 11/2/2021 | 11/2/2021 | 100 |  |  |  | 2021-11-02
b3336 | PJM WEST | Rebuild Benton Harbor-Riverside 138 kV double circuit extension (6 miles). | Baseline | 138 | 14.9 | 6/1/2022 | AEP |  | Appendix A | AEP:100 |  | MI | Benton Harbor-Riverside |  | Rebuild | IS | 14.9 |  | 11/1/2021 | 9/10/2021 | No | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3707.1 | PJM SOUTH | Reconductor approximately 0.57mi of 115kV Line #1021 from Harmony Village to Greys Point with 768 ACSS to achieve a summer emergency rating of 237MVA. The current conductor is 477 ACSR. | Baseline | 115 | 1.89 | 6/1/2022 | Dominion |  | Appendix A | Dominion:100 |  | VA | Harmony Village, Greys Point |  | Reconductor | IS | 1.11 |  | 4/28/2022 | 4/25/2022 | No | 2/8/2022 | 2/8/2022 | 100 |  |  |  | 2022-02-08
b3707.2 | PJM SOUTH | Reconductor approximately 0.97mi of 115 kV Line #65 from Rappahanock to White Stone with 768 ACSS to achieve a summer emergency rating of 237MVA. The current conductor is 477 ACSR. | Baseline | 115 | 1.89 | 6/1/2022 | Dominion |  | Appendix A | Dominion:100 |  | VA | Rappahanock, White Stone |  | Reconductor | IS | 1.89 |  | 5/31/2022 | 4/25/2022 | No | 2/8/2022 | 2/8/2022 | 100 |  |  |  | 2022-02-08
b3701 | PJM WEST | Replace terminal equipment on the French's Mill-Junction JST1 138 kV line. | Baseline | 138 | 0.77 | 11/1/2022 | APS | 202021_1-756 | Appendix A | APS:100 |  | WV | Junction-French's Mill |  | Upgrade | IS | 0.77 |  | 12/9/2022 | 12/22/2022 | No | 1/11/2022 | 1/11/2022 | 100 |  |  |  | 2022-01-11
b3712 | PJM WEST | Install a 28 MVAR cap bank at Liberty Junction 69 kV. | Baseline | 69 | 0.78 | 12/1/2022 | EKPC |  | Appendix A | EKPC:100 |  | KY | Liberty Junction |  | Install | UC | 0.54 |  | 5/21/2025 |  | Yes | 4/22/2022 | 4/22/2022 | 89 |  |  |  | 2022-04-22
b3765 | PJM MA | Purchase one 80 MVAR 345 kV spare reactor, to be located at the Mainesburg station. | Baseline | 345 | 6.44 | 12/1/2022 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Mainesburg |  | Provide | EP | 6.44 |  | 12/30/2026 |  | No | 11/4/2022 | 12/6/2022 | 25 |  |  |  | 2022-11-04
b3719 | PJM MA | Replace the two existing 1200A Bergen 138 kV Circuit Switchers with two (2) 138 kV Disconnect Switches to achieve a minimum summer normal device rating of 298 MVA and a minimum summer emergency rating of 454 MVA. | Baseline | 138 | 1.2 | 12/31/2022 | PSEG |  | Appendix A | PSEG:100 |  | NJ | Bergeb |  | Replace | IS | 1.2 |  | 3/31/2024 |  | Yes | 9/15/2022 | 9/15/2022 | 1 |  |  |  | 2022-09-15
b3703 | PJM MA | Construct a third 69 kV supply line from Penns Neck substation to the West Windsor substation. | Baseline | 69 | 1.05 | 1/1/2023 | PSEG |  | Appendix A | PSEG:100 |  | NJ | West Windsor |  | Construct | IS | 1.05 |  |  | 11/23/2022 | Yes | 1/20/2022 | 1/20/2022 | 100 |  |  |  | 2022-01-20
b3713 | PJM WEST | Avon Plant Separation:• Disconnect and remove five 138 kV bus tie lines and associated equipment from the Avon Lake Substation to the plant (800-B Bank, 8-AV-T Generator, 5-AV-T, 6-AV-T, and 7-AV-T).• Disconnect and remove one 345 kV bus tie line and associated equipment from the Avon substation to the plant (Unit 9).• Adjust relay settings at Avon Lake, Avon and Avondale substations.• Removal/rerouting of fiber to the plant and install new fiber between the 345 kV and 138 kV yards for the Q4-AV-BUS relaying.• Remove SCADA RTU, communications and associated equipment from plant. | Baseline | 345/138 | 2.5 | 4/28/2023 | ATSI |  | Appendix A | ATSI:100 |  | OH | Avon Lake |  | Remove | IS | 2.5 |  | 5/4/2023 | 5/4/2023 | No | 6/7/2022 | 6/7/2022 | 100 |  |  |  | 2022-06-07
b3213 | PJM SOUTH | Install 2nd Chickahominy 500/230 kV transformerRelocate the Chickahominy – Elmont 500kV line #557 to terminate in a new bay at Chickahominy substation and relocate the Chesterfield – Lanexa 115kV line #92 to allow for the expansion of the Chickahominy substation • Add three new 500 kV breakers with 50kA interrupting rating and associated equipment | Baseline | 500/230 | 22 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA | Chickahominy |  | Install 2nd | IS | 31.05 |  | 4/24/2024 | 4/24/2024 | No | 6/2/2020 | 6/8/2021 | 100 |  |  |  | 2020-06-02
b3213.1 | PJM SOUTH | Replace the eight (8) Chickahominy 230kV breakers with 63kA breakers: “SC122”, “205022”, 209122”, 210222-2”, “28722”, “H222”, “21922”, “287T2129” | Baseline | 230 | 3.76 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Replace | Cancelled | 3.76 |  | 6/1/2023 |  | No | 11/4/2020 | 4/6/2021 | 0 |  |  |  | 2020-11-04
b3223.1 | PJM SOUTH | Install a 2nd 230kV circuit with a minimum summer emergency rating of 1047 MVA between Lanexa and Northern Neck Substations. The 2nd circuit will utilize the vacant arms on the double-circuit structures that are being installed on the Line #224 (Lanexa-Northern Neck) End-of-Life rebuild project (b3089). | Baseline | 230 | 14 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Install | UC | 14 |  | 12/31/2025 |  | Yes | 9/1/2020 | 10/6/2020 | 90 |  |  |  | 2020-09-01
b3223.2 | PJM SOUTH | Expand the Northern Neck terminal from a 230kV, 4-breaker ring bus to a 6-breaker ring bus. | Baseline | 230 | 5 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Modify | UC | 5 |  | 12/31/2025 |  | Yes | 9/1/2020 | 10/6/2020 | 50 |  |  |  | 2020-09-01
b3223.3 | PJM SOUTH | Expand the Lanexa terminal from a 6-breaker ring bus to a breaker-and-a-half arrangement. | Baseline | 230 | 4 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Modify | UC | 4 |  | 7/31/2025 |  | Yes | 9/1/2020 | 10/6/2020 | 100 |  |  |  | 2020-09-01
b3246.1 | PJM SOUTH | Convert 115 kV Line #172 Liberty-Lomar and 115 kV Line #197 Cannon Branch-Lomar to 230 kV to provide a new 230 kV source between Cannon Branch and Liberty. The majority of 115 kV Line #172 Liberty-Lomar and Line #197 Cannon Branch-Lomar is adequate for 230 kV operation. Lines to have a summer rating of 1047 MVA/1047 MVA (SN/SE) | Baseline | 230 | 10 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Modify | UC | 8 |  | 12/19/2025 |  | Yes | 12/1/2020 | 8/31/2021 | 60 |  |  |  | 2020-12-01
b3246.2 | PJM SOUTH | Perform substation work for the 115 kV to 230 kV Line conversion at Liberty, Wellington, Godwin, Pioneer, Sandlot and Cannon Branch. | Baseline | 230 | 20 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Modify | UC | 16 |  | 12/19/2025 |  | Yes | 12/1/2020 | 8/31/2021 | 60 |  |  |  | 2020-12-01
b3246.3 | PJM SOUTH | Extend 230kV Line #2011 Cannon Branch – Clifton to Winters Branch by removing the existing Line #2011 termination at Cannon Branch and extending the line to Brickyard creating 230kV Line #2011 Brickyard-Clifton. Extend a new 230kV line between Brickyard and Winters Branch with a summer rating of 1572MVA/1572MVA (SN/SE) | Baseline | 230 | 8 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Modify | IS | 10 |  | 8/9/2025 | 8/19/2025 | Yes | 12/1/2020 | 12/1/2020 | 100 |  |  |  | 2020-12-01
b3246.4 | PJM SOUTH | Perform substation work at Cannon Branch, Brickyard and Winters Branch for the 230kV Line #2011 extension. | Baseline | 230 | 14.1 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Modify | IS | 4 |  | 8/9/2025 | 8/19/2025 | Yes | 12/1/2020 | 12/1/2020 | 100 |  |  |  | 2020-12-01
b3246.5 | PJM SOUTH | Replace the Gainesville 230kV 40kA breaker “216192” with a 50kA breaker. | Baseline | 230 | 0.5 | 6/1/2023 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Replace | IS | 0.5 |  | 5/19/2023 | 5/15/2023 | Yes | 12/1/2020 | 12/1/2020 | 100 |  |  |  | 2020-12-01
b3317 | PJM WEST | Modify backup relay clearing times at the 138 kV STA16 Waukegan station. | Baseline | 138 | 0.26 | 6/1/2023 | ComEd |  | Appendix A | ComEd:100 |  | IL | Waukegan |  | Modify | Cancelled | 0.26 |  | 6/1/2023 |  | No | 5/21/2021 | 5/21/2021 | 0 |  |  |  | 2021-05-21
b3333.1 | PJM WEST | Rebuild Skeggs Branch substation in the clear as Mount Heron substation. Establish New 138kV and 69kV Buses. Install 138/69kV 130 MVA transformer, two 138kV breakers, 138kV Circuit Switcher, two 69kV breaker. Retire Existing Skeggs Branch substation | Baseline | 138/69 | 6.32 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Coronado station |  | Build | EP | 9.94 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.10 | PJM WEST | At Whetstone Branch substation, Replace 69KV 600A 2 Way POP Switch with 69KV 1200A 2 Way POP Switch. Remove 69KV to Skeggs Branch (Switch "22" POP). | Baseline | 69 | 0.57 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Whetstone |  | Replace | EP | 1.7 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.11 | PJM WEST | At Garden Creek substation, remove 69 kV Richlands (via Coal Creek) line (Circuit Breaker F and disconnect switches) and update relay settings. | Baseline | 69 | 0.14 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Garden Creek |  | Modify | EP | 0.54 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.12 | PJM WEST | Remote end work at Clinch River substation | Baseline | 69 | 0.08 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Clinch River |  | Upgrade | EP | 0.08 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.13 | PJM WEST | Remote end work at Clinchfield substation. Install ~2.6 mi greenfield 69kV line from greenfield Mount Heron station to the existing Horn Mountain S.S. | Baseline | 69 | 0.08 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Clinchfield |  | Upgrade | EP | 18.1 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.2 | PJM WEST | New ~1.6 mi double circuit 138kV extension to new Mount Heron substation location and work required to tap the Clinch River – Garden Creek 138kV line. Retire the existing Skeggs Branch 138kV Tap | Baseline | 138 | 4.62 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Skeggs Branch - Cornonado |  | Build | EP | 19.14 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.3 | PJM WEST | Install 57.6 MVAR Cap bank at Whitewood along with 138kV breaker. | Baseline | 138 | 1.05 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Whitewood |  | Install | EP | 2.76 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.4 | PJM WEST | Rebuild ~9 mi 69kV line from Horn Mountain SS to Permac switch. Rebuild from Str. 340-28 to Coal Creek station. 6-wire the short double circuit section between Whetstone Branch and Str. 340-28 to convert the line to single circuit. Retire Garden Creek to Whetstone Branch 69kV line section | Baseline | 69 | 26.25 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | new Skegges branch - Coal Creek, Garden Creek-Whet |  | Rebuild | EP | 45.3 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.5 | PJM WEST | Retire Knox Creek SS. | Baseline | 69 | 0.06 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Knox Creek |  | Retire | EP | 0.06 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.6 | PJM WEST | Horn Mountain SS, Replace 600A Switch and structure with 3 Way 1200A POP Pole Switch and pole | Baseline | 69 | 0.05 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Horn Mountain |  | Retire | EP | 1.99 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.7 | PJM WEST | At Clell SS, Replace (2) 600A POP Switches and Poles with single 3 Way 1200A POP Switch and Pole | Baseline | 69 | 0.34 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Clell |  | Replace | EP | 1.8 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.8 | PJM WEST | At Permac, replace 600A Switch and structure with 2 Way 1200A POP Pole Switch and pole. | Baseline | 69 | 0.31 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Permac |  | Replace | EP | 2.5 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3333.9 | PJM WEST | At Marvin SS, Replace 600A Switch and structure with 3 Way 1200A POP Pole Switch and pole | Baseline | 69 | 0.31 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | VA | Marvin SS |  | Replace | EP | 2.69 |  | 12/10/2027 |  | No | 8/31/2021 | 7/18/2025 | 0 |  | 12/10/2027 |  | 2021-08-31
b3350.1 | PJM WEST | Replace overdutied 69 kV breakers C, G, I, Z, AB and JJ in place. The new 69 kV breakers to be rated at 3000 A 40 kA breakers. | Baseline | 69 | 2 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | KY | Bellefonte |  | Replace | UC | 2 |  | 12/2/2026 |  | Yes | 1/21/2022 | 1/21/2022 | 75 |  |  |  | 2022-01-21
b3350.2 | PJM WEST | Upgrade remote end relaying at Point Pleasant, Coalton and South Point 69 kV substations. | Baseline | 69 | 0 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | KY | Point Pleasant, Coalton and South Point 69KV subst |  | Upgrade | EP | 0 |  | 12/23/2026 |  | Yes | 1/21/2022 | 1/21/2022 | 50 |  |  |  | 2022-01-21
b3354 | PJM WEST | Replace circuit breakers '42' and '43' at Bexley station with 3000 A, 40 kA 69 kV breakers (operated at 40 kV), slab, control cables and jumpers. | Baseline | 69 | 1 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | OH | Bexley Station. Columbus, OH 43219 |  | Replace | IS | 1 |  | 2/13/2025 | 2/14/2024 | Yes | 1/21/2022 | 1/21/2022 | 100 |  |  |  | 2022-01-21
b3355 | PJM WEST | Replace circuit breakers 'A' and 'B' at South Side Lima station with 1200 A, 25 kA 34.5 kV breakers, slab, control cables and jumpers. | Baseline | 34.5 | 0.75 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | OH | South Side Lima Station. Lima, OH 45801 |  | Replace | IS | 0.75 |  | 10/31/2022 | 12/29/2022 | Yes | 1/21/2022 | 1/21/2022 | 100 |  |  |  | 2022-01-21
b3356 | PJM WEST | Replace circuit breaker 'H' at West End Fostoria station with 3000 A, 40 kA 69 kV breaker, slab, control cables and jumpers. | Baseline | 69 | 0.5 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | OH | West End Fostroia Station. Fostoria, OH 44830 |  | Replace | IS | 0.5 |  | 6/1/2022 | 3/21/2022 | Yes | 1/21/2022 | 1/21/2022 | 100 |  |  |  | 2022-01-21
b3357 | PJM WEST | Replace circuit breakers 'C', 'E,' and 'L' at Natrium station with 3000 A, 40 kA 69 kV breakers, slab, control cables and jumpers. | Baseline | 69 | 1.5 | 6/1/2023 | AEP |  | Appendix A | AEP:100 |  | WV | Natrium Station. New Martinsville, WV 26155 |  | Replace | IS | 1.5 |  | 6/1/2022 | 5/20/2022 | Yes | 1/21/2022 | 1/21/2022 | 100 |  |  |  | 2022-01-21
b3702 | PJM SOUTH | Install one 13.5 Ohm series reactor to control the power flow on the 230 kV line #2054 from Charlottesville substation to Proffit Rd 230 kV line. | Baseline | 230 | 11.38 | 6/1/2023 | Dominion | 202021_1-651 | Appendix A | AEC:1.59,APS:8.85,ATSI:5.54,BGE:10.79,ComEd:1.86,Dayton:0.21,DEOK:1.16,DL:1.16,Dominion:18.99,DPL:3.68,ECP:0.27,HTP:0.22,JCPL:4.53,ME:1.73,Neptune:0.68,PECO:6.95,PENELEC:4.75,PEPCO:9.69,PPL:9.78,PSEG:7.28,RE:0.29 |  | VA | Charlottesville-Proffit |  | Install | Cancelled | 11.38 |  | 6/1/2025 |  | No | 11/30/2021 | 3/5/2024 | 30 |  |  |  | 2021-11-30
b3714 | PJM WEST | Beaver Substation terminal upgrades:• Replace (4) 345 kV disconnect switches (D74, D92, D93, & D116) with 3000 A disconnect switches at Beaver. • Replace dual 954 45/7 ACSR SCCIR conductors between 5” pipe and WT with new, which meets or exceeds ratings of SN: 1542 MVA, SSTE: 1878 MVA at Beaver.• Replace 3000 SAC TL drop and 3000 SAC SCCIR between 954 ACSR and 5” bus with new, which meets or exceeds ratings of SN: 1542 MVA, SSTE: 1878 MVA at Beaver. • Upgrade BDD relays at breaker B-88 and B-115 at Beaver.• Relay settings changes at Hayes. | Baseline | 345 | 2.1 | 6/1/2023 | ATSI |  | Appendix A | ATSI:100 |  | OH | Beaver to Hayes |  | Replace | IS | 2.1 |  | 11/22/2024 | 12/30/2024 | No | 6/7/2022 | 6/7/2022 | 100 |  |  |  | 2022-06-07
b3777 | PJM WEST | Disconnect and remove three 345 kV breakers, foundations and associated equipment from Sammis substation. Remove nine 345 kV CVTs. Remove two 345 kV disconnect switches. Install new 345 kV bus work and foundations. Install new fencing. Remove and adjust relaying at Sammis substation. | Baseline | 345 | 2.1 | 6/1/2023 | ATSI |  | Appendix A | ATSI:100 |  | OH | Sammis |  | Modify | IS | 2.1 |  | 11/8/2024 | 3/12/2025 | No | 5/9/2023 | 5/9/2023 | 100 |  |  |  | 2023-05-09
b3737.60 | PJM MA | Perform a Pre-build Infrastructure evaluation study in alignment with the NJBPU Solicitation Guidance Document requirements. | Baseline |  | 0.28 | 6/2/2023 | MAOD | 2021_SAA-550 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee |  | Engineering Oversight | IS | 0.29 |  | 6/2/2023 | 6/2/2023 | No | 5/9/2023 | 5/9/2023 | 100 |  |  |  | 2023-05-09
b3130.11 | PJM MA | Replace four Atlantic 34.5 kV breakers (BK1A, BK1B, BK3A and BK3B) with 63kA rated breakers and associated equipment | Baseline | 34.5 | 3.5 | 9/30/2023 | JCPL |  | Appendix A | JCPL:100 |  | NJ | Atlantic |  | Replace | IS | 3.5 |  | 10/15/2024 | 11/26/2024 | No | 5/16/2022 | 5/16/2022 | 100 |  |  |  | 2022-05-16
b3698 | PJM MA | Reconductor the 14.2 miles of the existing Juniata-Cumberland 230 kV line with 1272 ACSS/TW HS285 "Pheasant" conductor. | Baseline | 230 | 8.99 | 12/31/2023 | PPL | 202021_1-218 | Appendix A | AEC:4.17,BGE:13.18,DEOK:1.22,Dominion:3.25,DPL:9.14,ECP:0.11,EKPC:0.22,HTP:0.20,JCPL:1.15,ME:27.02,Neptune:0.64,PECO:18.88,PEPCO:4.68,PPL:16.14 |  | PA | Juniata-Cumberland |  | Upgrade | IS | 9 |  | 12/31/2023 | 12/14/2023 | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3130.12 | PJM MA | Replace six Werner 34.5 kV breakers (E31A_Prelim, E31B_Prelim, V48 future, W101, M39 and U99) with 40 kA rated breakers and associated equipment. | Baseline | 34.5 | 4.2 | 6/1/2024 | JCPL |  | Appendix A | JCPL:100 |  | NJ | Werner |  | Replace | IS | 4.2 |  | 2/9/2025 | 12/18/2024 | No | 5/16/2022 | 5/16/2022 | 100 |  |  |  | 2022-05-16
b3240 | PJM WEST | Upgrade Cherry Run and Morgan terminals to make the Transmission Line the limiting component. Morgan: Wave Trap Cherry Run: Substation conductor, relays, CT | Baseline | 138 | 1.1 | 6/1/2024 | APS |  | Appendix A | APS:100 |  | WV |  |  | Upgrade | IS | 0.23 |  | 6/18/2024 | 6/1/2024 | No | 11/20/2020 | 10/5/2021 | 100 |  |  |  | 2020-11-20
b3763 | PJM WEST | Replace the Jug Street 138kV breakers M, N, BC, BF, BD, BE, D, H, J, L, BG, BH, BJ, BK with 80KA breakers | Baseline | 138 | 14 | 6/1/2024 | AEP |  | Appendix A | AEP:100 |  | OH | Jug Street |  | Replace | IS | 14 |  | 6/1/2024 | 4/8/2025 | No | 12/16/2022 | 12/16/2022 | 100 |  |  |  | 2022-12-16
b3764 | PJM WEST | Replace the Hyatt 138kV breakers AB1 and AD1 with 63kA breakers | Baseline | 138 | 2 | 6/1/2024 | AEP |  | Appendix A | AEP:100 |  | OH | Hyatt |  | Replace | EP | 2 |  | 12/9/2025 |  | No | 12/16/2022 | 12/16/2022 | 50 |  |  |  | 2022-12-16
b3847.1 | PJM WEST | Add a 765 kV breaker at Baker station for the reactor on the Broadford 765 kV line. | Baseline | 765 | 23.36 | 6/1/2024 | AEP | Immediate Need | Appendix A | AEP:70.68,EKPC:8.12,PEPCO:21.20 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | KY | Baker |  | Install | EP | 23.36 |  | 6/25/2027 |  | Yes | 6/5/2024 | 6/5/2024 | 50 |  |  |  | 2024-06-05
b3847.2 | PJM WEST | Add two 765 kV breakers to the reactors at Broadford station on the Baker and Jacksons Ferry 765 kV lines. | Baseline | 765 | 29.05 | 6/1/2024 | AEP | Immediate Need | Appendix A | AEP:36.98,BGE:9.18,Dayton:0.04,DEOK:0.10,Dominion:40.81,EKPC:0.05,PEPCO:12.84 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Broadford |  | Install | EP | 29.05 |  | 6/19/2028 |  | Yes | 6/5/2024 | 6/5/2024 | 10 |  |  |  | 2024-06-05
b3847.3 | PJM WEST | Add a 765 kV breaker to the reactor at Jefferson station on the Greentown 765 kV line. | Baseline | 765 | 8.53 | 6/1/2024 | AEP | Immediate Need | Appendix A | AEP:64.50,DEOK:27.02,EKPC:6.06,OVEC:2.42 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | IN | Jefferson |  | Install | EP | 8.53 |  | 4/15/2027 |  | Yes | 6/5/2024 | 6/5/2024 | 50 |  |  |  | 2024-06-05
b3131.1 | PJM WEST | Rebuild approximately 12.3 miles of remaining Lark conductor on the double circuit line between Haviland and East Lima with 1033 54/7 ACSR conductor. | Baseline | 138 | 25.9 | 12/1/2024 | AEP |  | Appendix A | AEP:100 |  | OH | Haviland and East Lima |  | Rebuild | IS | 25.9 |  | 6/14/2024 | 6/17/2024 | No | 1/15/2021 | 1/15/2021 | 100 |  |  |  | 2021-01-15
b3717.1 | PJM WEST | Install a series reactor on Cheswick-Springdale 138 kV line | Baseline | 138 | 9 | 12/31/2024 | APS |  | Appendix A | APS:23.19,DL:76.81 |  | PA | Springdale |  | Install | EP | 7.36 |  | 3/17/2026 |  | Yes | 9/6/2022 | 9/5/2023 | 5 |  |  |  | 2022-09-06
b3717.2 | PJM WEST | Transmission Line Rearrangement: · Replacement of four structures and reconductor DLCO portion of Plum-Springdale 138 kV line. · Associated communication and relay setting changes at Plum and Cheswick. | Baseline | 138 | 8 | 12/31/2024 | DL |  | Appendix A | DL:100 |  | PA | Cheswick |  | Reconductor | IS | 15 |  | 12/31/2024 | 2/11/2025 | Yes | 9/6/2022 | 9/6/2022 | 100 |  |  |  | 2022-09-06
b3717.3 | PJM WEST | Relay work at Springdale 138 kV | Baseline | 138 | 1 | 12/31/2024 | APS |  | Appendix A | APS:100 |  | PA | Cheswick |  | Modify | EP | 1 |  | 1/24/2025 |  | No | 4/11/2023 | 4/11/2023 | 39 |  |  |  | 2023-04-11
b3716 | PJM MA | Construct a third 69kV supply line from Totowa substation to the customer’s substation | Baseline | 69 | 3.1 | 1/1/2025 | PSEG |  | Appendix A | PSEG:100 |  | NJ | Totowa |  | Build | IS | 8.2 |  | 5/17/2024 | 6/8/2024 | Yes | 6/13/2022 | 6/13/2022 | 100 |  |  |  | 2022-06-13
b3717.4 | PJM WEST | Transmission line work – a new transmission structure and necessary tower work to handle the change in tension at Cheswick 138 kV | Baseline | 138 | 2 | 1/1/2025 | APS |  | Appendix A | APS:100 |  | PA | Cheswick |  | Install | IS | 2 |  | 1/2/2025 | 1/2/2025 | No | 4/11/2023 | 4/11/2023 | 100 |  |  |  | 2023-04-11
b3221 | PJM MA | Replace terminal equipment (bus conductor) on the 230 kV side of the Steel City 500/230 kV transformer #1 | Baseline | 230 | 0.09 | 6/1/2025 | PPL |  | Appendix A | PPL:100 |  | PA | Steel City |  | Reconductor | IS | 0.09 |  | 11/27/2024 | 6/6/2024 | No | 11/4/2020 | 11/4/2020 | 100 |  |  |  | 2020-11-04
b3222 | PJM MA | Install one (1) 7.2 MVAR fixed cap bank on the Lock Haven-Reno 69 kV line and one (1) 7.2 MVAR fixed cap bank on the Lock Haven-Flemington 69 kV line near the Flemington 69/12kV substation. | Baseline | 69 | 1.9 | 6/1/2025 | PPL |  | Appendix A | PPL:100 |  | PA |  |  | Install | IS | 1.9 |  | 6/1/2024 | 1/31/2024 | No | 11/18/2020 | 11/18/2020 | 100 |  |  |  | 2020-11-18
b3224 | PJM MA | Replace a disconnect switch and reconductor a short span of Mt. Pleasant - Middletown Tap line | Baseline | 138 | 0.43 | 6/1/2025 | DPL |  | Appendix A | DPL:100 |  | DE |  |  | Replace | EP | 0.42 |  | 12/31/2027 |  | No | 11/18/2020 | 11/18/2020 | 10 |  |  |  | 2020-11-18
b3226 | PJM MA | Add 10 MVAR 69 kV capacitor bank at Swainton substation | Baseline | 69 | 3.86 | 6/1/2025 | AEC |  | Appendix A | AEC:100 |  | NJ | Swainton substation |  | Install | IS | 2.9 |  | 5/31/2025 | 5/16/2025 | No | 11/18/2020 | 11/18/2020 | 100 |  |  |  | 2020-11-18
b3227 | PJM MA | Rebuild the Corson-Court 69 kV line to achieve ratings equivalent to 795 ACSR conductor or better | Baseline | 69 | 45.3 | 6/1/2025 | AEC |  | Appendix A | AEC:100 |  | NJ | Corson-Court 69 kV line |  | Rebuild | EP | 13.2 |  | 6/1/2026 |  | No | 11/18/2020 | 11/18/2020 | 46 |  |  |  | 2020-11-18
b3228 | PJM MA | Replace two relays at Center Substation to increase ratings on the 110552 circuit | Baseline | 115 | 0.02 | 6/1/2025 | BGE |  | Appendix A | BGE:100 |  | MD |  |  | Replace | IS | 0.02 |  | 6/1/2025 | 12/12/2024 | No | 11/18/2020 | 11/18/2020 | 100 |  |  |  | 2020-11-18
b3230 | PJM WEST | At Enon Substation install a second 138 kV, 28.8 MVAR nameplate, capacitor and the associated 138 kV capacitor switcher. | Baseline | 138 | 1.84 | 6/1/2025 | APS |  | Appendix A | APS:100 |  | PA |  |  | Install | IS | 1.8 |  | 10/13/2024 | 10/13/2024 | No | 11/20/2020 | 12/18/2020 | 100 |  |  |  | 2020-11-20
b3231 | PJM MA | Replace the existing No. 2 cap bank breaker at Huntingdon substation with a new breaker with higher interrupting capability. | Baseline | 46 | 0.8 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA |  |  | Replace | IS | 0.8 |  | 6/1/2023 | 6/1/2023 | No | 11/18/2020 | 11/18/2020 | 100 |  |  |  | 2020-11-18
b3232 | PJM MA | Replace the existing Williamsburg, ALH (Hollidaysburg) and bus section breaker at the Altoona substation with a new breaker with higher interrupting capability. | Baseline | 46 | 1.7 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA |  |  | Replace | EP | 1.7 |  | 6/1/2025 |  | No | 11/18/2020 | 11/18/2020 | 0 |  |  |  | 2020-11-18
b3233 | PJM MA | Install one 34 MVAR 115 kV shunt reactor and breaker. Install one 115 kV circuit breaker to expand the substation to a 4 breaker ring bus. | Baseline | 115 | 4.9 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA |  |  | Install | EP | 4.9 |  | 12/31/2027 |  | No | 11/18/2020 | 11/18/2020 | 3 |  |  |  | 2020-11-18
b3234 | PJM WEST | Extend both the east and west 138 kV buses at Pine substation, and install one 138 kV breaker, associated disconnect switches, and one 100 MVAR reactor. | Baseline | 138 | 3.8 | 6/1/2025 | ATSI |  | Appendix A | ATSI:100 |  | PA |  |  | Install | EP | 3.8 |  | 11/1/2027 |  | No | 10/16/2020 | 11/20/2020 | 2 |  |  |  | 2020-10-16
b3235 | PJM WEST | Extend 138 kV bus work to the west of Tangy substation for the addition of the 100 MVAR reactor bay and one 138 kV 40 kA circuit breaker. | Baseline | 138 | 3.7 | 6/1/2025 | ATSI |  | Appendix A | ATSI:100 |  | OH |  |  | Install | EP | 3.7 |  | 6/1/2027 |  | No | 10/16/2020 | 11/20/2020 | 4 |  |  |  | 2020-10-16
b3236 | PJM WEST | Extend the 138 kV Bus by adding two new breakers and associated equipment and install a 75 MVAR Reactor | Baseline | 138 | 4.5 | 6/1/2025 | ATSI |  | Appendix A | ATSI:100 |  | OH |  |  | Install | EP | 4.5 |  | 8/10/2027 |  | No | 10/16/2020 | 11/20/2020 | 1 |  |  |  | 2020-10-16
b3237 | PJM MA | Install two 46 kV 6.12 MVAR capacitors effective at Mt Union. | Baseline | 46 | 4 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA |  |  | Install | UC | 4 |  | 7/1/2025 |  | No | 11/18/2020 | 11/18/2020 | 75 |  |  |  | 2020-11-18
b3238 | PJM MA | Replace (7) overdutied 34.5 kV breakers with 50 kA rated equipment at the Whippany substation. | Baseline | 34.5 | 5.1 | 6/1/2025 | JCPL |  | Appendix A | JCPL:100 |  | NJ |  |  | Replace | UC | 8.67 |  | 3/31/2026 |  | No | 11/18/2020 | 11/18/2020 | 75 |  |  |  | 2020-11-18
b3239 | PJM MA | Replace (14) overdutied 34.5 kV breakers with 63 kA rated equipment. | Baseline | 34.5 | 8.5 | 6/1/2025 | JCPL |  | Appendix A | JCPL:100 |  | NJ |  |  | Replace | EP | 5.7 |  | 6/1/2025 |  | No | 11/18/2020 | 11/18/2020 | 0 |  |  |  | 2020-11-18
b3241 | PJM WEST | Install 138 kV, 36 MVAR capacitor and a 5 uF reactor protected by a 138 kV capacitor switcher. Install a breaker on the 138 kV Junction terminal. Install a 138 kV 3.5 uF reactor on the existing Hardy 138 kV capacitor. | Baseline | 138 | 2.85 | 6/1/2025 | APS |  | Appendix A | APS:100 |  | WV |  |  | Install | IS | 2.85 |  | 5/30/2025 | 6/13/2025 | No | 11/20/2020 | 12/18/2020 | 100 |  |  |  | 2020-11-20
b3242 | PJM WEST | Reconfigure Stonewall 138 kV substation from its current configuration to a six-breaker breaker-and-a-half layout and add two 36 MVAR capacitors with capacitor switchers. | Baseline | 138 | 13.3 | 6/1/2025 | APS |  | Appendix A | APS:100 |  | VA |  |  | Modify | UC | 13.3 |  | 6/1/2027 |  | No | 11/20/2020 | 12/18/2020 | 80 |  |  |  | 2020-11-20
b3243 | PJM WEST | Replace risers at Bass 34.5kV station | Baseline | 34.5 | 0.1 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | IN | Bass |  | Replace | EP | 0.1 |  | 11/3/2025 |  | No | 11/20/2020 | 11/20/2020 | 0 |  |  |  | 2020-11-20
b3244 | PJM WEST | Rebuild approximately 9 miles of the Rob Park - Harlan 69 kV line | Baseline | 69 | 20.9 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | IN | Rob Park-Harlan |  | Rebuild | EP | 20.9 |  | 7/24/2025 |  | No | 11/20/2020 | 11/20/2020 | 0 |  |  |  | 2020-11-20
b3245 | PJM MA | Construct a new breaker-and-a-half substation near Tiffany substation. All transmission assets and lines will be relocated to the new substation. The two distribution transformers will be fed via two dedication 115 kV feeds to the existing Tiffany substation. | Baseline | 115 | 23.2 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA |  |  | Construct | EP | 23.2 |  | 6/5/2026 |  | No | 11/18/2020 | 11/18/2020 | 20 |  |  |  | 2020-11-18
b3247 | PJM SOUTH | Replace 13 towers with galvanized steel towers on Doubs - Goose Creek 500 kV. Reconductor 3 mile section with 3-1351.5 ACSR 45/7. Upgrade line terminal equipment at Goose Creek substation to support the 500 kV line rebuild. | Baseline | 500 | 7.6 | 6/1/2025 | Dominion | 2020-W2-441 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Doubs - Goose Creek |  | Reconductor | Cancelled | 7.6 |  | 6/1/2025 |  | Yes | 9/1/2020 | 12/5/2023 | 10 |  |  |  | 2020-09-01
b3248 | PJM WEST | Install a low side 69 kV circuit breaker at Albion 138/69 kV transformer 1 | Baseline | 69 | 0.4 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | IN | Albion |  | Install | EP | 0.4 |  | 10/2/2028 |  | No | 11/20/2020 | 11/20/2020 | 0 |  |  |  | 2020-11-20
b3249 | PJM WEST | Rebuild the Chatfield-Melmore 138kV line (~ 10 miles) to 1033 ACSR conductor. | Baseline | 138 | 27.2 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Chatfield-Melmore |  | Rebuild | EP | 27.2 |  | 2/24/2026 |  | No | 2/17/2021 | 2/17/2021 | 0 |  |  |  | 2021-02-17
b3253 | PJM WEST | Install a 3000A 40 kA 138 kV breaker on high side of 138/69 kV transformer #5 at Millbrook Park station. The transformer and associated bus protection will be upgraded accordingly. | Baseline | 138 | 0.63 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Millbrook Park |  | Install | UC | 0.63 |  | 3/14/2028 |  | No | 11/20/2020 | 11/20/2020 | 26 |  |  |  | 2020-11-20
b3255 | PJM WEST | Upgrade 795 AAC risers at Sand Hill 138 kV station towards Cricket Switch with 1272 AAC | Baseline | 138 | 0.04 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | WV | Sand Hill |  | Upgrade | IS | 0.04 |  | 9/1/2024 | 6/30/2022 | No | 11/20/2020 | 11/20/2020 | 100 |  |  |  | 2020-11-20
b3256 | PJM WEST | Upgrade 500 MCM Cu risers at Tidd 138 kV station towards Wheeling Steel; replace with 1272 AAC conductor | Baseline | 138 | 0.07 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Tidd |  | Upgrade | IS | 0.07 |  | 9/1/2021 | 9/30/2019 | No | 11/20/2020 | 11/20/2020 | 100 |  |  |  | 2020-11-20
b3257 | PJM WEST | Replace two spans of 336.4 26/7 ACSR on Twin Branch-AM General #2 34.5 kV circuit | Baseline | 34.5 | 0.14 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | IN | Twin Branch-AM General #2 |  | Replace | IS | 0.14 |  | 3/17/2024 | 12/14/2023 | No | 11/20/2020 | 11/20/2020 | 100 |  |  |  | 2020-11-20
b3258 | PJM WEST | Install a 3000A 63 kA 138 kV breaker on high side of 138/69 kV transformer #2 at Wagenhals station. The transformer and associated bus protection will be upgraded accordingly. | Baseline | 138 | 1.1 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Wagenhals |  | Install | EP | 1.1 |  | 6/4/2027 |  | No | 11/20/2020 | 11/20/2020 | 0 |  |  |  | 2020-11-20
b3259 | PJM WEST | At West Millersburg station, replace the 138 kV MOAB on the West Millersburg - Wooster 138 kV line with a 3000A 40 kA breaker. | Baseline | 138 | 0.68 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | West Millersburg |  | Install | EP | 0.68 |  | 9/1/2024 |  | No | 11/20/2020 | 11/20/2020 | 0 |  |  |  | 2020-11-20
b3264 | PJM SOUTH | Install 115kV breaker at Stuarts Draft station and sectionalize 115kV Line#117 into two 115kV lines. | Baseline | 115 | 5 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Install | EP | 5 |  | 5/30/2025 |  | No | 11/4/2020 | 1/14/2021 | 0 |  |  |  | 2020-11-04
b3265 | PJM WEST | Implement slow circulation on existing underground 138 kV high pressure fluid filled (HPFF) cable between Arsenal and Riazzi substations. | Baseline | 138 | 2.7 | 6/1/2025 | DL |  | Appendix A | DL:100 |  | PA | Arsenal-Riazzi |  | Modify | IS | 2.4 |  | 12/31/2023 | 12/15/2023 | No | 11/20/2020 | 11/20/2020 | 100 |  |  |  | 2020-11-20
b3269 | PJM WEST | At West New Philadelphia station, add a high side 138 kV breaker on the 138/69 kV transformer #2 along with a 138 kV breaker on the line towards Newcomerstown. | Baseline | 138/69 | 2.02 | 6/1/2025 | AEP | 2020_1-179 | Appendix A | AEP:100 |  | OH | West New Philadelphia |  | Add | EP | 2.02 |  | 4/13/2028 |  | No | 10/6/2020 | 11/4/2020 | 0 |  |  |  | 2020-10-06
b3270 | PJM WEST | Install 1.7 miles of 795 ASCR 138kV conductor along the other side of Dragoon Tap 138 kV line, which is currently double circuit tower with one position open. Additionally, install a 2nd 138/34.5 kV transformer at Dragoon, install a high side circuit switcher on the current transformer at Dragoon Station, and install 2-138 kV line breakers on the Dragoon-Jackson 138 kV and Dragoon-Twin Branch 138 kV lines. | Baseline | 138/34.5 | 4.89 | 6/1/2025 | AEP | 2020_1-308 | Appendix A | AEP:100 |  | IN | Dragoon, Dragoon-Jackson, Dragoon - Twin Branch |  | Install | UC | 4.89 |  | 12/19/2025 |  | No | 10/6/2020 | 11/4/2020 | 75 |  |  |  | 2020-10-06
b3270.1 | PJM WEST | Replace Dragoon 34.5 kV Breakers "B", "C" and "D" with 40 kA breakers. | Baseline | 34.5 | 2 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | IN | Dragoon |  | Replace | EP | 2 |  | 1/1/2025 |  | No | 11/4/2020 | 11/4/2020 | 0 |  |  |  | 2020-11-04
b3271 | PJM WEST | Install a 138 kV circuit breaker at Fremont station on line towards Fremont Center and install a 9.6 MVAR 69 kV capacitor bank at Bloom Road station. | Baseline | 138/69 | 1.76 | 6/1/2025 | AEP | 2020_1-503 | Appendix A | AEP:100 |  | OH | Fremont, Bloom Road |  | Install | EP | 1.76 |  | 9/1/2024 |  | No | 10/6/2020 | 11/4/2020 | 25 |  |  |  | 2020-10-06
b3272 | PJM WEST | Install two 138 kV circuit switchers on the high side of 138/34.5 kV transformers #1 & #2 at Rockhill station. | Baseline | 138 | 1.47 | 6/1/2025 | AEP | 2020_1-848 | Appendix A | AEP:100 |  | OH | Rockhill |  | Install | EP | 1.47 |  | 6/1/2025 |  | No | 10/6/2020 | 11/4/2020 | 0 |  |  |  | 2020-10-06
b3273.1 | PJM WEST | Rebuild and convert the existing 17.6 miles East Leipsic-New Liberty 34.5 kV circuit to 138 kV using 795 ACSR | Baseline | 138/34.5 | 31.35 | 6/1/2025 | AEP | 2020_1-957 | Appendix A | AEP:100 |  | OH | East Leipsic-New Liberty |  | Rebuild | EP | 31.35 |  | 11/17/2027 |  | No | 12/1/2020 | 12/1/2020 | 25 |  |  |  | 2020-12-01
b3273.2 | PJM WEST | Convert the existing 34.5 kV equipment to 138 kV and expanded the existing McComb station to the north and east to allow for new equipment to be installed. Install two new 138 kV box bays to allow for line positions and two new 138/12 kV transformers. | Baseline | 138/12 | 0.87 | 6/1/2025 | AEP | 2020_1-957 | Appendix A | AEP:100 |  | OH | McComb |  | Upgrade | EP | 0.87 |  | 2/2/2027 |  | No | 12/1/2020 | 12/1/2020 | 25 |  |  |  | 2020-12-01
b3273.3 | PJM WEST | Expand the existing East Leipsic 138 kV station to the north to allow for another 138 kV line exit to be installed. The new line exit will involve installing a new 138 kV circuit breaker, disconnect switches and new dead end structure along with extending existing 138 kV bus work. | Baseline | 138 | 1.3 | 6/1/2025 | AEP | 2020_1-957 | Appendix A | AEP:100 |  | OH | East Leipsic |  | Upgrade | EP | 1.3 |  | 11/17/2027 |  | No | 12/1/2020 | 12/1/2020 | 25 |  |  |  | 2020-12-01
b3273.4 | PJM WEST | Add one 138 kV circuit breaker and disconnect switches in order to add an additional line position at New Liberty 138 kV station. Install line relaying potential devices and retire the 34.5 kV breaker F. | Baseline | 138/34.5 | 0.9 | 6/1/2025 | AEP | 2020_1-957 | Appendix A | AEP:100 |  | OH | New Liberty |  | Install | EP | 0.9 |  | 8/19/2027 |  | No | 12/1/2020 | 12/1/2020 | 25 |  |  |  | 2020-12-01
b3274 | PJM WEST | Rebuild approximately 8.9 miles of 69 kV line between Newcomerstown and Salt Fork Switch with 556 ACSR conductor. | Baseline | 69 | 15.89 | 6/1/2025 | AEP | 2020_1-182 | Appendix A | AEP:100 |  | OH | Newcomerstown-Salt Fork Switch |  | Rebuild | EP | 15.89 |  | 6/1/2025 |  | No | 12/1/2020 | 12/1/2020 | 0 |  |  |  | 2020-12-01
b3275.1 | PJM WEST | Rebuild Kammer Station-Cresaps Switch 69 kV, approximately 0.5 miles. | Baseline | 69 | 0.93 | 6/1/2025 | AEP | 2020_1-804 | Appendix A | AEP:100 |  | WV | Kammer Station-Cresaps Switch |  | Rebuild | IS | 0.93 |  | 9/4/2025 | 5/8/2025 | No | 12/1/2020 | 12/1/2020 | 100 |  |  |  | 2020-12-01
b3275.2 | PJM WEST | Rebuild Cresaps Switch-McElroy Station 69 kV, approximately 0.67 miles. | Baseline | 69 | 1.25 | 6/1/2025 | AEP | 2020_1-804 | Appendix A | AEP:100 |  | WV | Cresaps Switch-McElroy Station |  | Rebuild | EP | 1.25 |  | 9/4/2025 |  | No | 12/1/2020 | 12/1/2020 | 15 |  |  |  | 2020-12-01
b3275.3 | PJM WEST | Replace a single span of 4/0 ACSR from Moundsville-Natrium str 93L to Carbon Tap switch 69kV located between Colombia Carbon and Conner Run stations. Remainder of line is 336 ACSR. | Baseline | 69 | 0.01 | 6/1/2025 | AEP | 2020_1-804 | Appendix A | AEP:100 |  | WV | Moundsville-Natrium str 93L |  | Replace | IS | 0.01 |  | 9/4/2025 | 3/6/2025 | No | 12/1/2020 | 12/1/2020 | 100 |  |  |  | 2020-12-01
b3275.4 | PJM WEST | Rebuild from Colombia Carbon to Columbia Carbon Tap str 93N 69 kV, approximately 0.72 miles. The remainder of the line between Colombia Carbon Tap structure 93N and Natrium station is 336 ACSR and will remain. | Baseline | 69 | 1.08 | 6/1/2025 | AEP | 2020_1-804 | Appendix A | AEP:100 |  | WV | Colombia Carbon-Columbia Carbon Tap str 93N |  | Rebuild | IS | 1.08 |  | 9/4/2025 | 3/6/2025 | No | 12/1/2020 | 12/1/2020 | 100 |  |  |  | 2020-12-01
b3275.5 | PJM WEST | Replace the Cresaps 69 kV 3-Way Phase-Over-Phase Switch and structure with a new 1200 A 3-Way Switch and Steel Pole. | Baseline | 69 | 0.71 | 6/1/2025 | AEP | 2020_1-804 | Appendix A | AEP:100 |  | WV | Cresaps |  | Replace | IS | 0.71 |  | 9/4/2025 | 5/8/2025 | No | 12/1/2020 | 12/1/2020 | 100 |  |  |  | 2020-12-01
b3275.6 | PJM WEST | Replace 477 MCM Alum bus and risers at McElroy 69 kV station. | Baseline | 69 | 0.33 | 6/1/2025 | AEP | 2020_1-804 | Appendix A | AEP:100 |  | WV | McElroy |  | Replace | EP | 0.32 |  | 9/4/2025 |  | No | 12/1/2020 | 12/1/2020 | 15 |  |  |  | 2020-12-01
b3275.7 | PJM WEST | Replace Natrium 138 kV bus existing between CB-BT1 and along the 138 kV Main Bus # 1 dropping to CBH1 from the 500MCM conductors to a 1272 KCM AAC conductor. Replace the dead end clamp and strain insulators. | Baseline | 69 | 0.29 | 6/1/2025 | AEP | 2020_1-804 | Appendix A | AEP:100 |  | WV | Natrium |  | Replace | EP | 0.29 |  | 11/26/2025 |  | No | 12/1/2020 | 12/1/2020 | 75 |  |  |  | 2020-12-01
b3276.1 | PJM WEST | Rebuild the 2/0 Copper section of the Lancaster-South Lancaster 69 kV line, approximately 2.9 miles of the 3.2 mile total length with 556 ACSR conductor. The remaining section has 336 ACSR conductor. | Baseline | 69 | 5.37 | 6/1/2025 | AEP | 2020_1-915 | Appendix A | AEP:100 |  | OH | Lancaster-South Lancaster |  | Rebuild | EP | 5.37 |  | 12/31/2030 |  | No | 12/1/2020 | 12/1/2020 | 0 |  |  |  | 2020-12-01
b3276.2 | PJM WEST | Rebuild the 1/0 Copper section of the line between Lancaster Junction and Ralston station 69 kV, approximately 2.3 miles of the 3.1 mile total length. | Baseline | 69 | 4.58 | 6/1/2025 | AEP | 2020_1-915 | Appendix A | AEP:100 |  | OH | Lancaster Junction-Ralston |  | Rebuild | EP | 4.58 |  | 12/31/2030 |  | No | 12/1/2020 | 12/1/2020 | 0 |  |  |  | 2020-12-01
b3276.3 | PJM WEST | Rebuild the 2/0 Copper portion of the line between East Lancaster Tap and Lancaster 69 kV, approximately 0.81 miles. | Baseline | 69 | 1.2 | 6/1/2025 | AEP | 2020_1-915 | Appendix A | AEP:100 |  | OH | East Lancaster Tap-Lancaster |  | Rebuild | EP | 1.2 |  | 7/16/2026 |  | No | 12/1/2020 | 12/1/2020 | 15 |  |  |  | 2020-12-01
b3279 | PJM WEST | Install a new 138 kV, 21.6 MVAR cap bank and circuit switcher at Apple Grove Station. | Baseline | 138 | 1 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | WV | Apple Grove |  | Install | EP | 1 |  | 4/1/2027 |  | No | 2/17/2021 | 2/17/2021 | 10 |  |  |  | 2021-02-17
b3280 | PJM WEST | Rebuild the existing Cabin Creek - Kelly Creek 46 kV line (to structure 366-44), approximately 4.4 miles. This section is double circuit with the existing Cabin Creek - London 46 kV line so a double circuit rebuild would be required. | Baseline | 46 | 17.9 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | WV | Cabin Creek – Kelly Creek |  | Rebuild | EP | 17.9 |  | 10/15/2026 |  | No | 1/15/2021 | 1/15/2021 | 50 |  |  |  | 2021-01-15
b3282.1 | PJM WEST | Install a second 138 kV circuit utilizing 795 ACSR conductor on the open position of the existing double circuit towers from East Huntington-North Proctorville. Remove the existing 34.5 kV line from East Huntington-North Chesapeake and rebuild this section to 138 kV served from a new PoP switch off the new East Huntington-North Proctorville 138 kV #2 line. | Baseline | 138/34.5 | 7.1 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | WV | East Huntington-North Proctorville, East Huntingto |  | Install | EP | 7.1 |  | 3/21/2029 |  | No | 2/17/2021 | 2/17/2021 | 10 |  |  |  | 2021-02-17
b3282.2 | PJM WEST | Install a 138 kV 40 kA circuit breaker at North Proctorville. | Baseline | 138 | 1.4 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | WV | North Proctorville |  | Install | EP | 1.4 |  | 3/21/2029 |  | No | 2/17/2021 | 2/17/2021 | 10 |  |  |  | 2021-02-17
b3282.3 | PJM WEST | Install a 138 kV 40 kA circuit breaker at East Huntington. | Baseline | 138 | 1.1 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | WV | East Huntington |  | Install | EP | 1.1 |  | 3/21/2029 |  | No | 2/17/2021 | 2/17/2021 | 10 |  |  |  | 2021-02-17
b3282.4 | PJM WEST | Convert the existing 34/12 kV North Chesapeake to a 138/12 kV station. | Baseline | 138/12 | 0.8 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | WV | North Chesapeake |  | Modify | EP | 0.8 |  | 3/21/2029 |  | No | 2/17/2021 | 2/17/2021 | 10 |  |  |  | 2021-02-17
b3284 | PJM WEST | Rebuild ~5.44 miles of 69 kV line from Lock Lane to Point Pleasant. | Baseline | 69 | 13.5 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | WV | Lock Lane - Point Pleasant |  | Rebuild | EP | 13.5 |  | 9/10/2027 |  | No | 1/15/2021 | 1/15/2021 | 50 |  |  |  | 2021-01-15
b3285 | PJM WEST | Replace the Meigs 69 kV 4/0 Cu station riser towards Gavin and rebuild the section of the Meigs – Hemlock 69 kV circuit from Meigs to approximately structure #40 (~4 miles) replacing the line conductor 4/0 ACSR with the line conductor size 556.5 ACSR. | Baseline | 69 | 12.14 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Meigs, Meigs-Hemlock |  | Rebuild | UC | 12.14 |  | 2/2/2026 |  | No | 1/15/2021 | 1/15/2021 | 75 |  |  |  | 2021-01-15
b3286 | PJM WEST | Reconductor the first 3 spans from Merrimac station to Str. 464-3 of 3/0 ACSR conductor utilizing 336 ACSR on the existing Merrimac – Midway 69 kV circuit. | Baseline | 69 | 0.45 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | VA | Merrimac - Midway |  | Reconductor | Cancelled | 0.45 |  | 6/1/2025 |  | No | 1/15/2021 | 6/15/2021 | 0 |  |  |  | 2021-01-15
b3287 | PJM WEST | Upgrade 69 kV risers at Moundsville station towards George Washington. | Baseline | 69 | 0.05 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Moundsville |  | Replace | IS | 0.05 |  | 9/1/2024 | 6/30/2022 | No | 1/15/2021 | 1/15/2021 | 100 |  |  |  | 2021-01-15
b3289.1 | PJM WEST | Roanoke Station: Install high-side circuit switcher on 138/69/12 kV T5 | Baseline | 138/69/12 | 1.1 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | VA | Roanoke |  | Install | EP | 1.1 |  | 8/18/2027 |  | No | 1/15/2021 | 1/15/2021 | 10 |  |  |  | 2021-01-15
b3289.2 | PJM WEST | Huntington Court Station: Install high-side circuit switcher on 138/69/34.5 kV T1 | Baseline | 138/69/34.5 | 1.42 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | VA | Huntington Court |  | Install | EP | 1.42 |  | 5/21/2026 |  | No | 1/15/2021 | 1/15/2021 | 50 |  |  |  | 2021-01-15
b3290.1 | PJM WEST | Build 9.4 miles of single circuit 69 kV line from Roselms to near East Ottoville 69 kV Switch. | Baseline | 69 | 13.7 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Roselms - East Ottoville Switch |  | Modify | EP | 13.7 |  | 6/7/2027 |  | No | 1/15/2021 | 1/15/2021 | 50 |  |  |  | 2021-01-15
b3290.2 | PJM WEST | Rebuild 7.5 miles of double circuit 69kV line between East Ottoville Switch and Kalida Station (combining with the new Roselms to Kalida 69 kV circuit). | Baseline | 69 | 23.6 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | East Ottoville Switch - Kalida |  | Modify | EP | 23.6 |  | 2/19/2027 |  | No | 1/15/2021 | 1/15/2021 | 50 |  |  |  | 2021-01-15
b3290.3 | PJM WEST | At Roselms Switch, install a new three way 69kV, 1200 A phase-over-phase switch, with sectionalizing capability. | Baseline | 69 | 0.6 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Roselms Switch |  | Install | EP | 0.6 |  | 6/7/2027 |  | No | 1/15/2021 | 1/15/2021 | 50 |  |  |  | 2021-01-15
b3290.4 | PJM WEST | At Kalida 69 kV station, terminate the new line from Roselms Switch. Move the CS XT2 from high side of T2 to the high side of T1. Remove existing T2 transformer. | Baseline | 69 | 1 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Kalida |  | Modify | EP | 1 |  | 6/18/2027 |  | No | 1/15/2021 | 1/15/2021 | 50 |  |  |  | 2021-01-15
b3291 | PJM WEST | Replace the Russ St. 34.5 kV Switch | Baseline | 34.5 | 1.5 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | IN | Russ St. |  | Replace | EP | 1.5 |  | 10/23/2026 |  | No | 1/15/2021 | 1/15/2021 | 50 |  |  |  | 2021-01-15
b3293 | PJM WEST | Replace 2/0 Cu entrance span conductor on the South Upper Sandusky 69 kV line and 4/0 Cu Risers/Bus conductors on the Forest line at Upper Sandusky 69 kV station. | Baseline | 69 | 0.54 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Upper Sandusky |  | Replace | IS | 0.54 |  | 6/1/2025 | 1/25/2024 | No | 1/15/2021 | 1/15/2021 | 100 |  |  |  | 2021-01-15
b3294 | PJM WEST | Replace existing 69 kV disconnect switches for circuit breaker "C" at Walnut Avenue station | Baseline | 69 | 0 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | VA | Walnut Avenue |  | Replace | EP | 0 |  | 8/5/2027 |  | No | 1/15/2021 | 1/15/2021 | 10 |  |  |  | 2021-01-15
b3295 | PJM WEST | Grundy 34.5 kV: Install a 34.5 kV 9.6 MVAR cap bank | Baseline | 34.5 | 0.8 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | VA | Grundy |  | Install | Cancelled | 0.8 |  | 5/1/2028 |  | No | 2/17/2021 | 2/17/2021 | 0 |  |  |  | 2021-02-17
b3296 | PJM WEST | Rebuild the overloaded portion of the Concord-Whitaker 34.5 kV line (1.13 miles). Rebuild is double circuit and will utilize 795 ACSR conductor. | Baseline | 34.5 | 2.8 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | IN | Concord-Whitaker |  | Rebuild | EP | 2.8 |  | 8/30/2027 |  | No | 1/15/2021 | 1/15/2021 | 25 |  |  |  | 2021-01-15
b3297.1 | PJM WEST | Rebuild 4.23 miles of 69 kV line between Sawmill and Lazelle station, using 795 ACSR 26/7 conductor. | Baseline | 69 | 12 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Sawmill-Lazelle |  | Rebuild | EP | 12 |  | 7/22/2026 |  | No | 1/15/2021 | 1/15/2021 | 10 |  |  |  | 2021-01-15
b3297.2 | PJM WEST | Rebuild 1.94 miles of 69 kV line between Westerville and Genoa stations, using 795 ACSR 26/7 conductor. | Baseline | 69 | 5.9 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Westerville-Genoa |  | Rebuild | EP | 5.9 |  | 5/8/2027 |  | No | 1/15/2021 | 1/15/2021 | 10 |  |  |  | 2021-01-15
b3297.3 | PJM WEST | Replace risers and switchers at Lazelle, Westerville, and Genoa 69 kV stations. Upgrade associated relaying accordingly. | Baseline | 69 | 1.9 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Lazelle, Westerville, Genoa |  | Replace | EP | 1.9 |  | 7/22/2026 |  | No | 1/15/2021 | 1/15/2021 | 10 |  |  |  | 2021-01-15
b3298 | PJM WEST | Rebuild 0.8 miles of double circuit 69 kV line between South Toronto and West Toronto. Replace 219 kcmil ACSR with 556 ACSR. | Baseline | 69 | 2.83 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | South Toronto-West Toronto |  | Rebuild | EP | 2.83 |  | 4/10/2028 |  | No | 2/17/2021 | 2/17/2021 | 10 |  |  |  | 2021-02-17
b3298.1 | PJM WEST | Replace the 69 kV breaker D at South Toronto station with 40 kA breaker. | Baseline | 69 | 0.7 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | South Toronto |  | Replace | EP | 0.7 |  | 5/19/2026 |  | No | 2/17/2021 | 2/17/2021 | 10 |  |  |  | 2021-02-17
b3299 | PJM WEST | Rebuild 0.2 mile of the West End Fostoria - Lumberjack Switch 69 kV line with 556 ACSR (Dove) conductors. Replace jumpers on West End Fostoria line at Lumberjack Switch. | Baseline | 69 | 0.47 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | West End Fostoria - Lumberjack Switch |  | Rebuild | IS | 0.47 |  | 7/30/2025 | 2/14/2025 | No | 1/15/2021 | 1/15/2021 | 100 |  |  |  | 2021-01-15
b3300 | PJM SOUTH | Reconductor 230kV Line #2172 from Brambleton to Evergreen Mills along with upgrading the line leads at Brambleton to achieve a summer emergency rating of 1574 MVA. | Baseline | 230 | 2.32 | 6/1/2025 | Dominion | 2020_W1-26 | Appendix A | Dominion:100 |  | VA | Brambleton, Evergreen Mills |  | Reconductor | UC | 2.32 |  | 7/31/2026 |  | No | 12/1/2020 | 1/6/2021 | 60 |  |  |  | 2020-12-01
b3301 | PJM SOUTH | Reconductor 230kV Line #2210 from Brambleton to Evergreen Mills along with upgrading the line leads at Brambleton to achieve a summer emergency rating of 1574 MVA. | Baseline | 230 | 2.26 | 6/1/2025 | Dominion | 2020-W1-735 | Appendix A | Dominion:100 |  | VA | Brambleton, Evergreen Mills |  | Reconductor | UC | 2.26 |  | 7/31/2026 |  | No | 12/1/2020 | 1/6/2021 | 60 |  |  |  | 2020-12-01
b3302 | PJM SOUTH | Reconductor 230kV Line #2213 from Cabin Run to Yardley Ridge along with upgrading the line leads at Yardley to achieve a summer emergency rating of 1574 MVA. | Baseline | 230 | 1.75 | 6/1/2025 | Dominion | 2020-W1-134 | Appendix A | Dominion:100 |  | VA | Cabin Run, Yardley Ridge |  | Reconductor | UC | 1.75 |  | 7/31/2026 |  | No | 12/1/2020 | 1/6/2021 | 30 |  |  |  | 2020-12-01
b3303.1 | PJM SOUTH | Extend a new single circuit 230KV line (#9250) from Farmwell Substation to Nimbus Substation. | Baseline | 230 | 5.65 | 6/1/2025 | Dominion | 2020_W1-704 | Appendix A | Dominion:100 |  | VA | Nimbus, Farmwell |  | Build | EP | 5.65 |  | 12/31/2025 |  | No | 12/1/2020 | 1/6/2021 | 20 |  |  |  | 2020-12-01
b3303.2 | PJM SOUTH | Remove Beaumeade 230kV Line #2152 line switch. | Baseline | 230 | 0.05 | 6/1/2025 | Dominion | 2020_W1-704 | Appendix A | Dominion:100 |  | VA | Beaumeade |  | Modify | IS | 0.05 |  | 6/1/2023 | 5/16/2023 | No | 12/1/2020 | 1/6/2021 | 100 |  |  |  | 2020-12-01
b3304 | PJM SOUTH | Midlothian Area 300 MW Load Drop Relief Area Improvements | Baseline | 230 | 6.22 | 6/1/2025 | Dominion | 2020_W1-860 | Appendix A | Dominion:100 |  | VA | Midlothian, Trabue, Winterpock |  | Modify | EP | 6.22 |  | 6/1/2026 |  | No | 12/1/2020 | 1/6/2021 | 20 |  |  |  | 2020-12-01
b3304.1 | PJM SOUTH | Cut 230kV Line #2066 at Trabue junction | Baseline | 230 | 0 | 6/1/2025 | Dominion | 2020_W1-860 | Appendix A | Dominion:100 |  | VA | Trabue |  | Modify | EP |  |  | 6/1/2026 |  | No | 12/1/2020 | 1/6/2021 | 20 |  |  |  | 2020-12-01
b3304.2 | PJM SOUTH | Reconductor idle 230kV Line #242 (radial from Midlothian to Trabue junction) to allow a minimum summer rating of 1047 MVA and connect to the section of 230kV Line #2066 between Trabue junction and Winterpock; re-number 230kV Line #242 structures to #2066; | Baseline | 230 | 0 | 6/1/2025 | Dominion | 2020_W1-860 | Appendix A | Dominion:100 |  | VA | Midlothian, Trabue, Winterpock |  | Modify | EP |  |  | 6/1/2026 |  | No | 12/1/2020 | 1/6/2021 | 20 |  |  |  | 2020-12-01
b3304.3 | PJM SOUTH | Use the section of idle 115kV Line #153, between Midlothian and Trabue junction to connect to the section of (former) 230kV Line #2066 between Trabue junction and Trabue to create new Midlothian-Trabue lines with new line numbers #2218 and #2219 | Baseline | 230 | 0 | 6/1/2025 | Dominion | 2020_W1-860 | Appendix A | Dominion:100 |  | VA | Midlothian, Trabue, Winterpock |  | Modify | EP |  |  | 6/1/2026 |  | No | 12/1/2020 | 1/6/2021 | 20 |  |  |  | 2020-12-01
b3304.4 | PJM SOUTH | Create new line terminations at Midlothian for the new Midlothian-Trabue lines. | Baseline | 230 | 2.27 | 6/1/2025 | Dominion | 2020_W1-860 | Appendix A | Dominion:100 |  | VA | Midlothian |  | Modify | EP |  |  | 6/1/2026 |  | No | 12/1/2020 | 1/6/2021 | 10 |  |  |  | 2020-12-01
b3305 | PJM MA | Replace Pumphrey 230/115kV transformer | Baseline | 230/115 | 4.69 | 6/1/2025 | BGE | 2020_W1-494 | Appendix A | BGE:100 |  | MD | Pumphrey |  | Replace | Cancelled | 4.69 |  | 6/1/2025 |  | No | 12/1/2020 | 12/1/2020 | 0 |  |  |  | 2020-12-01
b3306 | PJM MA | Install a second 125 MVAR 345 kV shunt reactor and associated equipment at Pierce Brook Substation. Install a 345 kV breaker on the high side of the #1 345/230 kV transformer | Baseline | 345 | 8.08 | 6/1/2025 | PENELEC | 2020_W1-855 | Appendix A | PENELEC:100 |  | PA | Pierce Brook |  | Install | EP | 8.08 |  | 12/31/2026 |  | No | 12/1/2020 | 12/1/2020 | 0 |  |  |  | 2020-12-01
b3308 | PJM WEST | Reconductor and rebuild 1 span of T-line on the Fort Steuben-Sunset Blvd 69 kV branch with 556 ACSR. | Baseline | 69 | 0.73 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Fort Steuben-Sunset Blvd |  | Rebuild | EP | 0.73 |  | 4/10/2028 |  | No | 1/15/2021 | 1/15/2021 | 10 |  |  |  | 2021-01-15
b3309 | PJM WEST | Rebuild 1.75 miles of the Greenlawn - East Tiffin line section of the Carrothers - Greenlawn 69 kV circuit containing 133 ACSR conductor with 556 ACSR conductor. Upgrade relaying as required. | Baseline | 69 | 3.45 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Greenlawn – East Tiffin |  | Rebuild | EP | 3.45 |  | 3/21/2029 |  | No | 1/15/2021 | 1/15/2021 | 50 |  |  |  | 2021-01-15
b3310.1 | PJM WEST | Rebuild 10.5 miles of the Howard-Willard 69 kV line utilizing 556 ACSR conductor. | Baseline | 69 | 19 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Howard-Willard |  | Rebuild | IS | 19 |  | 5/30/2025 | 5/30/2025 | No | 2/17/2021 | 2/17/2021 | 100 |  |  |  | 2021-02-17
b3310.2 | PJM WEST | Upgrade relaying at Howard 69 kV station. | Baseline | 69 | 0.23 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Howard |  | Upgrade | IS | 0.23 |  | 10/31/2025 | 6/5/2025 | No | 2/17/2021 | 2/17/2021 | 100 |  |  |  | 2021-02-17
b3310.3 | PJM WEST | Upgrade relaying at Willard 69 kV station. | Baseline | 69 | 0.23 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Willard |  | Upgrade | IS | 0.23 |  | 6/1/2025 | 5/30/2024 | No | 2/17/2021 | 2/17/2021 | 100 |  |  |  | 2021-02-17
b3312 | PJM WEST | Rebuild approximately 4.0 miles of existing 69 kV line between West Mount Vernon and Mount Vernon stations. Replace the existing 138/69 kV transformer at West Mount Vernon with a larger 90 MVA unit along with existing 69 kV breaker 'C'. | Baseline | 138/69 | 12.93 | 6/1/2025 | AEP | 2020_3-860 | Appendix A | AEP:100 |  | OH | West Mount Vernon-Mount Vernon |  | Rebuild | UC | 12.93 |  | 1/21/2026 |  | No | 1/6/2021 | 1/6/2021 | 75 |  |  |  | 2021-01-06
b3313 | PJM WEST | Add 40 kA circuit breakers on the low and high side of East Lima 138/69 kV Transformer | Baseline | 138/69 | 1.2 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | East Lima |  | Install | EP | 1.2 |  | 10/26/2026 |  | No | 3/19/2021 | 3/19/2021 | 50 |  |  |  | 2021-03-19
b3314.1 | PJM WEST | Install a new 138/69 kV 130 MVA transformer and associated protection at Elliot station. | Baseline | 138/69 | 3 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Elliot |  | Install | EP | 3 |  | 9/20/2029 |  | No | 3/19/2021 | 3/19/2021 | 50 |  |  |  | 2021-03-19
b3314.2 | PJM WEST | Perform work at Strouds Run station to retire 138/69/13 kV 33.6 MVA transformer #1 and install a dedicated 138/13 KV distribution transformer. | Baseline | 138/13 | 0 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Strouds Run |  | Install | EP | 0 |  | 10/24/2030 |  | No | 3/19/2021 | 3/19/2021 | 50 |  |  |  | 2021-03-19
b3315 | PJM WEST | Upgrade Relaying on Mark Center-South Hicksville 69 kV line and replace Mark Center cap bank with a 7.7 MVAR unit. | Baseline | 69 | 1.25 | 6/1/2025 | AEP |  | Appendix A | AEP:100 |  | OH | Mark Center, South Hicksville |  | Upgrade | IS | 1.25 |  | 6/1/2025 | 3/20/2025 | No | 3/19/2021 | 3/19/2021 | 100 |  |  |  | 2021-03-19
b3316 | PJM WEST | Greene Substation - replace 138 kV 40 kA breaker GJ-138C with a 63 kA breaker | Baseline | 138 | 0.28 | 6/1/2025 | Dayton |  | Appendix A | Dayton:100 |  | OH | Greene Sub |  | Replace | IS | 0.28 |  | 6/1/2022 | 5/23/2022 | No | 5/21/2021 | 5/21/2021 | 100 |  |  |  | 2021-05-21
b3697 | PJM MA | Replace station conductor and metering inside Whitpain and Plymouth substations to increase the ratings of the 220-13/220-14 Whitpain-Plymouth 230 kV line facilities. | Baseline | 230 | 0.62 | 6/1/2025 | PECO | 202021_1-704 | Appendix A | PECO:100 |  | PA | Plymouth-Whitpain |  | Upgrade | IS | 0.62 |  | 6/1/2025 | 12/30/2024 | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3718.1 | PJM SOUTH | Install one 500/230kV 1440MVA transformer at a new substation called Wishing Star. Cut and extend 500 kV Line #546 (Brambleton-Mosby) and 500 kV Line #590 (Brambleton-Mosby) to the proposed Wishing Star substation. Lines to terminate in a 500 kV breaker and a half configuration. | Baseline | 500/230 | 342.3 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Wishing Star |  | Install | UC | 111.28 |  | 12/19/2025 |  | Yes | 9/6/2022 | 9/6/2022 | 50 |  |  |  | 2022-09-06
b3718.10 | PJM SOUTH | Reconductor ~1.61 miles of 230 kV line #9349 (Sojourner-Mars) to achieve a summer rating of 1574 MVA. | Baseline | 230 | 1.4 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Sojourner, Mars |  | Reconductor | IS | 1.43 |  | 6/1/2025 | 1/29/2024 | Yes | 9/6/2022 | 9/6/2022 | 100 |  |  |  | 2022-09-06
b3718.11 | PJM SOUTH | Upgrade 4-500 kV breakers (total) to 63kA on either end of 500 kV Line #502 (Loudoun-Mosby) | Baseline | 500 | 0 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Loudoun, Mosby |  | Reconductor | EP | 6.27 |  | 12/31/2026 |  | Yes | 9/6/2022 | 9/6/2022 | 20 |  |  |  | 2022-09-06
b3718.12 | PJM SOUTH | Upgrade 4-500 kV breakers (total) to 63 kA on either end of 500 kV Line #584 (Loudoun-Mosby) | Baseline | 500 | 0 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Loudoun, Mosby |  | Reconductor | EP | 6.38 |  | 12/31/2026 |  | Yes | 9/6/2022 | 9/6/2022 | 10 |  |  |  | 2022-09-06
b3718.13 | PJM SOUTH | Cut and loop 230 kV Line #2079 (Sterling Park-Dranesville) into Davis Drive substation and install two GIS 230 kV breakers. | Baseline | 230 | 0 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Sterling Park, Dranesville |  | Modify | EP | 15 |  | 11/30/2026 |  | Yes | 9/6/2022 | 9/6/2022 | 0 |  |  |  | 2022-09-06
b3718.14 | PJM SOUTH | Construct a new 230 kV transmission line for ~3.5 miles along with substation upgrades at Wishing Star and Mars. New right-of-way will be needed and will share same structures with the 500 kV line. New conductor to have a minimum summer normal rating of 1573 MVA. | Baseline | 230 | 40 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Wishing Star, Mars |  | Construct | UC | 78.68 |  | 12/19/2025 |  | Yes | 9/6/2022 | 9/6/2022 | 50 |  |  |  | 2022-09-06
b3718.2 | PJM SOUTH | Install one 500/230 kV 1440 MVA transformer at a new substation called Mars near Dulles International Airport. | Baseline | 500/230 | 290 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Mars |  | Install | UC | 114.04 |  | 12/19/2025 |  | Yes | 9/6/2022 | 9/6/2022 | 50 |  |  |  | 2022-09-06
b3718.3 | PJM SOUTH | Construct a new 500 kV transmission line for ~ 3.5 miles along with substation upgrades at Wishing Star and Mars. New right-of-way will be needed and will share same structures with the line. New conductor to have a minimum summer normal rating of 4357 MVA. | Baseline | 500 | 40 | 6/1/2025 | Dominion |  | Appendix A | APS:10.46,Dominion:89.54 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Wishing Star, Mars |  | Construct | UC | 267 |  | 12/19/2025 |  | Yes | 9/6/2022 | 9/6/2022 | 50 |  |  |  | 2022-09-06
b3718.4 | PJM SOUTH | Reconductor ~0.62 miles of 230 kV line #2214 (Buttermilk-Roundtable) to achieve a summer rating of 1574 MVA. | Baseline | 230 | 4.8 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Buttermilk, Roundtable |  | Reconductor | UC | 4.79 |  | 6/1/2025 |  | Yes | 9/6/2022 | 9/6/2022 | 100 |  |  |  | 2022-09-06
b3718.5 | PJM SOUTH | Reconductor ~1.52 miles of 230 kV line #2031 (Enterprise-Greenway-Roundtable) to achieve a summer rating of 1574 MVA. | Baseline | 230 | 0 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Enterprise, Greenway, Roundtable |  | Reconductor | UC | 5.89 |  | 3/13/2026 |  | Yes | 9/6/2022 | 9/6/2022 | 90 |  |  |  | 2022-09-06
b3718.6 | PJM SOUTH | Reconductor ~0.64 miles of 230 kV line #2186 (Enterprise-Shellhorn) to achieve a summer rating of 1574 MVA. | Baseline | 230 | 0 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Enterprise, Shellhorn |  | Reconductor | UC | 3.96 |  | 6/1/2025 |  | Yes | 9/6/2022 | 9/6/2022 | 100 |  |  |  | 2022-09-06
b3718.7 | PJM SOUTH | Reconductor ~2.17 miles of 230 kV line #2188 (Lockridge-Greenway-Shellhorn) to achieve a summer rating of 1574 MVA. | Baseline | 230 | 0 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Lockridge, Greenway, Shellhorn |  | Reconductor | IS | 3.8 |  | 6/1/2025 |  | Yes | 9/6/2022 | 9/6/2022 | 100 |  |  |  | 2022-09-06
b3718.8 | PJM SOUTH | Reconductor ~0.84 miles of 230 kV line #2223 (Lockridge-Roundtable) to achieve a summer rating of 1574 MVA. | Baseline | 230 | 0 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Lockridge, Roundtable |  | Reconductor | UC | 2.59 |  | 3/13/2026 |  | Yes | 9/6/2022 | 9/6/2022 | 80 |  |  |  | 2022-09-06
b3718.9 | PJM SOUTH | Reconductor ~3.98 miles of 230 kV line #2218 (Sojourner-Runway-Shellhorn) to achieve a summer rating of 1574 MVA. | Baseline | 230 | 8 | 6/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA | Sojourner, Runway, Shellhorn |  | Reconductor | IS | 6.51 |  | 3/10/2025 |  | Yes | 9/6/2022 | 9/6/2022 | 100 |  |  |  | 2022-09-06
b3726 | PJM WEST | Install two new 500 kV breakers on the existing open SVC string to create a new bay position. Relocate & Reterminate facilities as necessary to move the 500 kV SVC into the new bay position and Install a 500 kV breaker on the 500/138 kV #3 transformer. Upgrade relaying at Black Oak substation. | Baseline | 500 | 17.37 | 6/1/2025 | APS | 2022_1-21 | Appendix A | APS:100 |  | WV | Black Oak |  | Install | UC | 17.37 |  | 12/19/2025 |  | No | 11/1/2022 | 11/1/2022 | 50 |  |  |  | 2022-11-01
b3760 | PJM WEST | At Powerton Sub, replace most limiting facility 800A wave trap with 2000A wave trap on the Powerton-Towerline 138kV line terminal | Baseline | 138 | 0.2 | 6/1/2025 | ComEd |  | Appendix A | AEC:0.93,AEP:13.17,APS:5.41,ATSI:6.91,BGE:3.21,Dayton:1.80,DEOK:2.68,DL:1.38,Dominion:10.80,DPL:1.92,ECP:0.14,EKPC:1.40,HTP:0.12,JCPL:2.22,ME:1.68,Neptune:0.50,OVEC:0.02,PECO:4.06,PENELEC:2.17,PEPCO:3.37,PPL:3.41,PSEG:4.18,RE:0.14,MISO:28.38 |  | IL | Powerton Sub |  | Upgrade | IS | 0.2 |  | 9/30/2024 | 9/9/2024 | No | 12/6/2022 | 12/6/2022 | 100 | 9/9/2024 |  |  | 2022-12-06
b3780.1 | PJM MA | Peach Bottom North upgrades – substation work Add 3x 500 kV breakers to form a breaker-and-a-half bay. | Baseline | 500 | 76.63 | 6/1/2025 | PECO |  | Appendix A | ATSI:0.02,BGE:28.40,Dominion:33.36,DPL:0.02,JCPL:6.36,Neptune:0.73,PECO:0.01,PEPCO:17.90,PSEG:12.69,RE:0.51 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Peach Bottom |  | Build | EP | 76.63 |  | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 8 |  |  |  | 2023-06-06
b3780.10 | PJM MA | Install new Conastone capacitor. New capacitor rating: 350 MVAR | Baseline | 500 | 33.7 | 6/1/2025 | BGE |  | Appendix A | BGE:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Conastone |  | Install | EP | 33.7 |  | 12/31/2027 |  | Yes | 6/6/2023 | 6/6/2023 | 10 |  |  |  | 2023-06-06
b3780.11 | PJM MA | Brighton Statcom and capacitor New STATCOM rating: 350 MVAR New capacitor rating: 350 MVAR | Baseline | 500 | 229 | 6/1/2025 | PEPCO |  | Appendix A | PEPCO:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Brighton |  | Install | EP | 229 |  | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 5 |  |  |  | 2023-06-06
b3780.12 | PJM MA | Burchess Hill Cap New capacitor rating: 250 MVAR | Baseline | 500 | 12 | 6/1/2025 | PEPCO |  | Appendix A | PEPCO:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Burchess Hill |  | Install | EP | 12 |  | 12/31/2027 |  | Yes | 6/6/2023 | 6/6/2023 | 5 |  |  |  | 2023-06-06
b3780.13 | PJM MA | Batavia Road to Riverside 230 kV reconductor New rating: 1941 MVA SN / 2181 MVA SE | Baseline | 230 | 57.3 | 6/1/2025 | BGE |  | Appendix A | BGE:51.24,PEPCO:48.76 |  | MD | Batavia - Riverton |  | Reconductor | EP | 57.3 |  | 12/31/2027 |  | Yes | 6/6/2023 | 6/6/2023 | 10 |  |  |  | 2023-06-06
b3780.14 | PJM MA | Reconfigure Cooper transmission feeds by establishing new Cooper-North Delta 230 kV line and rerouting existing transmissions lines by Cooper. | Baseline | 500 | 6.73 | 6/1/2025 | PECO | 2022-W3 | Appendix A | DPL:38.25,PECO:61.75 |  | PA | Cooper |  | Build | EP | 6.73 |  | 12/31/2028 |  | Yes | 12/5/2023 | 1/9/2024 | 17 |  |  |  | 2023-12-05
b3780.15 | PJM MA | Cut in 5012 Peach Bottom-Conastone 500 kV line into North Delta 500/230 kV substation by rebuilding 5012 between new terminal at Peach Bottom South and North Delta on single circuit structures and terminating at North Delta. | Baseline | 230 | 7.29 | 6/1/2025 | PECO | Immediate Need Project - Brandon Shores | Appendix A | AEC:11.03,BGE:37.40,DPL:22.90,PEPCO:28.67 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 |  | Cooper |  | Build | EP | 7.29 |  | 12/31/2028 |  | No | 12/5/2023 | 1/9/2024 | 17 |  |  |  | 2023-12-05
b3780.16 | PJM MA | Terminate new Cooper-North Delta 230 kV line (Transource Scope) at North Delta 230 kV. | Baseline | 500 | 4.48 | 6/1/2025 | Transource | Immediate Need Project - Brandon Shores | Appendix A | DPL:38.25,PECO:61.75 |  |  | Cooper |  | Build | EP | 0.47 |  | 10/15/2028 |  | No | 12/5/2023 | 1/9/2024 | 15 |  |  |  | 2023-12-05
b3780.17 | PJM MA | Cut in 5012 Peach Bottom-Conastone 500 kV line into North Delta 500/230 kV substation by rebuilding 5012 between new terminal at Peach Bottom South and North Delta on single circuit structures and terminating at North Delta (Transource Scope). | Baseline | 230 | 3.37 | 6/1/2025 | Transource | Immediate Need Project - Brandon Shores | Appendix A | AEC:11.03,BGE:37.40,DPL:22.90,PEPCO:28.67 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 |  | Cooper |  | Build | EP | 1.1 |  | 5/31/2028 |  | No | 12/5/2023 | 1/9/2024 | 15 |  |  |  | 2023-12-05
b3780.2 | PJM MA | Peach Bottom to Graceton (PECO) – New 500 kV transmission line New rating: 4503 MVA SN/ 5022 MVA SE | Baseline | 500 | 63.74 | 6/1/2025 | PECO |  | Appendix A | ATSI:0.02,BGE:28.40,Dominion:33.36,DPL:0.02,JCPL:6.36,Neptune:0.73,PECO:0.01,PEPCO:17.90,PSEG:12.69,RE:0.51 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Peach Botton - Graceton |  | Install | EP | 63.74 |  | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 5 |  |  |  | 2023-06-06
b3780.3 | PJM MA | West Cooper substation (3 breaker ring + transformer, control house + substation build, reconfigure Cooper distribution station feed) New transformer rating: 1559 MVA SN/ 1940 MVA SE | Baseline | 500 | 60 | 6/1/2025 | PECO |  | Appendix A | DPL:41.52,PECO:58.48 |  | PA | Cooper |  | Build | Cancelled | 60 |  | 12/31/2028 |  | Yes | 6/6/2023 | 12/5/2023 | 0 |  |  |  | 2023-06-06
b3780.4 | PJM MA | Peach Bottom to Graceton (BGE) – transmission work New rating: 4503 MVA SN/ 5022 MVA SE | Baseline | 500 | 38.8 | 6/1/2025 | BGE |  | Appendix A | ATSI:0.03,BGE:28.40,Dominion:33.36,DPL:0.02,JCPL:6.36,Neptune:0.73,PEPCO:17.90,PSEG:12.69,RE:0.51 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Peach Botton - Graceton |  | Upgrade | EP | 38.8 |  | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 10 |  |  |  | 2023-06-06
b3780.5 | PJM MA | Build Solley Road substation + Statcom. New STATCOM rating: 350 MVAR Add 4x 230 kV breakers bays. | Baseline | 230 | 239.6 | 6/1/2025 | BGE |  | Appendix A | BGE:100 |  | MD | Solley Road |  | Build | EP | 239.6 |  | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 10 |  |  |  | 2023-06-06
b3780.6 | PJM MA | Build Granite substation + Statcom. New STATCOM rating: 350 MVAR Add 4x 230 kV breaker bays. | Baseline | 230 | 198.6 | 6/1/2025 | BGE |  | Appendix A | BGE:100 |  | MD | Granite |  | Build | EP | 198.6 |  | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 10 |  |  |  | 2023-06-06
b3780.7 | PJM MA | Build Batavia Road substation. Add 4x 230 kV breaker bays. | Baseline | 230 | 127.8 | 6/1/2025 | BGE |  | Appendix A | BGE:100 |  | MD | Batavia |  | Build | EP | 127.8 |  | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 10 |  |  |  | 2023-06-06
b3780.8 | PJM MA | Graceton 500 kV expansion Add 3x 500 kV breaker bays, 2x 500/230 kV auto transformer, 1x 500 kV caps. New transformer rating: 1559 MVA SN / 1940 MVA SE New capacitor rating: 250 MVAR | Baseline | 500 | 213.2 | 6/1/2025 | BGE |  | Appendix A | BGE:81.92,PEPCO:18.08 |  | MD | Graceton |  | Install | EP | 213.2 |  | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 10 |  |  |  | 2023-06-06
b3780.9 | PJM MA | Graceton to Batavia Road 230 kV double circuit pole line New rating: 1331 MVA SN/ 1594 MVA SE | Baseline | 230 | 207.2 | 6/1/2025 | BGE |  | Appendix A | BGE:100 |  | MD | Graceton |  | Install | EP | 207.2 |  | 12/31/2028 |  | Yes | 6/6/2023 | 6/6/2023 | 10 |  |  |  | 2023-06-06
b3782 | PJM WEST | Adjust relay settings at Riverton substation on the Riverton-Bethel Tap 138 kV line. | Baseline | 138 | 0.08 | 6/1/2025 | APS |  | Appendix A | APS:100 |  | VA | Bethel-Riverton |  | Modify | IS | 0.08 |  | 5/23/2025 | 5/22/2025 | Yes | 9/5/2023 | 9/5/2023 | 100 |  |  |  | 2023-09-05
b3783 | PJM MA | Cut and remove the 345 kV and 230 kV generator lead lines at Homer City. Install new station service supply, separate AC station service, separate protection and controls schemes, and review and adjust relay protection settings | Baseline | 345/230 | 2.25 | 6/1/2025 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Homer City |  | Modify | UC | 2.25 |  | 10/1/2026 |  | Yes | 9/5/2023 | 9/5/2023 | 80 |  |  |  | 2023-09-05
b3853.1 | PJM SOUTH | Replace over duty Ladysmith CT 230kV circuit breakers SX1272 and SX3472 with an interrupting rating of 63 kA | Baseline | 230 | 1.25 | 6/1/2025 | Dominion | Immediate Need | Appendix A | Dominion:100 |  | VA | Ladysmith CT |  | Replace | EP | 1.25 |  | 6/1/2025 |  | Yes | 7/9/2024 | 7/9/2024 | 0 |  |  |  | 2024-07-09
b3854.1 | PJM SOUTH | Replace over duty Carson 230kV circuit breakers 200272 and 24972-3 with an interrupting rating of 63 kA | Baseline | 230 | 1.25 | 6/1/2025 | Dominion | Immediate Need | Appendix A | Dominion:100 |  | VA | Carson |  | Replace | IS | 1.25 |  | 6/1/2025 | 5/3/2025 | Yes | 7/9/2024 | 7/9/2024 | 100 |  |  |  | 2024-07-09
b3262 | PJM SOUTH | Install a second 115kV 33.67MVar cap bank at Harrisonburg substation along with a 115kV breaker. | Baseline | 115 | 1 | 12/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Install | UC | 1.25 |  | 10/31/2025 |  | No | 11/4/2020 | 1/14/2021 | 30 |  |  |  | 2020-11-04
b3263 | PJM SOUTH | Cut existing 115kV Line#5 between Bremo and Cunningham substations and loop in and out of Fork Union Substation. | Baseline | 115 | 2.5 | 12/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Modify | IS | 2.5 |  | 12/1/2025 | 2/24/2022 | No | 11/4/2020 | 1/14/2021 | 100 |  |  |  | 2020-11-04
b3268 | PJM SOUTH | Build a switching station at the junction of 115kV line #39 and 115kV line #91 with a 115kV capacitor bank. The switching station will built with 230kV structures but will operate at 115kV. | Baseline | 115 | 23.65 | 12/1/2025 | Dominion |  | Appendix A | Dominion:100 |  | VA |  |  | Install | EP | 12 |  | 5/28/2026 |  | No | 12/1/2020 | 1/14/2021 | 50 |  |  |  | 2020-12-01
b3278.1 | PJM WEST | Saltville Station: Replace H.S. MOAB Switches on the high side of the 138/69/34.5 kV T1 with a H.S. Circuit Switcher. | Baseline | 138/69/34.5 | 0.72 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | VA | Saltville |  | Replace | EP | 0.72 |  | 6/23/2031 |  | No | 2/17/2021 | 2/17/2021 | 25 |  |  |  | 2021-02-17
b3278.2 | PJM WEST | Meadowview Station: Replace existing 138/69/34.5 kV transformer T2 with a new 130 MVA 138/69/13 kV transformer. | Baseline | 138/69/34.5 | 3.14 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | VA | Meadowview |  | Replace | EP | 3.14 |  | 10/19/2032 |  | No | 2/17/2021 | 2/17/2021 | 25 |  |  |  | 2021-02-17
b3278.3 | PJM WEST | Saltville Station: Install two 138 kV breakers and bus diff protection | Baseline | 138 | 0.36 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | VA | Saltville |  | Install | EP | 0.36 |  | 5/12/2028 |  | No | 7/16/2021 | 7/16/2021 | 25 |  |  |  | 2021-07-16
b3281 | PJM WEST | Install 138 kV circuit switcher on the 138/69 kV transformer #1 and 138/34.5 kV transformer #2 at Dewey. Install 138 kV 2000 A 40 kA breaker on Stanville line at Dewey 138 kV substation. | Baseline | 138 | 1.4 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | KY | Dewey |  | Install | UC | 1.4 |  | 11/5/2025 |  | No | 2/17/2021 | 2/17/2021 | 75 |  |  |  | 2021-02-17
b3283 | PJM WEST | Replace the existing Inez 138/69 kV 50 MVA autotransformer with a 138/69 kV 90 MVA autotransformer. | Baseline | 138/69 | 2.96 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | KY | Inez |  | Replace | IS | 2.96 |  | 12/1/2025 | 10/31/2022 | No | 2/17/2021 | 2/17/2021 | 100 |  |  |  | 2021-02-17
b3288.1 | PJM WEST | Construct ~ 2.75 mi Orinoco - Stone 69 kV transmission line in the clear between Orinoco station and Stone station. | Baseline | 69 | 9.23 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | KY | Orinoco - Stone |  | Build | UC | 9.23 |  | 5/7/2027 |  | No | 1/15/2021 | 1/15/2021 | 75 |  |  |  | 2021-01-15
b3288.2 | PJM WEST | Construct ~ 3.25 mi Orinoco – New Camp 69 kV transmission line in the clear between Orinoco station and New Camp station. | Baseline | 69 | 9.95 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | KY | Orinoco – New Camp |  | Build | UC | 9.95 |  | 11/8/2027 |  | No | 1/15/2021 | 1/15/2021 | 75 |  |  |  | 2021-01-15
b3288.3 | PJM WEST | At Stone substation, circuit breaker A to remain in place and be utilized as T1 low side breaker, circuit breaker B to remain in place and be utilized as new Hatfield (via Orinoco and New Camp) 69 kV line breaker. Add new 69 kV circuit breaker E for Coleman Line exit. | Baseline | 69 | 0.66 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | KY | Stone |  | Install | UC | 0.66 |  | 5/7/2027 |  | No | 1/15/2021 | 1/15/2021 | 75 |  |  |  | 2021-01-15
b3288.4 | PJM WEST | Reconfigure the New Camp 69 kV tap which includes access road improvements/installation, temporary wire and permanent wire work along with dead end structures installation. | Baseline | 69 | 0.45 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | KY | New Camp |  | Modify | UC | 0.45 |  | 11/12/2027 |  | No | 1/15/2021 | 1/15/2021 | 75 |  |  |  | 2021-01-15
b3288.5 | PJM WEST | At New Camp substation, rebuild the 69 kV bus, add 69 kV MOAB W and replace the 69 kV ground switch Z1 with a 69 kV circuit switcher on the New Camp transformer. | Baseline | 69 | 1.18 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | KY | New Camp |  | Modify | UC | 1.18 |  | 11/8/2027 |  | No | 1/15/2021 | 1/15/2021 | 75 |  |  |  | 2021-01-15
b3292 | PJM WEST | Replace existing 69 kV capacitor bank at Stuart Station with a 17.2 MVAr capacitor bank | Baseline | 69 | 0 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | VA | Stuart |  | Replace | EP | 0 |  | 12/13/2028 |  | No | 1/15/2021 | 1/15/2021 | 25 |  |  |  | 2021-01-15
b3307 | PJM WEST | Rebuild Fleming station in the clear; Replace 138/69kV Fleming Transformer #1 with 138/69 kV 130 MVA transformer with high side 138 kV CB; Install a 5 breaker 69 kV ring bus on the low side of the transformer, replace 69 kV circuit switcher AA, replace 69/12kV transformer #3 with 69/12 kV 30 MVA transformer, replace 12 kV CB A and D. Retire existing Fleming substation. | Baseline | 138/69 | 21.1 | 12/1/2025 | AEP |  | Appendix A | AEP:100 |  | KY | Fleming subtation |  | Rebuild | UC | 21.1 |  | 11/21/2025 |  | No | 1/15/2021 | 1/15/2021 | 75 |  |  |  | 2021-01-15
b3709 | PJM WEST | Rebuild the Summer Shade-West Columbia 69 kV 0.19 miles of 266 conductor double circuit to 556 conductor. | Baseline | 69 | 0.19 | 12/1/2025 | EKPC |  | Appendix A | EKPC:100 |  | KY | Summer Shade-West Columbia |  | Rebuild | EP | 0.19 |  | 12/1/2026 |  | No | 3/18/2022 | 3/18/2022 | 0 |  |  |  | 2022-03-18
b3781 | PJM WEST | Replace line drops to Doubs transformer 3. New transformer rating: 721MVA SN /862 MVA SE | Baseline | 230 | 0.8 | 12/31/2025 | APS |  | Appendix A | APS:100 |  | MD | Doubs |  | Replace | EP | 0.8 |  | 11/21/2025 |  | Yes | 6/6/2023 | 6/6/2023 | 4 |  |  |  | 2023-06-06
b3337 | PJM WEST | Replace the one (1) Hyatt 138 kV breaker “AB1(101N)” with 3000 A, 63 kA interrupting breaker. | Baseline | 138 | 0.48 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Hyatt Substattion |  | Replace | EP | 0.48 |  | 12/9/2025 |  | No | 9/17/2021 | 10/15/2021 | 50 |  |  |  | 2021-09-17
b3338 | PJM WEST | Replace the two (2) Kenny 138 kV breakers, “102” (SC-3) and “106” (SC-4), each with a 3000 A, 63 kA interrupting breaker. | Baseline | 138 | 0.76 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Kenny Substation |  | Replace | EP | 0.76 |  | 6/1/2026 |  | No | 9/17/2021 | 10/5/2021 | 50 |  |  |  | 2021-09-17
b3339 | PJM WEST | Replace the one (1) Canal 138 kV breaker “3” with 3000 A, 63 kA breaker. | Baseline | 138 | 0.48 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Canal Street Substation |  | Replace | EP | 0.48 |  | 10/22/2025 |  | No | 9/17/2021 | 10/15/2021 | 50 |  |  |  | 2021-09-17
b3340 | PJM WEST | Replace one (1) Cheswick 138 kV breaker with a 3000 A, 63 kA breaker: “Z-53 LF_3”. | Baseline | 138 | 0.35 | 6/1/2026 | DL |  | Appendix A | DL:100 |  | PA | Cheswick Substation |  | Replace | IS | 0.35 |  | 11/24/2021 | 11/24/2021 | No | 9/17/2021 | 10/15/2021 | 100 |  |  |  | 2021-09-17
b3341.1 | PJM WEST | Marysville Substation: Install two 69 kV 16.6 MVAR cap banks; Install five 69 kV circuit breakers; Upgrade station relaying; Replace 600 A wave trap on the Marysville-Kings Creek 69 kV (6660) circuit | Baseline | 69 | 2.43 | 6/1/2026 | Dayton |  | Appendix A | Dayton:100 |  | OH | Maryville |  | Install | EP | 2.43 |  | 7/17/2026 |  | No | 10/15/2021 | 10/15/2021 | 0 |  |  |  | 2021-10-15
b3341.2 | PJM WEST | Darby Substation: Upgrade remote end relaying at Darby 69 kV substation | Baseline | 69 | 0.25 | 6/1/2026 | Dayton |  | Appendix A | Dayton:100 |  | OH | Darby |  | Upgrade | EP | 0.25 |  | 6/1/2026 |  | No | 10/15/2021 | 10/15/2021 | 0 |  |  |  | 2021-10-15
b3341.3 | PJM WEST | Kings Creek: Upgrade remote end relaying at Kings Creek 69 kV substation | Baseline | 69 | 0.25 | 6/1/2026 | Dayton |  | Appendix A | Dayton:100 |  | OH | Kings Creek |  | Upgrade | IS | 0.25 |  | 6/1/2026 | 2/7/2025 | No | 10/15/2021 | 10/15/2021 | 100 |  |  |  | 2021-10-15
b3342 | PJM WEST | Replace the 2156 ACSR & 2874 ACSR bus and risers with 2-bundled 2156 ACSR at Muskingum River 345 kV station to address loading issues on Muskingum-Waterford 345 kV line. | Baseline | 345 | 0.53 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Muskingum |  | Replace | IS | 0.53 |  | 9/1/2025 | 4/25/2023 | No | 11/2/2021 | 11/2/2021 | 100 |  |  |  | 2021-11-02
b3343 | PJM WEST | Rebuild approximately 0.3 miles of overloaded 69 kV line between Albion-Philips Switch and Philips Switch-Brimfield Switch with 556 ACSR conductor. | Baseline | 69 | 0.61 | 6/1/2026 | AEP | Proposal #2021_1-25 | Appendix A | AEP:100 |  | IN | Ablion-Philips Switch - Brimfield Switch |  | Rebuild | IS | 0.61 |  | 6/1/2026 | 9/4/2023 | No | 11/2/2021 | 11/2/2021 | 100 |  |  |  | 2021-11-02
b3345.1 | PJM WEST | Rebuild ~4.2 miles of overloaded sections of the 69 kV line between Salt Fork Switch and Leatherwood Switch with 556 ACSR. | Baseline | 69 | 9.06 | 6/1/2026 | AEP | 2021_1-115 | Appendix A | AEP:100 |  | OH | Salt Fork Switch - Leatherwood Switch 69kV |  | Rebuild | EP | 9.06 |  | 10/5/2027 |  | No | 11/2/2021 | 11/2/2021 | 25 |  |  |  | 2021-11-02
b3345.2 | PJM WEST | Update relay settings at Broom Road station. | Baseline | 69 | 0.04 | 6/1/2026 | AEP | 2021_1-115 | Appendix A | AEP:100 |  | OH | Broom Road |  | Upgrade | EP | 0.04 |  | 10/5/2027 |  | No | 11/2/2021 | 11/2/2021 | 25 |  |  |  | 2021-11-02
b3346.1 | PJM WEST | Rebuild approximately 3.5 miles of overloaded 69 kV line between North Delphos-East Delphos-Elida Road switch. This includes approximately 1.1 miles of double circuit line that makes up a portion of the North Delphos-South Delphos 69 kV line and the North Delphos-East Delphos 69 kV line. Approximately 2.4 miles of single circuit line will also be rebuilt between the double circuit portion to East Delphos station and from East Delphos to Elida Road Switch. | Baseline | 69 | 8.43 | 6/1/2026 | AEP | 2021_1-202 | Appendix A | AEP:100 |  | OH | North Delphos-East Delphos-Elida Road switch |  | Rebuild | EP | 8.43 |  | 10/19/2026 |  | No | 11/30/2021 | 11/30/2021 | 25 |  |  |  | 2021-11-30
b3346.2 | PJM WEST | Replace the line entrance spans at South Delphos to eliminate the overloaded 4/0 Copper and 4/0 ACSR conductor. | Baseline | 69 | 0.44 | 6/1/2026 | AEP | 2021_1-202 | Appendix A | AEP:100 |  | OH | South Delphos |  | Replace | EP | 0.44 |  | 6/16/2027 |  | No | 11/30/2021 | 11/30/2021 | 25 |  |  |  | 2021-11-30
b3349 | PJM WEST | Replace Bellefonte 69 kV risers on the section between Bellefonte TR #3 and 69 kV Bus #2. | Baseline | 69 | 0.54 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | Bellefonte |  | Replace | UC | 0.54 |  | 12/2/2026 |  | No | 11/19/2021 | 11/19/2021 | 75 |  |  |  | 2021-11-19
b3351 | PJM WEST | Replace the 69 kV in-line switches at Monterey 69 kV substation. | Baseline | 69 | 0 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | VA | Monterey Substation |  | Replace | EP | 0 |  | 8/31/2029 |  | No | 11/19/2021 | 11/19/2021 | 0 |  |  |  | 2021-11-19
b3352 | PJM WEST | Replace MOAB W, MOAB Y, line and bus side jumpers of both W and Y at 47th Street 69 kV station. Upgrade the 69 kV strain bus between MOABs W and Y to 795 KCM AAC. Change the connectors on the tap to MOAB X1 to accommodate the larger 795 KCM AAC. | Baseline | 69 | 0 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | 47th 69kV station |  | Replace | IS | 0 |  | 12/1/2025 | 4/15/2025 | No | 11/19/2021 | 11/19/2021 | 100 |  |  |  | 2021-11-19
b3358 | PJM WEST | Install a 69 kV 11.5 MVAR capacitor at Biers Run station. | Baseline | 69 | 0.85 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Biers Run Station; Chillicothe OH 45601 |  | Install | IS | 0.85 |  | 3/6/2024 | 3/6/2024 | No | 11/19/2021 | 11/19/2021 | 100 |  |  |  | 2021-11-19
b3359 | PJM WEST | Rebuild approximately 2.3 miles of the existing North Van Wert Sw-Van Wert 69 kV line utilizing 556 ACSR conductor. | Baseline | 69 | 6.2 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Van Wert, OH 45891 |  | Rebuild | EP | 6.2 |  | 1/6/2027 |  | No | 11/19/2021 | 11/19/2021 | 50 |  |  |  | 2021-11-19
b3362 | PJM WEST | Rebuild approximately 3.1 miles of the overloaded conductor on the existing Oertels Corner-North Portsmouth 69 kV line utilizing 556 ACSR. | Baseline | 69 | 8 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Oertels Corner - North Portsmouth |  | Rebuild | EP | 8 |  | 10/20/2026 |  | No | 11/19/2021 | 11/19/2021 | 50 |  |  |  | 2021-11-19
b3664 | PJM MA | Juniata: Replace the limiting 230 kV T2 transformer leads, bay conductor and bus conductor with double bundle 1590 ACSR. Replace the limiting 1200 A MODs on the Bus tie breaker with 3000 A MODs | Baseline | 500/230 | 0.68 | 6/1/2026 | PPL |  | Appendix A | PPL:100 |  | PA | Juniata |  | Replace | UC | 0.68 |  | 8/1/2025 |  | No | 11/2/2021 | 11/2/2021 | 90 |  |  |  | 2021-11-02
b3665 | PJM MA | Replace several pieces of 1033.5 AAC substation conductor at East Towanda 230 kV Substation (on East Towanda-Canyon 230 kV Line terminal) | Baseline | 230 | 0.41 | 6/1/2026 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | East Towanda |  | Replace | IS | 0.41 |  | 5/31/2025 | 5/27/2025 | No | 11/2/2021 | 11/2/2021 | 100 |  |  |  | 2021-11-02
b3666 | PJM MA | Marshall 230 kV Substation: Install dual reactors and expand existing ring bus | Baseline | 230 | 5.83 | 6/1/2026 | PENELEC | 2021_1-745 | Appendix A | PENELEC:100 |  | PA | Marshall |  | Install | EP | 5.83 |  | 12/31/2027 |  | No | 11/2/2021 | 11/2/2021 | 3 |  |  |  | 2021-11-02
b3667 | PJM MA | Pierce Brook Substation: Install second 230/115 kV transformer | Baseline | 230/115 | 5.07 | 6/1/2026 | PENELEC | 2021_1-101 | Appendix A | PENELEC:100 |  | PA | Pierce Brook |  | Install | EP | 5.07 |  | 12/1/2027 |  | No | 11/2/2021 | 11/2/2021 | 10 |  |  |  | 2021-11-02
b3668 | PJM MA | Upgrade Windy Edge 115 kV substation conductor to increase ratings of the Windy Edge-Chesco Park 110501 circuit. | Baseline | 115 | 0.5 | 6/1/2026 | BGE |  | Appendix A | BGE:100 |  | MD | Windy Edge |  | Replace | EP | 0.5 |  | 10/1/2025 |  | No | 11/18/2021 | 11/18/2021 | 0 |  |  |  | 2021-11-18
b3670 | PJM MA | Upgrade terminal equipment on the Loretto-Fruitland 69 kV circuit: Replace the 477 ACSR stranded bus on the 6711 line terminal inside Loretto substation and the 500 SDCU stranded bus on the 6711 line terminal inside Fruitland substation with 954 ACSR conductor. | Baseline | 69 | 0.8 | 6/1/2026 | DPL |  | Appendix A | DPL:100 |  | MD | Loretto/Fruitland |  | Replace | EP | 0.8 |  | 6/1/2026 |  | No | 11/18/2021 | 11/18/2021 | 0 |  |  |  | 2021-11-18
b3671 | PJM MA | Rebuild approx. 3.6 miles of 875 (N. Boyertown-W. Boyertown). Upgrade terminal equipment (circuit breaker, disconnect switches, substation conductor) and relays at N. Boyertown and W. Boyertown substation. | Baseline | 69 | 8.79 | 6/1/2026 | ME |  | Appendix A | ME:100 |  | PA | N. Boyertown/W. Boyertown |  | Rebuild | Cancelled | 8.79 |  |  |  | No | 11/18/2021 | 8/18/2022 | 0 |  |  |  | 2021-11-18
b3672 | PJM MA | East Towanda-North Meshoppen 115 kV line: Rebuild 2.5 miles of 636 ACSR with 1113 ACSS conductor using single circuit construction. Upgrade all terminal equipment to the rating of 1113 ACSS. | Baseline | 115 | 6.66 | 6/1/2026 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | East Towanda/North Meshoppen |  | Rebuild | EP | 6.66 |  | 12/31/2025 |  | No | 11/18/2021 | 11/18/2021 | 30 |  |  |  | 2021-11-18
b3673 | PJM MA | Replace the relay panels at Bethlehem 33 46 kV substation on the Cambria Prison line. | Baseline | 46 | 0.3 | 6/1/2026 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Bethlehem 33 |  | Replace | EP | 0.3 |  | 6/1/2026 |  | No | 11/18/2021 | 11/18/2021 | 0 |  |  |  | 2021-11-18
b3674 | PJM MA | Replace four Atlantic 34.5 kV breakers (J36, BK1A, BK1B, BK3A and BK3B) with 63 kA rated breakers and associated equipment. | Baseline | 34.5 | 3.5 | 6/1/2026 | JCPL |  | Appendix A | JCPL:100 |  | NJ | Atlantic |  | Replace | Cancelled | 3.5 |  | 9/30/2023 |  | No | 11/18/2021 | 5/16/2022 | 0 |  |  |  | 2021-11-18
b3675 | PJM MA | Replace six Werner 34.5 kV breakers (E31A_Prelim, E31B_Prelim, V48 future, W101, M39 and U99) with 40 kA rated breakers and associated equipment. | Baseline | 34.5 | 4.2 | 6/1/2026 | JCPL |  | Appendix A | JCPL:100 |  | NJ | Werner |  | Replace | Cancelled | 4.2 |  | 6/1/2024 |  | No | 11/18/2021 | 5/16/2022 | 0 |  |  |  | 2021-11-18
b3676 | PJM MA | Replace one Freneau 34.5 kV breaker (BK6) with 63 kA rated breakers and associated equipment. | Baseline | 34.5 | 0.7 | 6/1/2026 | JCPL |  | Appendix A | JCPL:100 |  | NJ | Freneau |  | Replace | Cancelled | 0.7 |  |  |  | No | 11/18/2021 | 5/16/2022 | 0 |  |  |  | 2021-11-18
b3680 | PJM WEST | At Sanborn, replace limiting substation conductors on Ashtabula 138 kV exit to make transmission line conductor the limiting element. | Baseline | 138 | 0.3 | 6/1/2026 | ATSI |  | Appendix A | ATSI:100 |  | OH | Ashtabula - Sanborn Q3 138 kV line |  | Replace | IS | 0.3 |  | 11/4/2022 | 11/2/2022 | No | 11/19/2021 | 11/19/2021 | 100 |  |  |  | 2021-11-19
b3681 | PJM WEST | Upgrade the Shingletown #82 230-46 kV transformer circuit by installing a 230 kV breaker and disconnect switches, removing existing 230 kV switches, replacing 46 kV disconnect switches, replacing limiting substation conductor, and installing/replacing relays. | Baseline | 230 | 1.66 | 6/1/2026 | APS | 2021_1-919 | Appendix A | APS:100 |  | PA | Shingletown 230 kV substation |  | Install | EP | 1.66 |  | 10/31/2025 |  | No | 11/30/2021 | 11/30/2021 | 30 |  |  |  | 2021-11-30
b3682 | PJM WEST | Install a second 345/138 kV transformer at Hayes, 448 MVA nameplate rating. Add one 345 kV circuit breaker (3000A) to provide transformer high-side connection between breaker B-18 and the new breaker. Connect the new transformer low side to the 138 kV bus. Add one 138 kV circuit breaker (3000A) at Hayes 138 kV substation between B-42 and the new breaker. Relocate the existing 138 kV No. 1 capacitor bank between B-42 and the new breaker. Protection per FE standard. | Baseline | 345 | 7.59 | 6/1/2026 | ATSI | 2021_1-549 | Appendix A | ATSI:100 |  | OH | Hayes 345 substation |  | Install | EP | 7.59 |  | 6/1/2026 |  | No | 11/30/2021 | 11/30/2021 | 2 |  |  |  | 2021-11-30
b3683 | PJM WEST | Reconductor the existing 556.5 ACSR line segments (3.49 miles) on the Messick Road-Ridgeley WC4 138 kV line with 954 45/7 ACSR to achieve 308/376 MVA SN/SE and 349/445 MVA WN/WE ratings. Replace the remote end equipment for the Messick Road-Ridgeley WC4 138 kV line. The total length of the line is 5.02 miles. | Baseline | 138 | 11.2 | 6/1/2026 | APS |  | Appendix A | APS:100 |  | WV | Ridgley to Messick 138 kV |  | Reconductor | EP | 11.2 |  | 6/30/2028 |  | No | 12/17/2021 | 12/17/2021 | 10 |  |  |  | 2021-12-17
b3684 | PJM SOUTH | Rebuild 12.4 miles of 115 line #126 segment from Earleys to Kelford with a summer emergency rating of 262 MVA. Replace structures as needed to support the new conductor. Upgrade breaker switch 13668 at Earleys from 1200 A to 2000 A. | Baseline | 115 | 50.7 | 6/1/2026 | Dominion |  | Appendix A | Dominion:100 |  | NC | Earleys, Kelford |  | Rebuild | UC | 18.75 |  | 3/1/2027 |  | No | 11/18/2021 | 11/18/2021 | 30 |  |  |  | 2021-11-18
b3685 | PJM SOUTH | Install a 33 MVAR cap bank at Cloud 115 kV bus along with a 115 kV breaker. Add 115 kV circuit breaker for 115 kV line #38. | Baseline | 115 | 1.5 | 6/1/2026 | Dominion |  | Appendix A | Dominion:100 |  | VA | Cloud |  | Install | EP | 1.5 |  | 6/1/2026 |  | No | 11/18/2021 | 11/18/2021 | 0 |  |  |  | 2021-11-18
b3687 | PJM SOUTH | Rebuild approximately 15.1-mile-long line segment between 115 kV line #183 Bristers and Minnieville D.P. with 2-768 ACSS and 4000 A supporting equipment from Bristers to Ox to allow for future 230 kV capability of 115 kV line #183. The continuous summer normal rating will be 523 MVA from Ox-Minnieville. The continuous summer normal rating will be 786 MVA from Minnieville-Bristers. | Baseline | 115 | 30 | 6/1/2026 | Dominion |  | Appendix A | Dominion:100 |  | VA | Bristers, Ox |  | Rebuild | UC | 30 |  | 12/17/2025 |  | No | 11/18/2021 | 11/18/2021 | 50 |  |  |  | 2021-11-18
b3688 | PJM MA | Replace the 4/0 SDCU stranded bus with 954 ACSR and a 600 A disconnect switch with a 1200 A disconnect switch on the 6716 line terminal inside Todd substation (on the Preston-Todd 69 kV circuit). | Baseline | 69 | 0.75 | 6/1/2026 | DPL |  | Appendix A | DPL:100 |  | DE | Todd |  | Replace | IS | 0.75 |  | 6/1/2025 | 1/29/2024 | No | 12/20/2021 | 12/20/2021 | 100 |  |  |  | 2021-12-20
b3689.1 | PJM SOUTH | Reconductor approximately 24.42 miles of 230 kV line #2114 Remington CT-Elk Run-Gainesville to achieve a summer rating of 1574 MVA by fully reconductoring the line and upgrading the wave trap and substation conductor at Remington CT and Gainesville. | Baseline | 230 | 52 | 6/1/2026 | Dominion | Proposal #2021_1-445 | Appendix A | Dominion:100 |  | VA | Remington CT, Elk Run, Gainesville |  | Reconductor | IS | 28.99 |  | 6/1/2025 | 5/19/2025 | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3689.2 | PJM SOUTH | Replace 230 kV breakers SC102, H302, H402 and 218302 at Brambleton substation with 4000A 80 kA breakers and associated equipment including breaker leads as necessary to address breaker duty issues identified in short circuit analysis. | Baseline | 230 | 4.88 | 6/1/2026 | Dominion | Proposal #2021_1-445 | Appendix A | Dominion:100 |  | VA | Brambleton |  | Replace | UC | 1.69 |  | 3/31/2027 |  | No | 11/30/2021 | 11/30/2021 | 30 |  |  |  | 2021-11-30
b3690 | PJM SOUTH | Reconductor approximately 1.07 miles of 230 kV line #2008 segment from Cub Run-Walney to achieve a summer rating of 1574 MVA. Replace line switch 200826 with a 4000A switch. | Baseline | 230 | 2.03 | 6/1/2026 | Dominion | Proposal #2021_1-600 | Appendix A | Dominion:100 |  | VA | Cub Run, Walney |  | Reconductor | IS | 1.93 |  | 11/15/2024 |  | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3691 | PJM SOUTH | Reconductor approximately 1.4 miles of 230 kV line #2141 from Lakeview-Carolina to achieve a summer rating of 1047 MVA. | Baseline | 230 | 1.19 | 6/1/2026 | Dominion | Proposal #2021_1-414 | Appendix A | Dominion:100 |  | NC | Lakeview, Carolina |  | Reconductor | IS | 1.18 |  | 5/31/2022 | 5/31/2022 | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3692 | PJM SOUTH | Rebuild approximately 27.7 miles of 500 kV transmission line from Elmont to Chickahominy with current 500 kV standards construction practices to achieve a summer rating of 4330 MVA. Latest TEAC changes structures from lattice structures to H-frame | Baseline | 500 | 214 | 6/1/2026 | Dominion | 2021_1-124 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Elmont, Chickahominy |  | Rebuild | EP | 110.66 |  | 6/30/2029 |  | No | 11/30/2021 | 5/6/2025 | 0 |  | 6/1/2026 |  | 2021-11-30
b3692.2 | PJM SOUTH | Switch to 5/2 H-frame structures and install approximately 27.7 miles of 230kV transmission line (but not be terminated) from Elmont to Chickahominy. String up approximately 8 miles of new 230kV conductor on the open arms of the structures of 230kV Line #2075 that runs parallel to 500kV Line #557. | Baseline | 230 | 74.5 | 6/1/2026 | Dominion |  |  |  |  | VA | Elmont |  | Install | EP | 74.5 |  | 6/30/2028 |  | No | 5/6/2025 | 5/6/2025 | 0 |  |  |  | 2025-05-06
b3694.1 | PJM SOUTH | Convert line #29 Aquia Harbor to Possum Point to 230 kV (Extended line #2104) and swap line #2104 and converted line #29 at Aquia Harbor backbone termination. Upgrade terminal equipment at Possum Point to terminate converted line 29 (now extended line #2104). (Line #29 from Fredericksburg to Aquia Harbor is being rebuilt under baseline b2981 to 230kV standards.) | Baseline | 230 | 11.4 | 6/1/2026 | Dominion | Proposal #2021_1-224 | Appendix A | Dominion:100 |  | VA | Aquia Harbor, Possum Point |  | Modify | EP | 9.39 |  | 9/28/2029 |  | No | 11/30/2021 | 11/30/2021 | 20 |  |  |  | 2021-11-30
b3694.10 | PJM SOUTH | Reconductor approximately 2.9 miles of 230 kV line #211 Chesterfield-Hopewell to achieve a minimum summer emergency rating of 1046 MVA. | Baseline | 230 | 18 | 6/1/2026 | Dominion | Proposal #2021_1-224 | Appendix A | Dominion:100 |  | VA | Chesterfield, Hopewell |  | Reconductor | IS | 4.91 |  | 5/30/2025 | 5/30/2025 | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3694.11 | PJM SOUTH | Reconductor approximately 2.9 miles of 230 kV line #228 Chesterfield-Hopewell to achieve a minimum summer emergency rating of 1046 MVA. | Baseline | 230 | 18 | 6/1/2026 | Dominion | Proposal #2021_1-224 | Appendix A | Dominion:100 |  | VA | Chesterfield, Hopewell |  | Reconductor | IS | 4.91 |  | 5/30/2025 | 5/30/2025 | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3694.12 | PJM SOUTH | Upgrade equipment at Chesterfield substation to not limit ratings on lines 211 and 228. | Baseline | 230 | 18 | 6/1/2026 | Dominion | Proposal #2021_1-224 | Appendix A | Dominion:100 |  | VA | Chesterfield |  | Upgrade | IS | 0.76 |  | 5/30/2025 | 5/30/2025 | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3694.13 | PJM SOUTH | Upgrade equipment at Hopewell substation to not limit ratings on lines 211 and 228. | Baseline | 230 | 18 | 6/1/2026 | Dominion | Proposal #2021_1-224 | Appendix A | Dominion:100 |  | VA | Hopewell |  | Upgrade | IS | 1.71 |  | 5/30/2025 | 5/30/2025 | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3694.2 | PJM SOUTH | Upgrade Aquia Harbor terminal equipment to not limit 230 kV line #9281 conductor rating. | Baseline | 230 | 1.9 | 6/1/2026 | Dominion | Proposal #2021_1-224 | Appendix A | Dominion:100 |  | VA | Aquia Harbor |  | Upgrade | EP | 0.63 |  | 6/16/2028 |  | No | 11/30/2021 | 11/30/2021 | 20 |  |  |  | 2021-11-30
b3694.3 | PJM SOUTH | Upgrade Fredericksburg terminal equipment by rearranging 230 kV bus configuration to terminate converted line 29 (now becoming 9281). The project will add a new breaker at the 230 kV bay and reconfigure line termination of 230 kV lines #2157, #2090 and #2083. | Baseline | 230 | 3 | 6/1/2026 | Dominion | Proposal #2021_1-224 | Appendix A | Dominion:100 |  | VA | Fredericksburg |  | Upgrade | EP | 2.72 |  | 6/25/2027 |  | No | 11/30/2021 | 11/30/2021 | 20 |  |  |  | 2021-11-30
b3694.4 | PJM SOUTH | Reconductor/rebuild approximately 7.6 miles of 230 kV line #2104 Cranes Corner-Stafford to achieve a summer rating of 1047 MVA(1). Reconductor/rebuild approximately 0.34 miles of 230 kV line #2104 Stafford-Aquia Harbor to achieve a summer rating of 1047 MVA. Upgrade terminal equipment at Cranes Corner to not limit the new conductor rating. | Baseline | 230 | 4.1 | 6/1/2026 | Dominion | 2021_1-224 | Appendix A | Dominion:100 |  | VA | Cranes Corner, Stafford |  | Reconductor | EP | 19.6 |  | 4/17/2026 |  | No | 11/30/2021 | 11/30/2021 | 20 |  |  |  | 2021-11-30
b3694.5 | PJM SOUTH | Upgrade wave trap and line leads at 230 kV line #2090 Ladysmith CT terminal to achieve 4000A rating. | Baseline | 230 | 0.15 | 6/1/2026 | Dominion | 2021_1-224 | Appendix A | Dominion:100 |  | VA | Ladysmith CT |  | Upgrade | EP | 0.15 |  | 12/15/2027 |  | No | 11/30/2021 | 11/30/2021 | 20 |  |  |  | 2021-11-30
b3694.6 | PJM SOUTH | Upgrade Fuller Road substation to feed Quantico substation via 115 kV radial line. Install four-breaker ring and break 230 kV line #252 into two new lines: 1) #252 between Aquia Harbor to Fuller Road and 2) #9282 between Fuller Road and Possum Point. Install a 230/115 kV transformer which will serve Quantico substation. | Baseline | 230 | 59.3 | 6/1/2026 | Dominion | 2021_1-224 | Appendix A | Dominion:100 |  | VA | Fuller Road, Quantico |  | Upgrade | EP | 24.16 |  | 1/2/2029 |  | No | 11/30/2021 | 11/30/2021 | 20 |  |  |  | 2021-11-30
b3694.7 | PJM SOUTH | Energize in-service spare 500/230 kV Carson Tx#1. | Baseline | 500/230 | 0 | 6/1/2026 | Dominion | Proposal #2021_1-224 | Appendix A | Dominion:100 |  | VA | Carson |  | Provide | IS | 0 |  | 6/1/2025 | 5/3/2025 | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3694.8 | PJM SOUTH | Partial wreck and rebuild 10.34 miles of 230 kV line #249 Carson-Locks to achieve a minimum summer emergency rating of 1047 MVA. Upgrade terminal equipment at Carson and Locks to not limit the new conductor rating. | Baseline | 230 | 26.3 | 6/1/2026 | Dominion | Proposal #2021_1-224, only CRL was accepted in 202 | Appendix A | Dominion:100 |  | VA | Carson, Chaparral, Locks |  | Rebuild | IS | 25.6 |  | 6/1/2025 | 5/3/2025 | No | 11/30/2021 | 1/9/2024 | 100 |  | 6/30/2025 |  | 2021-11-30
b3694.9 | PJM SOUTH | Wreck and rebuild 5.4 miles of 115 kV line #100 Locks-Harrowgate to achieve a minimum summer emergency rating of 393 MVA. Upgrade terminal equipment at Locks and Harrowgate to not limit the new conductor rating and perform line #100 Chesterfield terminal relay work. | Baseline | 115 | 9.1 | 6/1/2026 | Dominion | Proposal #2021_1-224 | Appendix A | Dominion:100 |  | VA | Locks, Harrowgate |  | Rebuild | IS | 9.1 |  | 2/7/2025 |  | No | 11/30/2021 | 11/30/2021 | 100 |  |  |  | 2021-11-30
b3704 | PJM MA | Replace the Lawrence switching station 230/69 kV transformer No. 220-4 and its associated circuit switchers with a new larger capacity transformer with load tap changer (LTC) and new dead tank circuit breaker. Install a new 230 kV gas insulated breaker, associated disconnects, overhead bus and other necessary equipment to complete the bay within the Lawrence 230 kV switchyard | Baseline | 230/69 | 13.36 | 6/1/2026 | PSEG | 2021_3-524 | Appendix A | PSEG:96.26,RE:3.74 |  | NJ | Lawrence |  | Replace | IS | 13.36 |  | 12/30/2024 | 12/19/2024 | No | 2/8/2022 | 2/8/2022 | 100 |  |  |  | 2022-02-08
b3705 | PJM MA | Replace existing 230/138 kV Athenia No. 220-1 transformer. | Baseline | 230/138 | 7.2 | 6/1/2026 | PSEG | 2021_3-770 | Appendix A | PSEG:96.26,RE:3.74 |  | NJ | Athenia |  | Replace | IS | 13.04 |  | 5/31/2024 | 6/21/2024 | No | 2/8/2022 | 2/8/2022 | 100 |  |  |  | 2022-02-08
b3706 | PJM MA | Replace Fair Lawn 230/138kV transformer No. 220-1 with an existing O&M system spare at Burlington. | Baseline | 230/138 | 4.45 | 6/1/2026 | PSEG | 2021_3-510 | Appendix A | PSEG:100 |  | NJ | Fair Lawn |  | Replace | IS | 4.45 |  |  | 3/29/2023 | No | 2/8/2022 | 2/8/2022 | 100 |  |  |  | 2022-02-08
b3708 | Not Specified | Replace the Shawville 230/115/17.2 kV transformer with a new Shawville 230/115 kV transformer and associated facilities. Replace the plant’s No. 2B 115/17.2 kV transformer with a larger 230/17.2 kV transformer. | Baseline | 230/115/17.2 | 8.78 | 6/1/2026 | PENELEC | 2021_1-100 | Appendix A | PENELEC:100 |  | PA | Shawville |  | Replace | EP | 8.78 |  | 6/1/2026 |  | No | 3/8/2022 | 3/8/2022 | 0 |  |  |  | 2022-03-08
b3710 | PJM WEST | Cancelled at the December 2023 SRRTEP West Meeting.Rescope: Reconductor Both Yukon - AA2-161 138 kV ckt 1 and 2 with 954 ACSS | Baseline | 138 | 10.64 | 6/1/2026 | APS |  | Appendix A | APS:100 |  | PA | Yukon to AA2-161 Tap |  | Modify | Cancelled | 10.64 |  | 6/1/2026 |  | No | 4/22/2022 | 12/12/2023 | 0 |  |  |  | 2022-04-22
b3715.1 | PJM MA | At the existing PPL Williams Grove substation, install a new 300 MVA 230/115 kV transformer. | Baseline | 230/115 | 6.3 | 6/1/2026 | PPL | 2021_1-99 | Appendix A | ME:100 |  | PA | Williams Grove |  | Install | UC | 6.3 |  | 5/6/2026 |  | No | 5/10/2022 | 5/10/2022 | 30 |  |  |  | 2022-05-10
b3715.2 | PJM MA | Construct a new ~3.4 mile 115 kV single circuit transmission line from Williams Grove to Allen substation. | Baseline | 115 | 5.11 | 6/1/2026 | PPL | 2021_1-99 | Appendix A | ME:100 |  | PA | Williams Grove-Allen |  | Build | UC | 5.11 |  | 4/3/2026 |  | No | 5/10/2022 | 5/10/2022 | 40 |  |  |  | 2022-05-10
b3715.3 | PJM MA | Install a new Allen four breaker ring bus within the existing MetEd Allen substation. Terminate the Round Top-Allen and the Allen-PPGI (PPG Industries) 115 kV lines into the new switchyard. | Baseline | 115 | 11.73 | 6/1/2026 | ME | 2021_1-99 | Appendix A | ME:100 |  | PA | Allen |  | Modify | EP | 6.41 |  | 6/1/2026 |  | No | 5/10/2022 | 5/10/2022 | 5 |  |  |  | 2022-05-10
b3882.1 | PJM WEST | Replace 138 kV circuit breaker BB with higher fault current capable counterpart. | Baseline | 138 | 1 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Sunnyside |  | Replace | EP | 1 |  | 6/1/2026 |  | Yes | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3884.1 | PJM WEST | Replace the 69 kV circuit breaker D at Van Wert with a 40 kA breaker. | Baseline | 69 | 1 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Van Wert |  | Replace | EP | 1 |  | 6/1/2026 |  | Yes | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3885.1 | PJM WEST | Replace 69 kV circuit breakers N and M at Schroyer Avenue station with higher fault current capable counterparts. | Baseline | 69 | 2 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Schroyer Avenue |  | Replace | EP | 2 |  | 6/1/2026 |  | Yes | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3886.1 | PJM WEST | Replace 69 kV circuit breaker 'A' along with disconnect switches at Benwood substation with a 40 kA Circuit Breaker. | Baseline | 69 | 1 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | WV | Benwood |  | Replace | EP | 1 |  | 6/1/2026 |  | Yes | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3887.1 | PJM WEST | Replace Greentown 138kV circuit switcher for Transformer #5 with a 138kV 63kA Circuit Breaker | Baseline | 765 | 1 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | IN | Greentown |  | Replace | EP | 1 |  | 6/1/2026 |  | Yes | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3892.1 | PJM WEST | Replace 69 kV circuit breakers A and S at Mount Vernon station with 40 kA breakers. | Baseline | 69 | 2 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | OH | Mount Vernon |  | Replace | EP | 2 |  | 6/1/2026 |  | Yes | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3895.1 | PJM WEST | Replace existing 138 kV, 40 kA Circuit Switcher L at Jacksons Ferry Station with new 138 kV, 63 kA Circuit Breaker | Baseline | 765 | 1 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | VA | Jacksons Ferry |  | Replace | EP | 1 |  | 6/1/2026 |  | Yes | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3897.1 | PJM WEST | Replace the 138 kV 40kA circuit switcher XT8 with a 63 kA circuit breaker. | Baseline | 138 | 1 | 6/1/2026 | AEP |  | Appendix A | AEP:100 |  | VA | Cloverdale |  | Replace | EP | 1 |  | 6/1/2026 |  | Yes | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3903.1 | PJM WEST | Replace the Kewannee 138 kV kV L7411 circuit breaker with a SF6 63 kA circuit breaker. | Baseline | 138 | 1.1 | 6/1/2026 | ComEd |  | Appendix A | ComEd:100 |  | IL | Kewanee |  | Replace | EP | 1.1 |  | 6/1/2026 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3344.1 | PJM WEST | Install two (2) 138 kV circuit breakers in the M and N strings in the breaker-and-a half configuration in West Kingsport station 138 kV yard to allow the Clinch River-Moreland Dr. 138 kV to cut in the West Kingsport station | Baseline | 138 | 1.85 | 11/1/2026 | AEP | 2021_1-19 | Appendix A | AEP:100 |  | TN | West Kingsport station |  | Install | EP | 1.85 |  | 11/1/2025 |  | No | 11/2/2021 | 11/2/2021 | 50 |  |  |  | 2021-11-02
b3344.2 | PJM WEST | Upgrade remote end relaying at Riverport 138 kV station due to the line cut in at West Kingsport station | Baseline | 138 | 0.25 | 11/1/2026 | AEP | 2021_1-19 | Appendix A | AEP:100 |  | TN | Riverport station |  | Upgrade | EP | 0.25 |  | 11/1/2026 |  | No | 11/2/2021 | 11/2/2021 | 50 |  |  |  | 2021-11-02
b3347.1 | PJM WEST | Rebuild approximately 20 miles of line between Bancroft and Milton stations with 556 ACSR conductor | Baseline | 69 | 56.55 | 11/1/2026 | AEP | 2021_1-116 | Appendix A | AEP:100 |  | WV | Bancroft- Milton |  | Rebuild | EP | 56.55 |  | 12/17/2031 |  | No | 11/2/2021 | 11/2/2021 | 10 |  |  |  | 2021-11-02
b3347.2 | PJM WEST | Replace the jumpers around Hurrican switch with 556 ACSR | Baseline | 69 | 0.01 | 11/1/2026 | AEP | 2021_1-116 | Appendix A | AEP:100 |  | WV | Hurrican |  | Replace | EP | 0.01 |  | 5/10/2030 |  | No | 11/2/2021 | 11/2/2021 | 10 |  |  |  | 2021-11-02
b3347.3 | PJM WEST | Replace the jumpers around Teays switch with 556 ACSR | Baseline | 69 | 0.01 | 11/1/2026 | AEP | 2021_1-116 | Appendix A | AEP:100 |  | WV | Teays |  | Replace | EP | 0.01 |  | 11/22/2030 |  | No | 11/2/2021 | 11/2/2021 | 10 |  |  |  | 2021-11-02
b3347.4 | PJM WEST | Winfield Station Relay Settings: Update relay settings to coordinate with remote ends on line rebuild | Baseline | 69 | 0.05 | 11/1/2026 | AEP | 2021_1-116 | Appendix A | AEP:100 |  | WV | Winfield |  | Upgrade | EP | 0.05 |  | 6/11/2031 |  | No | 11/2/2021 | 11/2/2021 | 10 |  |  |  | 2021-11-02
b3347.5 | PJM WEST | Bancroft Station Relay Settings: Update relay settings to coordinate with remote ends on line rebuild | Baseline | 69 | 0.03 | 11/1/2026 | AEP | 2021_1-116 | Appendix A | AEP:100 |  | WV | Bancroft |  | Upgrade | EP | 0.03 |  | 12/17/2031 |  | No | 11/2/2021 | 11/2/2021 | 10 |  |  |  | 2021-11-02
b3347.6 | PJM WEST | Milton Station Relay Settings: Update relay settings to coordinate with remote ends on line rebuild. | Baseline | 69 | 0.03 | 11/1/2026 | AEP | 2021_1-116 | Appendix A | AEP:100 |  | WV | Milton |  | Upgrade | EP | 0.03 |  | 12/19/2029 |  | No | 11/2/2021 | 11/2/2021 | 10 |  |  |  | 2021-11-02
b3347.7 | PJM WEST | Putnam Village Station Relay Settings: Update relay settings to coordinate with remote ends on line rebuild | Baseline | 69 | 0.05 | 11/1/2026 | AEP | 2021_1-116 | Appendix A | AEP:100 |  | WV | Putnam Village |  | Upgrade | EP | 0.05 |  | 6/11/2031 |  | No | 11/2/2021 | 11/2/2021 | 10 |  |  |  | 2021-11-02
b3348.1 | PJM WEST | Construct a 138 kV single bus station (Tin Branch) consisting of a 138 kV box bay with a distribution transformer and 12 kV distribution bay. Two 138 kV lines will feed this station (from Logan and Sprigg stations), and distribution will have one 12 kV feed. Install two 138 kV circuit breakers on the line exits. Install 138 kV circuit switcher for the new transformer. | Baseline | 138/12 | 5.58 | 11/1/2026 | AEP | 2021_1-488 | Appendix A | AEP:100 |  | WV | Tin Branch |  | Construct | EP | 5.58 |  | 2/3/2028 |  | No | 11/30/2021 | 11/30/2021 | 25 |  |  |  | 2021-11-30
b3348.2 | PJM WEST | Construct a new 138/46/12 kV Argyle station to replace Dehue station. Install a 138 kV ring bus using a breaker-and-a-half configuration, with an autotransformer with a 46 kV feed and a distribution transformer with a 12 kV distribution bay. Two 138 kV lines will feed this station (from Logan and Wyoming stations). There will also be a 46 kV feed from this station to Becco station. Distribution will have two 12 kV feeds. Retire Dehue station in its entirety. | Baseline | 138 | 10 | 11/1/2026 | AEP | 2021_1-488 | Appendix A | AEP:100 |  | WV | Argyle |  | Construct | EP | 10 |  | 7/19/2027 |  | No | 11/30/2021 | 11/30/2021 | 25 |  |  |  | 2021-11-30
b3348.3 | PJM WEST | Bring the Logan-Sprigg #2 138 kV circuit in and out of Tin Branch station by constructing approximately 1.75 miles of new overhead double circuit 138 kV line. Double circuit T3 series lattice towers will be used along with 795,000 cm ACSR 26/7 conductor. One shield wire will be conventional 7 #8 ALUMOWELD, and one shield wire will be OPGW. | Baseline | 138 | 8.58 | 11/1/2026 | AEP | 2021_1-488 | Appendix A | AEP:100 |  | WV | Tin Branch |  | Loop in | EP | 8.58 |  | 2/3/2028 |  | No | 11/30/2021 | 11/30/2021 | 25 |  |  |  | 2021-11-30
b3348.4 | PJM WEST | Logan-Wyoming No. 1 circuit in and out of the proposed Argyle station. Double circuit T3 series lattice towers will be used along with 795,000 cm ACSR 26/7 conductor. One shield wire will be conventional 7 #8 ALUMOWELD, and one shield wire will be OPGW. | Baseline | 138 | 7.7 | 11/1/2026 | AEP | 2021_1-488 | Appendix A | AEP:100 |  | WV | Argyle |  | Loop in | EP | 7.7 |  | 4/26/2027 |  | No | 11/30/2021 | 11/30/2021 | 25 |  |  |  | 2021-11-30
b3348.5 | PJM WEST | Rebuild approximately 10 miles of 46 kV line between Becco and the new Argyle substation. Retire approximately 16 miles of 46 kV line between the new Argyle substation and Chauncey station. | Baseline | 46 | 33.71 | 11/1/2026 | AEP | 2021_1-488 | Appendix A | AEP:100 |  | WV | Becco - Argyle |  | Rebuild | EP | 33.7 |  | 7/19/2027 |  | No | 11/30/2021 | 11/30/2021 | 25 |  |  |  | 2021-11-30
b3348.6 | PJM WEST | Adjust relay settings due to new line terminations and retirements at Logan, Wyoming, Sprigg, Becco and Chauncey stations. | Baseline | 138 | 0.23 | 11/1/2026 | AEP | 2021_1-488 | Appendix A | AEP:100 |  | WV | Logan, Wyoming, Sprigg, Becco, and Chauncey statio |  | Modify | EP | 0.23 |  | 2/13/2028 |  | No | 11/30/2021 | 11/30/2021 | 25 |  |  |  | 2021-11-30
b3677 | PJM WEST | Rebuild a 13 mile section of 138 kV line 0108 between LaSalle and Mazon with 1113 ACSR or higher rated conductor. The 13 mile portion of line 7713 from Oglesby (future Corbin) to Mazon that shares double circuit towers with line 0108 will also be reconductored due to the rebuild. | Baseline | 138 | 54.4 | 11/1/2026 | ComEd |  | Appendix A | ComEd:100 |  | IL | LaSalle-Mazon |  | Rebuild | IS | 42.06 |  | 6/1/2025 |  | No | 11/19/2021 | 11/19/2021 | 100 |  |  |  | 2021-11-19
b3678 | PJM WEST | Expand Galion 138 kV substation; Install 100 MVAR reactor, associated breaker and relaying. | Baseline | 69 | 5.74 | 11/1/2026 | ATSI |  | Appendix A | ATSI:100 |  | OH | Galion |  | Install | EP | 1.7 |  | 6/1/2027 |  | No | 11/19/2021 | 11/19/2021 | 2 |  |  |  | 2021-11-19
b3679 | PJM WEST | Replace West Fremont 138/69 kV TR2 with a transformer having additional high-side taps. | Baseline | 69 | 6.44 | 11/1/2026 | ATSI |  | Appendix A | ATSI:100 |  | OH | West Fremont 69 kV substation |  | Replace | EP | 2.9 |  | 5/21/2027 |  | No | 11/19/2021 | 11/19/2021 | 4 |  |  |  | 2021-11-19
b3693 | PJM SOUTH | Expand substation and install approximately 294 MVAR cap bank at 500 kV Lexington substation along with a 500 kV breaker. Adjust the tap positions associated with the two 230/69 kV transformers at Harrisonburg to neutral position and lock them. | Baseline | 500 | 5.86 | 11/1/2026 | Dominion | 2021_1-722 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Lexington, Bath County |  | Install | EP | 5.86 |  | 11/1/2026 |  | No | 11/30/2021 | 11/30/2021 | 20 |  |  |  | 2021-11-30
b3353.1 | PJM WEST | Allen substation: Rebuild Allen station to the northwest of its current footprint utilizing a standard air-insulated substation with equipment raised by 7’ concrete platforms and control house raised by a 10’ platform to mitigate flooding concerns. Install five 69 kV 3000A 40 kA circuit breakers in a ring bus (operated at 46 kV) configuration with a 13.2 MVAR capacitor bank. Existing Allen station will be retired (does not include the distribution cost). Distribution scope of work: Install 69/46 kV-12 kV 20 MVA transformer along with 2-12 kV breakers on 7’ concrete platforms (conversion of S2405.1). | Baseline | 46 | 10.55 | 12/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | Allen |  | Rebuild | EP | 10.55 |  | 12/31/2027 |  | No | 11/19/2021 | 11/19/2021 | 30 |  |  |  | 2021-11-19
b3353.2 | PJM WEST | Allen-East Prestonsburg: A 0.20 mile segment of this 46 kV line will be relocated to the new station (SN/SE/WN/WE: 53/61/67/73MVA). (Conversion of S2405.2) | Baseline | 46 | 0.33 | 12/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | Allen – East Prestonsburg |  | Modify | EP | 0.33 |  | 12/31/2027 |  | No | 11/19/2021 | 11/19/2021 | 30 |  |  |  | 2021-11-19
b3353.3 | PJM WEST | McKinney-Allen: The new line extension will walk around the south and east sides of the existing Allen station to the new Allen station being built in the clear. A short segment of new single circuit 69 kV line and a short segment of new double circuit 69 kV line (both operated at 46 kV) will be added to the line to tie into the new Allen station bays. (Conversion of S2405.3) | Baseline | 46 | 1.95 | 12/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | McKinney – Allen |  | Install | EP | 1.95 |  | 12/31/2027 |  | No | 11/19/2021 | 11/19/2021 | 30 |  |  |  | 2021-11-19
b3353.4 | PJM WEST | Stanville-Allen: A segment of this line will have to be relocated to the new station (SN/SE/WN/WE: 50/50/63/63MVA). (Conversion of S2405.4) | Baseline | 46 | 0.17 | 12/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | Stanville – Allen |  | Modify | EP | 0.17 |  | 12/31/2027 |  | No | 11/19/2021 | 11/19/2021 | 30 |  |  |  | 2021-11-19
b3353.5 | PJM WEST | Allen-Prestonsburg: 0.25 mile segment of this existing single circuit will be relocated. The relocated line segment will require construction of one custom self-supporting double circuit dead-end structure and single circuit suspension structure. A short segment of new double circuit 69 kV line (energized at 46 kV) will be added to tie into the new Allen station bays, which will carry Allen-Prestonsburg 46 kV and Allen-East Prestonsburg 46 kV lines. A temporary 0.15 mile section double circuit line will be constructed to keep Allen-Prestonsburg and Allen-East Prestonsburg 46 kV lines energized during construction. (Conversion of S2405.5) | Baseline | 46 | 2.66 | 12/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | Allen – Prestonsburg |  | Modify | EP | 2.66 |  | 12/31/2027 |  | No | 11/19/2021 | 11/19/2021 | 30 |  |  |  | 2021-11-19
b3353.6 | PJM WEST | Remote end work will be required at Prestonsburg, Stanville and McKinney stations. (Conversion of S2405.6) | Baseline | 46 | 0.34 | 12/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | Prestonsburg, Stanville, McKinney |  | Modify | EP | 0.34 |  | 12/31/2027 |  | No | 11/19/2021 | 11/19/2021 | 30 |  |  |  | 2021-11-19
b3360 | PJM WEST | Replace Thelma Transformer #1 with a 138/69/46 kV 130/130/90 MVA transformer and replace 46 kV risers and relaying toward Kenwood substation. Existing TR#1 to be used as spare. | Baseline | 69 | 3.54 | 12/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | Thelma |  | Replace | EP | 3.54 |  | 11/20/2026 |  | No | 11/19/2021 | 11/19/2021 | 50 |  |  |  | 2021-11-19
b3361 | PJM WEST | Rebuild Prestonsburg - Thelma 46kV circuit connecting though Kenwood station, approximately 12.7 miles. Retire Jenny Wiley SS and Van Lear SS. | Baseline | 46 | 63.6 | 12/1/2026 | AEP |  | Appendix A | AEP:100 |  | KY | Prestonsburg - Thelma |  | Rebuild | EP | 63.6 |  | 12/16/2027 |  | No | 11/19/2021 | 5/16/2025 | 50 |  | 12/16/2027 |  | 2021-11-19
b3669.1 | PJM MA | Replace terminal equipment (stranded bus, disconnect switch and circuit breaker) at Church substation (Townsend-Church 138 kV). | Baseline | 138 | 1 | 12/1/2026 | DPL |  | Appendix A | DPL:100 |  | MD | Church |  | Replace | EP | 1 |  | 12/1/2026 |  | No | 11/18/2021 | 11/18/2021 | 0 |  |  |  | 2021-11-18
b3669.2 | PJM MA | Replace terminal equipment (circuit breaker) at Townsend substation (Townsend-Church 138 kV). | Baseline | 138 | 0.45 | 12/1/2026 | DPL |  | Appendix A | DPL:100 |  | DE | Townsend |  | Replace | EP | 0.45 |  | 12/1/2026 |  | No | 11/18/2021 | 11/18/2021 | 0 |  |  |  | 2021-11-18
b3686 | PJM SOUTH | Purchase land close to the bifurcation point of 115 kV line #4 (where the line is split into two sections) and build a new 115 kV switching station called Duncan Store. The new switching station will require space for an ultimate transmission interconnection consisting of a 115 kV six-breaker ring bus (with three breakers installed initially). | Baseline | 115 | 16 | 12/1/2026 | Dominion |  | Appendix A | Dominion:100 |  | VA | Duncan Store, Bremo, Columbia DP |  | Build | EP | 16 |  | 6/30/2027 |  | No | 11/18/2021 | 11/18/2021 | 10 |  |  |  | 2021-11-18
b3711 | PJM WEST | Install 345 kV bus tie 5-20 circuit breaker in the ring at Dresden station in series with existing bus tie 5-6. | Baseline | 345 | 4.6 | 12/1/2026 | ComEd | 2021_2-408 | Appendix A | ComEd:100 |  | IL | Dresden |  | Install | EP | 4.26 |  | 12/1/2026 |  | No | 4/12/2022 | 4/12/2022 | 10 |  |  |  | 2022-04-12
b3762 | PJM WEST | Rebuild EKPC’s Fawkes-Duncannon Lane Tap 556.5 ACSR 69 kV line section (7.2 miles) using 795 ACSR. | Baseline | 69 | 12.77 | 12/1/2026 | EKPC |  | Appendix A | EKPC:100 |  | KY | Fawkes-Duncannon Lane Tap |  | Rebuild | IS | 8.5 |  | 12/1/2024 | 11/17/2024 | No | 12/16/2022 | 12/16/2022 | 98 |  |  |  | 2022-12-16
b3775.1 | PJM WEST | Outside of the Green Acres substation, swap the NIPSCO Green Acre Tap towers from the St. John-Green Acres-Olive 345 kV line to the University Park N-Olive 345 kV line to create a University Park N-Green Acres-Olive and St. John-Olive 345 kV lines. | Baseline | 345 | 1.98 | 12/1/2026 | NEET | 2022_MD-644 (modified) | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ ComEd:54.45,Dayton:45.55_x000D_ |  | IL | St. John-Green Acres-Olive, University Park N-Olive |  | Modify | EP | 1.98 |  | 12/1/2026 |  | No | 1/10/2023 | 1/10/2023 | 10 |  |  |  | 2023-01-10
b3775.10 | PJM WEST | Perform a sag study on the Olive – University Park 345kV line to increase the operating temperature to 225 F. Remediation work includes two tower replacements on the line. | Baseline | 345 | 1.5 | 12/1/2026 | AEP | 2022_MD-908 | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ AEP:100_x000D_ |  | IL | Olive-University Park N |  | Sag Study | EP | 1.5 |  | 12/1/2026 |  | No | 1/10/2023 | 1/10/2023 | 10 |  |  |  | 2023-01-10
b3775.11 | PJM WEST | Upgrade the limiting element at Stillwell substation to increase the rating of the Stillwell-Dumont 345 kV line to match conductor rating. | Baseline | 345 | 0.14 | 12/1/2026 | AEP | 2022_MD-644 (modified) | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ AEP:12.38,ComEd:87.62_x000D_ |  | IL | Stillwell |  | Upgrade | EP | 1.78 |  | 12/1/2026 |  | No | 4/11/2023 | 4/11/2023 | 50 |  |  |  | 2023-04-11
b3775.3 | PJM WEST | Rebuild ComEd’s section of 345 kV double circuit in IL from St. John to Crete (5 miles) with twin bundled 1277 ACAR conductor. | Baseline | 345 | 16.64 | 12/1/2026 | ComEd | 2022_MD-253 | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ ComEd:62.41,Dayton:37.59_x000D_ |  | IL | Crete-St. John, Olive-University Park N-E. Frankfort |  | Rebuild | EP | 16.64 |  | 12/1/2026 |  | No | 1/10/2023 | 1/10/2023 | 5 |  |  |  | 2023-01-10
b3775.4 | PJM WEST | Rebuild 12.7 miles of 345 kV double circuit extending from Crete to E. Frankfort with twin bundled 1277 ACAR conductor. | Baseline | 345 | 42.28 | 12/1/2026 | ComEd | 2022_MD-253 | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ ComEd:100_x000D_ |  | IL | Crete-E. Frankfort, Olive-University Park N-E. Frankfort |  | Rebuild | EP | 42.28 |  | 12/1/2026 |  | No | 1/10/2023 | 1/10/2023 | 5 |  |  |  | 2023-01-10
b3775.5 | PJM WEST | Replace E. Frankfort 345 kV circuit breaker “9-14” with 3150A SF6 circuit breaker. | Baseline | 345 | 4.17 | 12/1/2026 | ComEd | 2022_MD-253 | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ ComEd:100_x000D_ |  | IL | E. Frankfort |  | Replace | EP | 3.27 |  | 12/1/2026 |  | No | 1/10/2023 | 1/10/2023 | 5 |  |  |  | 2023-01-10
b3775.6 | PJM WEST | Perform sag study mitigation work on the Dumont-Stillwell 345 kV line (remove a center-pivot irrigation system from under the line, allowing for the normal and emergency ratings of the line to increase, replace two structures and modify a third structure). | Baseline | 345 | 2.22 | 12/1/2026 | AEP | 2022_MD-644 (modified) | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ AEP:12.38,ComEd:87.62_x000D_ |  | IN | Dumont-Stillwell |  | Sag Study | EP | 2.22 |  | 11/20/2026 |  | No | 1/10/2023 | 4/11/2023 | 50 |  |  |  | 2023-01-10
b3775.7 | PJM WEST | Upgrade the limiting element at Dumont substation to increase the rating of the Stillwell-Dumont 345 kV line to match conductor rating. | Baseline | 345 | 2 | 12/1/2026 | AEP | 2022_MD-644 (modified) | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ AEP:12.38,ComEd:87.62_x000D_ |  | IN | Dumont |  | Upgrade | EP | 2 |  | 12/1/2026 |  | No | 1/10/2023 | 4/11/2023 | 50 |  |  |  | 2023-01-10
b3775.8 | PJM WEST | Upgrade the existing terminal equipment (substation conductor) at St. John on the existing Crete to St. John 345 kV line with bundled 2x1590 ACSR Lapwing | Baseline | 345 | 2 | 12/1/2026 | NEET | 2022_MD-644 (modified) | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ ComEd:62.41,Dayton:37.59_x000D_ |  | IL | St. John |  | Upgrade | EP | 2 |  | 12/1/2026 |  | No | 1/10/2023 | 1/10/2023 | 10 |  |  |  | 2023-01-10
b3775.9 | PJM WEST | Upgrade the existing terminal equipment (substation conductor) at Green Acres on the existing St. John to Green Acres 345 kV line with bundled 2x1590 ACSR Lapwing | Baseline | 345 | 2 | 12/1/2026 | NEET | 2022_MD-644 (modified) | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ ComEd:54.45,Dayton:45.55_x000D_ |  | IL | Green Acres |  | Upgrade | EP | 2 |  | 12/1/2026 |  | No | 1/10/2023 | 1/10/2023 | 10 |  |  |  | 2023-01-10
b3844.1 | PJM MA | Replacement of relays at Macdade, Printz and Morton to increase rating limits of transmission relay equipment. Line protection relays will be upgraded with latest standard relays used across the PECO system. | Baseline | 230 | 1.6 | 12/31/2026 | PECO |  | Appendix A | PECO:100 |  |  | Macdade--(39.9018,-75.296)-{1AA69AA4-1A3D-450C-BFC8-277AC581AAE7} |  | Upgrade | EP | 1.4 |  | 6/30/2026 |  | No | 12/5/2023 | 12/5/2023 | 30 |  |  |  | 2023-12-05
b3720 | PJM WEST | Rebuild the Abbe-Johnson #2 69 kV line (approx. 4.9 miles) with 556 kcmil ACSR conductor. Replace three disconnect switches (A17, D15 & D16) and line drops and revise relay settings at Abbe. Replace one disconnect switch (A159) and line drops and revise relay settings at Johnson. Replace two MOAB disconnect switches (A4 & A5), one disconnect switch (D9), and line drops at Redman. | Baseline | 69 | 12.4 | 6/1/2027 | ATSI |  | Appendix A | ATSI:100 |  | OH | Abbe - Johnson |  | Rebuild | EP | 10.9 |  | 6/1/2027 |  | No | 10/14/2022 | 10/14/2022 | 0 |  |  |  | 2022-10-14
b3721 | PJM WEST | Rebuild and reconductor the Avery-Hayes 138 kV line (approx. 6.5 miles) with 795 kcmil 26/7 ACSR. | Baseline | 138 | 19.49 | 6/1/2027 | ATSI |  | Appendix A | ATSI:100 |  | OH | Avery - Hayes |  | Reconductor | Cancelled | 10.4 |  | 6/1/2027 |  | No | 10/14/2022 | 10/14/2022 | 0 |  |  |  | 2022-10-14
b3723 | PJM WEST | Rebuild the George Washington – Kammer 138 kV circuit, except for 0.1-mile of previously-upgraded T-line outside each terminal station (6.7 miles of total upgrade scope). Remove the existing 6-wired steel lattice towers and supplement the right-of-way as needed. | Baseline | 138 | 18.3 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | WV | George Washington - Kammer |  | Rebuild | IS | 18.3 |  | 6/1/2024 | 4/14/2025 | No | 10/14/2022 | 10/14/2022 | 100 |  |  |  | 2022-10-14
b3724 | PJM WEST | Install 138 kV circuit switcher on the high-side of Transformer #2 at Roanoke station (previously proposed as a portion of s2469.7, posted in 2021 AEP local plan). | Baseline | 138 | 0.1 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | VA | Roanoke |  | Install | EP | 0.1 |  | 8/18/2027 |  | No | 10/14/2022 | 10/14/2022 | 10 |  |  |  | 2022-10-14
b3729 | PJM MA | To increase the Maximum Operating Temperature of DPL Circuit 22088 (Colora-Conowingo 230 kV), install cable shunts on each phase, on each side of four (4) dead-end structures and replace existing insulator bells. | Baseline | 230 | 0.26 | 6/1/2027 | DPL | 2022_1-236, only CRL was accpeted in 2022, just se | Appendix A | DPL:100 |  | MD | Colora, Conowingo |  | Upgrade | EP | 0.26 |  | 6/1/2026 |  | No | 10/4/2022 | 1/9/2024 | 0 |  | 6/1/2026 |  | 2022-10-04
b3730 | PJM MA | Reterminate the Lackawanna T3 and T4 500/230 kV transformers on the 230 kV side to remove them from the 230 kV buses and bring them into dedicated bay positions that are not adjacent to one another. | Baseline | 500/230 | 10.7 | 6/1/2027 | PPL | 2022_1-127 | Appendix A | PPL:100 |  | PA | Lackawanna |  | Modify | UC | 10.7 |  | 12/19/2025 |  | No | 10/4/2022 | 11/1/2022 | 30 |  |  |  | 2022-10-04
b3731 | PJM WEST | Replace 40kV breaker J at McComb station with a new 3000A 40kA breaker | Baseline | 46 | 0.5 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | OH | McComb |  | Replace | EP | 0.5 |  | 8/14/2028 |  | No | 11/18/2022 | 11/18/2022 | 25 |  |  |  | 2022-11-18
b3732 | PJM WEST | Install a 6 MVAR, 34.5kV cap bank at Morgan Run station | Baseline | 34.5 | 0.37 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | OH | Morgan Run |  | Install | EP | 0.37 |  | 5/15/2026 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3733 | PJM WEST | Rebuild the 1.8 mile 69kV T-line between Summerhill and Willow Grove Switch. Replace 4/0 ACSR conductor with 556 ACSR. | Baseline | 69 | 5.1 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | OH | Summerhill - willow Grove switch |  | Rebuild | EP | 5.1 |  | 6/1/2027 |  | No | 11/18/2022 | 11/18/2022 | 10 |  |  |  | 2022-11-18
b3734 | PJM WEST | Install a 7.7 MVAR, 69kV cap bank at both Otway station and Rosemount station | Baseline | 69 | 1.73 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | OH | Otway, Rosement |  | Install | EP | 1.73 |  | 2/23/2028 |  | No | 11/18/2022 | 11/18/2022 | 25 |  |  |  | 2022-11-18
b3735 | PJM WEST | Terminate the existing Broadford – Wolf Hills #1 138 kV line into Abingdon 138 kV Station. This line currently bypasses the existing Abingdon 138 kV Station; Install two new 138 kV circuit breakers on each new line exit towards Broadford and towards Wolf Hills #1; Install one new 138 kV circuit breaker on line exit towards South Abingdon for standard bus sectionalizing | Baseline | 138 | 8.48 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | VA | Abingdon, Wolf Hills - broadford |  | Loop in | UC | 8.48 |  | 12/10/2025 |  | No | 11/18/2022 | 11/18/2022 | 75 |  |  |  | 2022-11-18
b3737.47 | PJM MA | Build New North Delta 500 kV substation (four bay breaker and half configuration ) - the substation will include 12 - 500kV breakers and one 500/230 kV transformer, will allow the termination of six - 500 kV lines | Baseline | 500/230 | 104.1 | 6/1/2027 | Transource | 2021_SAA-63 | Appendix C | Reliability driver (26.73%):_x000D_ PECO:100_x000D_ PublicPolicy driver (73.27%):_x000D_ AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09_x000D_ | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | North Delta |  | Build | EP | 104.1 |  | 10/15/2027 |  | No | 11/4/2022 | 12/5/2023 | 15 |  |  |  | 2022-11-04
b3738 | PJM WEST | Charleroi - Dry Run 138 kV Line: Replace Limiting Terminal Equipment | Baseline | 138 | 0.38 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Charleroi - Dry Run 138 kV |  | Replace | EP | 0.38 |  | 6/1/2027 |  | No | 11/18/2022 | 11/18/2022 | 3 |  |  |  | 2022-11-18
b3739 | PJM WEST | Dry Run - Mitchell 138 kV Line: Replace Limiting Terminal Equipment | Baseline | 138 | 0.4 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Dry Run - Mitchell 138 kV |  | Replace | EP | 0.4 |  | 6/1/2027 |  | No | 11/18/2022 | 11/18/2022 | 2 |  |  |  | 2022-11-18
b3740 | PJM WEST | Glen Falls - Bridgeport 138 kV Line: Replace Limiting Terminal Equipment | Baseline | 138 | 1.88 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Glen Falls - Bridgeport 138 kV |  | Replace | EP | 1.88 |  | 5/29/2026 |  | No | 11/18/2022 | 11/18/2022 | 4 |  |  |  | 2022-11-18
b3741 | PJM WEST | Yukon - Charleroi No.1 138 kV Line: Replace Limiting Terminal Equipment | Baseline | 138 | 0.7 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Yukon - Charleroi No.1 138 kV |  | Replace | EP | 0.7 |  | 6/1/2026 |  | No | 11/18/2022 | 11/18/2022 | 3 |  |  |  | 2022-11-18
b3742 | PJM WEST | Yukon - Charleroi No.1 138 kV Line: Replace Limiting Terminal Equipment | Baseline | 138 | 0.7 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Yukon - Charleroi No.1 138 kV |  | Replace | EP | 0.45 |  | 9/26/2025 |  | No | 11/18/2022 | 11/18/2022 | 4 |  |  |  | 2022-11-18
b3743 | PJM WEST | At Bedington Substation: Replace substation conductor, wavetrap, CT's and upgrade relaying At Cherry Run Substation: Replace substation conductor, wavetrap, CT's, disconnect switches, circuit breaker and upgrade relaying At Marlowe: Replace substation conductor, wavetrap, CT's and upgrade relaying. | Baseline | 500 | 4.66 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | WV | Cherry Run - Harmony Jct Tap 138 kV |  | Replace | IS | 4.6 |  | 6/1/2027 | 11/9/2023 | No | 11/18/2022 | 11/18/2022 | 100 |  |  |  | 2022-11-18
b3744 | PJM WEST | Replace one span of 1272 ACSR from Krendale substation to structure 35 (~630 ft) Replace one span of 1272 ACSR from Shanor Manor to structure 21 (~148 ft) Replace 1272 ACSR risers at Krendale & Shanor Manor Substations Replace 1272 ACSR Substation Conductor at Krendale Substation Replace relaying at Krendale Substation Revise Relay Settings at Butler & Shanor Manor Substations. | Baseline | 138 | 1.75 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Shanor – Krendale 138 kV |  | Replace | IS | 1.75 |  | 12/1/2023 | 11/9/2023 | No | 11/18/2022 | 11/18/2022 | 100 |  |  |  | 2022-11-18
b3745 | PJM WEST | Carbon Center Substation - Install Redundant Relaying | Baseline | 230 | 0.57 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Carbon Center 230 kVSubstation |  | Replace | EP | 0.57 |  | 6/1/2026 |  | No | 11/18/2022 | 11/18/2022 | 2 |  |  |  | 2022-11-18
b3746 | PJM WEST | Meadow Brook Substation - Install Redundant Relaying | Baseline | 500 | 0.21 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | WV | Meadow Brook 500 kV Substation |  | Replace | EP | 0.21 |  | 6/1/2027 |  | No | 11/18/2022 | 11/18/2022 | 1 |  |  |  | 2022-11-18
b3747 | PJM WEST | Bedington Substation - Install Redundant Relaying | Baseline | 500 | 0.28 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | WV | Bedington 500 kV Substation |  | Replace | EP | 0.28 |  | 5/29/2026 |  | No | 11/18/2022 | 11/18/2022 | 0 |  |  |  | 2022-11-18
b3748 | PJM WEST | Replace four Clifty Creek 345 kV 3000A switches with 5000 A 345 kV switches. | Baseline | 345 | 0.85 | 6/1/2027 | AEP | 2022_1-965 | Appendix A | AEP:100 |  | IN | Clifty Creek |  | Replace | IS | 0.85 |  | 6/28/2024 | 6/11/2024 | No | 11/1/2022 | 11/1/2022 | 100 |  |  |  | 2022-11-01
b3749 | PJM MA | Rebuild the New Church - Piney Grove 138 kV line | Baseline | 138 | 63 | 6/1/2027 | DPL |  | Appendix A | DPL:100 |  | MD | New Church - Piney Grove |  | Rebuild | EP | 63 |  | 6/15/2027 |  | No | 10/13/2022 | 11/17/2022 | 12 |  |  |  | 2022-10-13
b3750 | PJM MA | Upgrade Seward Terminal Equipment of the Seward-Blairsville 115 kV Line to increase the line rating such that the Transmission Line conductor is the limiting component. | Baseline | 115 | 0.43 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Seward |  | Upgrade | EP | 0.43 |  | 5/1/2026 |  | No | 10/13/2022 | 11/17/2022 | 20 |  |  |  | 2022-10-13
b3751 | PJM MA | Rebuild 6.4 miles of the Roxbury - Shade Gap 115 kV line from Roxbury to the AE1-071 115 kV ring bus with single circuit 115 kV construction | Baseline | 115 | 15.03 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Roxbury to the AE1-071 |  | Rebuild | EP | 15.03 |  | 7/1/2027 |  | No | 10/13/2022 | 11/17/2022 | 23 |  |  |  | 2022-10-13
b3752 | PJM MA | Rebuild 7.2 miles of the Shade Gap - AE1-071 115 kV line section of the Roxbury - Shade Gap 115 kV line | Baseline | 115 | 17.43 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Shade Gap - AE1-071 115 |  | Rebuild | EP | 17.43 |  | 7/1/2027 |  | No | 10/13/2022 | 11/17/2022 | 23 |  |  |  | 2022-10-13
b3753 | PJM MA | Replace the Tyrone North 115 /46 kV transformer with a new standard 75 MVA top rated bank and upgrade the entire terminal to minimum 100 MVA capability for both SN and SE rating | Baseline | 115/46 | 2.82 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Tyrone North |  | Replace | EP | 2.82 |  | 6/1/2027 |  | No | 10/13/2022 | 11/17/2022 | 2 |  |  |  | 2022-10-13
b3754 | PJM MA | At Maclane tap: Construct a new three breaker ring bus to tie into the Warrior Ridge - Belleville 46 kV D line and the 1LK line | Baseline | 46 | 10.09 | 6/1/2027 | PENELEC |  | Appendix A | PENELEC:100 |  | PA | Maclane |  | Modify | EP | 10.09 |  | 9/9/2028 |  | No | 10/13/2022 | 11/17/2022 | 0 |  |  |  | 2022-10-13
b3755 | PJM MA | Convert Locust Street 69kV from a Straight Bus to a Ring Bus. | Baseline | 69 | 46.5 | 6/1/2027 | PSEG |  | Appendix A | PSEG:100 |  | NJ | Locust Street |  | Modify | UC | 30 |  | 6/1/2027 |  | No | 10/13/2022 | 11/17/2022 | 54 |  |  |  | 2022-10-13
b3756 | PJM MA | Convert Maple Shade 69kV from a Straight Bus to a Ring Bus | Baseline | 69 | 39.5 | 6/1/2027 | PSEG |  | Appendix A | PSEG:100 |  | NJ | Maple Shade |  | Modify | UC | 33.9 |  | 6/1/2027 |  | No | 10/13/2022 | 11/17/2022 | 54 |  |  |  | 2022-10-13
b3757 | PJM MA | Convert existing Medford 69kV Straight bus to Seven breaker ring bus, , construct a new 230/69kV transformer at Cox's Corner and a new line from Cox's Corner to Medford. | Baseline | 69 | 116.3 | 6/1/2027 | PSEG |  | Appendix A | PSEG:100 |  | NJ | Medford |  | Modify | UC | 101.5 |  | 12/31/2027 |  | No | 10/13/2022 | 11/17/2022 | 40 |  |  |  | 2022-10-13
b3758 | PJM MA | Construct a new 69kV line from 14th Street to Harts Lane | Baseline | 69 | 41.3 | 6/1/2027 | PSEG |  | Appendix A | PSEG:100 |  | NJ | 14th Street to Harts Lane |  | Construct | UC | 34.4 |  | 6/1/2027 |  | No | 10/13/2022 | 11/17/2022 | 54 |  |  |  | 2022-10-13
b3759 | PJM SOUTH | * Wreck and rebuild approximately 10.5 miles of 115kV Line #23 segment from Oak Ridge to AC2-079 Tap to minimum emergency ratings of 393 MVA Summer / 412 MVA Winter. Structures to be rebuilt to current 115kV standards. Transmission Estimated Cost: $37.1M * Reconductor 115kV Line #44 segment from Oak Ridge to AC2-079 Tap which also shares the same structures to minimum emergency ratings of 393 MVA Summer / 412 MVA Winter. Existing conductor is about 70 years old. Transmission Estimated Cost: $3.9M | Baseline | 115 | 39.5 | 6/1/2027 | Dominion |  | Appendix A | Dominion:100 |  | VA | Bell Ave, Suffolk |  | Reconductor | EP | 41 |  | 2/1/2027 |  | No | 11/17/2022 | 12/12/2024 | 20 |  |  |  | 2022-11-17
b3761 | PJM WEST | Install 138 kV Breaker on the Ridgway 138/46 kV #2 Transformer | Baseline | 138 | 1.1 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | Ridgway 138/46 kV |  | Install | EP | 1.1 |  | 6/1/2027 |  | No | 12/16/2022 | 12/16/2022 | 0 |  |  |  | 2022-12-16
b3766.1 | PJM WEST | Hayes – New Westville 138 kV line: Build ~0.19 miles of 138 kV line to the Indiana/ Ohio State line to connect to AES’s line portion of the Hayes – New Westville 138 kV line with the conductor size 795 ACSR26/7 Drake. The following cost includes the line construction and ROW. | Baseline | 138 | 0.38 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | OH | Hayes - New Westville |  | Build | EP | 0.38 |  | 6/17/2027 |  | No | 12/6/2022 | 12/6/2022 | 25 |  |  |  | 2022-12-06
b3766.2 | PJM WEST | Hayes – Hodgin 138 kV line: Build ~0.05 miles of 138 kV line with the conductor size 795 ACSR26/7 Drake. The following cost includes the line construction, ROW, and fiber. | Baseline | 138 | 1.22 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | OH | Hayes-Hodgin |  | Build | EP | 1.22 |  | 6/17/2027 |  | No | 12/6/2022 | 12/6/2022 | 25 |  |  |  | 2022-12-06
b3766.3 | PJM WEST | Hayes 138 kV: Build a new 4-138 kV circuit breaker ring bus. The following cost includes the new station construction, property purchase, metering, station fiber and the College Corner –Randolph 138 kV line connection. | Baseline | 138 | 7.44 | 6/1/2027 | AEP |  | Appendix A | AEP:100 |  | OH | Hayes |  | Build | EP | 7.44 |  | 6/17/2027 |  | No | 12/6/2022 | 12/6/2022 | 25 |  |  |  | 2022-12-06
b3766.4 | PJM WEST | New Westville – AEP Hodgin 138kV Line: Construct a 138kV 1.86-mile single circuit transmission line. This transmission line will help loop the radial load served at New Westville as part of the overall effort to improve reliability in this area. Also, it provides a source to feed New Westville load while the 138kV tie built back into the AES Ohio system | Baseline | 138 | 3.7 | 6/1/2027 | Dayton |  | Appendix A | Dayton:100 |  | OH | New Westville – AEP Hodgin 138kV Line |  | Construct | EP | 3.7 |  | 3/3/2027 |  | No | 12/6/2022 | 12/6/2022 | 20 |  |  |  | 2022-12-06
b3766.5 | PJM WEST | New Westville – West Manchester 138kV Line: Construct a new approximate 11-mile single circuit 138kV line from New Westville to the Lewisburg tap off 6656. Convert a portion of 6656 West Manchester – Garage Rd 69kV line between West Manchester - Lewisburg to 138kV operation (circuit is built to 138kV). This will utilize part of the line already built to 138kV and will take place of the 3302 that currently feeds New Westville. The 3302 line will be retired as part of this project. | Baseline | 138 | 16 | 6/1/2027 | Dayton |  | Appendix A | Dayton:100 |  | OH | New Westville – West Manchester 138kV Line |  | Construct | EP | 16 |  | 6/18/2027 |  | No | 12/6/2022 | 12/6/2022 | 20 |  |  |  | 2022-12-06
b3766.6 | PJM WEST | West Manchester Substation: The West Manchester Substation will be expanded to a double bus double breaker design where AES Ohio will install one 138kV circuit breaker, a 138/69kV transformer, and eight new 69kV circuit breakers. These improvements will improve help improve a non-standard bus arrangement where there is only one bus tie today and will improve the switching arrangement for the West Sonora Delivery Point. | Baseline | 138 | 9.9 | 6/1/2027 | Dayton |  | Appendix A | Dayton:100 |  | OH | West Manchester Substation |  | Modify | EP | 9.9 |  | 11/20/2026 |  | No | 12/6/2022 | 12/6/2022 | 20 |  |  |  | 2022-12-06
b3768 | PJM MA | Rebuild/Reconductor the Germantown - Lincoln 115 kV Line. Approximately 7.6 miles. Upgrade limiting terminal equipment at Lincoln, Germantown and Straban | Baseline | 115 | 20 | 6/1/2027 | ME |  | Appendix A | ME:100 |  | PA | Lincoln,Germantown and Straban |  | Rebuild | Cancelled | 17.36 |  | 6/1/2027 |  | No | 12/6/2022 | 12/5/2023 | 0 |  |  |  | 2022-12-06
b3769 | PJM MA | Install second TMI 500/230kV Transformer with additional 500 and 230 bus expansions | Baseline | 500/230 | 30.19 | 6/1/2027 | ME | 2022-W1-880 | Appendix A | ME:45.74,PPL:54.26 |  | PA | TMI |  | Install | EP | 30.19 |  | 6/1/2027 |  | No | 12/6/2022 | 1/6/2023 | 3 |  |  |  | 2022-12-06
b3770 | PJM MA | Rebuild 1.4 miles of existing single circuit 230 kV tower line between BGE's Graceton substation to the Brunner Island PPL tie-line at the MD/PA state line to double circuit steel pole line with one (1) circuit installed to uprate 2303 circuit | Baseline | 230 | 10.17 | 6/1/2027 | BGE | 2022-W1-912 | Appendix A | BGE:99.98,ME:0.01,PPL:0.01 |  | PA | Graceton - Brunner Island |  | Rebuild | EP | 8.4 |  | 6/1/2027 |  | No | 12/6/2022 | 1/6/2023 | 25 |  |  |  | 2022-12-06
b3771 | PJM MA | Reconductor two (2) 230 kV circuits from Conastone to Northwest #2 | Baseline | 230 | 40.86 | 6/1/2027 | BGE | 2022-W1-94 | Appendix A | BGE:70.70,PEPCO:29.30 |  | MD | Conastone - North West |  | Reconductor | EP | 37.76 |  | 6/1/2027 |  | No | 12/6/2022 | 1/6/2023 | 25 |  |  |  | 2022-12-06
b3772 | PJM SOUTH | Reconductor 27.3 miles of the Messick Road - Morgan 138 kV Line from 556 ACSR to 954 ACSR. At Messick Road Substation: Replace 138 kV wave trap, circuit breaker, CT's, disconnect switch, and substation conductor and upgrade relaying. At Morgan Substation: Upgrade Relaying | Baseline | 138 | 49.23 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | MD | Messick Road - Morgan |  | Reconductor | EP | 49.23 |  | 12/25/2028 |  | No | 12/6/2022 | 1/6/2023 | 4 |  |  |  | 2022-12-06
b3773 | PJM WEST | Install (1) 31.7 MVAR switched capacitor, 138 kV breaker, and associated relaying at Warfordsburg Substation | Baseline | 138 | 3.05 | 6/1/2027 | APS |  | Appendix A | APS:100 |  | PA | McConnellsburg |  | Install | EP | 3.05 |  | 6/1/2027 |  | No | 12/6/2022 | 4/11/2025 | 4 |  |  |  | 2022-12-06
b3774 | PJM MA | Upgrade terminal equipment at Brunner Island (on the Brunner Island - Yorkana 230 kV circuit) | Baseline | 230 | 2.5 | 6/1/2027 | PPL |  | Appendix A | PPL:100 |  | PA | Brunner Island |  | Replace | EP | 2.5 |  | 6/1/2027 |  | No | 12/6/2022 | 1/6/2023 | 10 |  |  |  | 2022-12-06
b3779 | PJM SOUTH | Cut existing 230 kV line #2183 and extend from Poland Road substation to Evergreen Mills substation. Approximately 0.59 miles of new line will be built from the cut-in to the Evergreen Mills substation. Cut and extend the existing 230 kV line #2183 creating a new line #2210 from Brambleton substation to be terminated at Evergreen Mills substation. Approximately 0.59 miles of new line will be built from the cut-in to the Evergreen Mills substation. | Baseline | 230 | 7.71 | 6/1/2027 | Dominion | 2022_2-648 | Appendix A | Dominion:100 |  | VA | Poland, Evergreen Mills, Brambleton |  | Modify | EP | 7.71 |  | 6/1/2027 |  | No | 4/11/2023 | 4/11/2023 | 20 |  |  |  | 2023-04-11
b3800.1 | PJM MA | Build New Otter Creek 500 kV (Collinsville) - (switching station -Two bay three breaker configuration). | Baseline | 500 | 32.76 | 6/1/2027 | PPL | 2022-W3-374 | Appendix A | APS:13.16,BGE:0.71,Dominion:74.28,DPL:0.36,PECO:0.68,PEPCO:10.59,PPL:0.22 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Build | EP | 32.76 |  | 4/23/2027 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.10 | PJM MA | Rebuild the Germantown-Lincoln 115 kV line for 230 kV double circuit construction. | Baseline | 115 | 30.1 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  |  | Rebuild | EP | 30.1 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.100 | PJM WEST | Establish a new 500 kV breaker position for the low-side of the existing 765/500 kV transformer at Cloverdale Station. The new position will be between two new 500 kV circuit breakers located in a new breaker string, electrically converting the 500 kV yard to "double-bus double-breaker" configuration. | Baseline | 500 | 11.59 | 6/1/2027 | AEP | 2022-W3-410 | Appendix A | AEP:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Cloverdale |  | Install | EP | 11.59 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 10 |  |  |  | 2023-12-05
b3800.101 | PJM WEST | 502 Junction substation two 500 kV circuit breaker expansion. | Baseline | 500 | 30.6 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:25.59,BGE:9.79,Dominion:51.94,PEPCO:12.68 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | 502 Junction |  | Upgrade | EP | 30.6 |  | 12/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 10 |  |  |  | 2023-12-05
b3800.102 | PJM WEST | New 500 kV line from existing 502 Junction substation to Woodside 500 KV substation (bypass Black Oak) (NEET Portion). | Baseline | 500 | 315.64 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:25.59,BGE:9.79,Dominion:51.94,PEPCO:12.68 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Build | EP | 315.64 |  | 12/31/2031 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.103 | PJM WEST | Rebuild ~16 miles of the Gore-Stonewall 138 kV line with 500 kV overbuild (502 Jct to Woodside 500 kV line section). | Baseline | 500 | 158.8 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:25.59,BGE:9.79,Dominion:51.94,PEPCO:12.68 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Build | EP | 151.72 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 30 |  |  |  | 2023-12-05
b3800.104 | PJM WEST | Rebuild ~15 miles of the Stonewall-Millville 138 kV line with 500 kV overbuild (502 Jct to Woodside 500 kV line section). | Baseline | 500 | 165.23 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:9.18,BGE:7.21,Dominion:72.52,PEPCO:11.09 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | WV | Woodside |  | Build | EP | 136.93 |  | 6/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 30 |  |  |  | 2023-12-05
b3800.105 | PJM WEST | Rebuild Millville-Doubs 138 kV for ~16 miles from structure MVF1-39 to structure MVF1-101(outside of Doubs Substation) with 500 kV overbuild | Baseline | 500 | 162.11 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:9.18,BGE:7.21,Dominion:72.52,PEPCO:11.09 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Build | EP | 147.45 |  | 6/1/2028 |  | No | 12/6/2023 | 12/6/2023 | 30 |  |  |  | 2023-12-06
b3800.106 | PJM WEST | Woodside 500 kV substation (Except terminations, Transformer, Cap Banks and Statcom). | Baseline | 500 | 43.96 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Build | EP | 43.96 |  | 12/31/2031 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.107 | PJM WEST | Line Termination cost at Woodside 500 kV for 502 Jct to Woodside 500 kV line. | Baseline | 500 | 0.51 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:25.59,BGE:9.79,Dominion:51.94,PEPCO:12.68 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Modify | EP | 0.51 |  | 12/31/2031 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.108 | PJM WEST | Line Termination cost at Woodside 500 kV for Woodside to Aspen 500 kV line. | Baseline | 500 | 0.51 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:9.18,BGE:7.21,Dominion:72.52,PEPCO:11.09 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Modify | EP | 0.51 |  | 12/31/2031 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.109 | PJM WEST | Termination work for two 500/138 kV transformer at Woodside 500 kV substation | Baseline | 500/138 | 1.35 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:100 |  | VA | Woodside |  | Build | EP | 1.35 |  | 12/31/2031 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.11 | PJM MA | Rebuild the Hunterstown-Lincoln 115 kV line for 230 kV double circuit construction. | Baseline | 115 | 11.48 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  |  | Rebuild | EP | 11.48 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.110 | PJM WEST | Two 500/138 kV transformers at Woodside 500 kV substation. | Baseline | 500/138 | 33.68 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:100 |  | VA | Woodside |  | Install | EP | 33.68 |  | 12/31/2031 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.111 | PJM WEST | Construct the Woodside-Stonewall 138 kV No. 1 line. | Baseline | 138 | 6.28 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:100 |  | VA | Woodside |  | Build | EP | 6.28 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 15 |  |  |  | 2023-12-05
b3800.112 | PJM WEST | Construct the Woodside-Stonewall 138 kV No. 2 line. | Baseline | 138 | 6.31 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:100 |  | VA | Woodside |  | Build | EP | 6.31 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 15 |  |  |  | 2023-12-05
b3800.113 | PJM WEST | Two 150 MVAR Cap banks and one +500/-500 MVAR STATCOM at Woodside 500 kV substation. | Baseline | 500 | 44.22 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Install | EP | 44.22 |  | 12/31/2031 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.114 | PJM WEST | Stonewall 138 kV substation two 138kV breaker expansion. | Baseline | 138 | 8.3 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:100 |  | VA | Woodside |  | Upgrade | EP | 8.3 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 30 |  |  |  | 2023-12-05
b3800.115 | PJM WEST | Line work for terminating Doubs to Bismark line for Doubs side for Woodside 500 kV substation. (NEET Portion) | Baseline | 500 | 0.51 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:27.49,BGE:9.83,Dominion:53.78,PEPCO:8.90 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Modify | EP | 0.51 |  | 12/31/2031 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.116 | PJM WEST | Line work for terminating Doubs to Bismark line for Doubs side for Woodside 500 kV substation. (FE Portion) | Baseline | 500 | 0.06 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:27.49,BGE:9.83,Dominion:53.78,PEPCO:8.90 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Modify | EP | 0.06 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.117 | PJM WEST | Line work for terminating Doubs to Bismark line for Bismark side for Woodside 500 kV substation. (NEET Portion) | Baseline | 500 | 0.51 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:21.09,BGE:6.55,Dominion:64.94,PEPCO:7.42 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Modify | EP | 0.51 |  | 12/31/2031 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.118 | PJM WEST | Line work for terminating Doubs to Bismark line into Woodside 500 kV substation. (DOM Portion) | Baseline | 500 | 5.1 | 6/1/2027 | Dominion | 2022-W3-853 | Appendix A | APS:21.09,BGE:6.55,Dominion:64.94,PEPCO:7.42 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Modify | EP | 5.1 |  | 9/30/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.119 | PJM WEST | New 500 kV transmission line from Woodside substation to Aspen substation (in DOM zone). (NEET Portion) | Baseline | 500 | 71.72 | 6/1/2027 | NEET | 2022-W3-853 | Appendix A | APS:9.18,BGE:7.21,Dominion:72.52,PEPCO:11.09 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Woodside |  | Build | Cancelled | 71.72 |  | 12/31/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.12 | PJM MA | Rebuild the Germantown-Carroll 138 kV line for 230 kV double circuit construction (MAIT). | Baseline | 138 | 12.16 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  |  | Rebuild | UC | 12.16 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 50 |  |  |  | 2023-12-05
b3800.120 | PJM SOUTH | Terminate new NextEra 500 kV line from Woodside into Goose Creek substation (instead of termination at the new Aspen substation). The Goose Creek 500 kV cap bank will be moved to Aspen substation | Baseline | 500 | 30.49 | 6/1/2027 | Dominion | 2022-W3-853 | Appendix A | APS:9.18,BGE:7.21,Dominion:72.52,PEPCO:11.09 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Aspen |  | Build | EP | 30.49 |  | 9/30/2030 |  | No | 12/5/2023 | 12/5/2023 | 10 |  |  |  | 2023-12-05
b3800.121 | PJM WEST | Kammer to 502 Junction 500 kV line: Conduct LIDAR Sag Study to assess SE rating and needed upgrades. | Baseline | 500 | 0.1 | 6/1/2027 | AEP | 2022-W3-853 | Appendix A | AEP:21.66,APS:0.01,BGE:7.14,DEOK:0.01,Dominion:62.25,PEPCO:8.93 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | 502 Junction |  | Sag Study | EP | 0.1 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.122 | PJM SOUTH | Rebuild 500 kV line No. 514 from Doubs-Goose Creek 500 kV line. The Doubs-Goose Creek 500 kV line will be rebuilt (APS Portion) | Baseline | 500 | 103.27 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:0.08,Dominion:99.90,PEPCO:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Doubs |  | Build | EP | 103.27 |  | 6/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.123 | PJM SOUTH | Doubs substation work - Re-terminate the rebuilt Doubs-Goose Creek 500 kV line in its existing bay, Terminate the new Doubs-Aspen 500 kV line in the open bay at Doubs, Replace three 500 kV breakers, Replace 500 kV terminal equipment including disconnect switches, CTs and substation conductor & Replace relaying. (APS Portion) | Baseline | 500 | 31.7 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:0.08,Dominion:99.90,PEPCO:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Doubs |  | Build | EP | 31.7 |  | 6/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.124 | PJM SOUTH | New Doubs to Aspen 500 kV line - Aspen substation is not yet constructed but is a component in Dominion's proposal 2022-W3-692. (APS Portion) | Baseline | 500 | 68.8 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:0.09,Dominion:99.89,PEPCO:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Doubs |  | Build | EP | 68.8 |  | 6/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.125 | PJM SOUTH | Rebuild the Doubs-Dickerson 230 kV line. This will be underbuilt on the new Doubs-Goose Creek 500 kV line. (APS Portion) | Baseline | 230 | 13.04 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | PEPCO:100 |  | VA | Doubs |  | Modify | EP | 13.04 |  | 6/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.126 | PJM SOUTH | Rebuild the Doubs-Aqueduct 230 kV line. This will be underbuilt on the new Doubs-Aspen 500 kV line. (APS Portion) | Baseline | 230 | 11.35 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | PEPCO:100 |  | VA | Doubs |  | Modify | EP | 11.35 |  | 6/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.127 | PJM SOUTH | Rebuild the Dickerson-Aqueduct 230 kV line. This will be underbuilt on the new Doubs-Aspen 500 kV line. (APS Portion) | Baseline | 230 | 6.8 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | PEPCO:100 |  | VA | Doubs |  | Modify | EP | 6.8 |  | 6/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.128 | PJM WEST | Construct new Woodside-Goose Creek 500 kV line for ~15 miles on single circuit monopole structures within the Doubs-Goose Creek Corridor. (FE Portion) | Baseline | 500 | 115.3 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:9.26,BGE:7.30,Dominion:72.31,PEPCO:11.13 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Doubs |  | Construct | EP | 115.3 |  | 12/31/2031 |  | No | 7/10/2024 | 7/10/2024 | 30 |  |  |  | 2024-07-10
b3800.129 | PJM WEST | Construct 500 kV line from existing structure MVF1-101 on the Doubs-Millville 138 kV line around Doubs substation and into the entrance of the Doubs-Goose Creek corridor. (~2 miles) | Baseline | 500 | 13.2 | 6/1/2027 | APS | 2022-W3-853 | Appendix A | APS:9.26,BGE:7.30,Dominion:72.31,PEPCO:11.13 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Doubs |  | Construct | EP | 13.2 |  | 6/1/2031 |  | No | 7/10/2024 | 7/10/2024 | 0 |  |  |  | 2024-07-10
b3800.13 | PJM MA | Rebuild the Germantown-Carroll 138 kV line to 230 kV double circuit construction (APS-PE Section). | Baseline | 138 | 47.31 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:82.49,ME:17.51 |  | MD |  |  | Rebuild | EP | 47.31 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.14 | PJM MA | Construct New 230 kV Hunterstown-Carroll line (MAIT section). | Baseline | 230 | 17.37 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | APS:99.86,ME:0.14 |  | PA |  |  | Construct | EP | 17.37 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.15 | PJM MA | Construct New 230 kV Hunterstown-Carroll line (APS-PE Section). | Baseline | 230 | 6.71 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:99.86,ME:0.14 |  | MD |  |  | Construct | UC | 6.71 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 50 |  |  |  | 2023-12-05
b3800.16 | PJM MA | Expand Carroll 230 kV substation to ring bus. | Baseline | 230 | 7.62 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:99.86,ME:0.14 |  | MD |  |  | Modify | EP | 7.62 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.17 | PJM MA | Network upgrade at Caroll substation. | Baseline | 230 | 0.43 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:99.86,ME:0.14 |  | MD |  |  | Upgrade | EP | 0.43 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.18 | PJM MA | Add a new 230 kV Breaker at the Hunterstown 230 kV substation for the new Hunterstown-Carroll 230 kV termination. | Baseline | 230 | 2.31 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | APS:99.86,ME:0.14 |  | PA |  |  | Build | EP | 2.31 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.19 | PJM MA | Reconductor Lincoln-Orrtanna 115 kV line. | Baseline | 115 | 10.98 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  |  | Reconductor | UC | 10.98 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 50 |  |  |  | 2023-12-05
b3800.2 | PJM MA | Break the existing TMI-Peach Bottom line within the existing right-of-way and install new structures rerouting the line toward Chanceford switchyard taps being constructed by PPL. | Baseline | 500 | 7.43 | 6/1/2027 | ME | 2022-W3-374, DENL | Appendix A | APS:13.16,BGE:0.71,Dominion:74.28,DPL:0.36,PECO:0.68,PEPCO:10.59,PPL:0.22 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Modify | EP | 7.43 |  | 6/1/2027 |  | No | 12/6/2023 | 5/1/2024 | 0 |  |  |  | 2023-12-06
b3800.20 | PJM MA | Fayetteville-Grand Point 138 kV – Replace line trap at Grand Point 138 kV. | Baseline | 138 | 0.4 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:100 |  | MD |  |  | Reconductor | EP | 0.4 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 10 |  |  |  | 2023-12-05
b3800.200 | PJM SOUTH | Build a new 500kV line from Aspen - Golden on 500/230kV double circuit structures with substation upgrades at Aspen and Golden. New conductor to have a minimum summer normal rating of 4357MVA. | Baseline | 500 | 176.02 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Aspen, Golden |  | Build | EP | 176.02 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.201 | PJM SOUTH | Install (2) 500-230kV transformer banks at Golden substation | Baseline | 500/230 | 70 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Golden |  | Install | EP | 70 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.202 | PJM SOUTH | Install (1) 500-230kV transformer bank at Aspen substation | Baseline | 500/230 | 42 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:86.28,PEPCO:13.72 |  | VA | Aspen |  | Install | EP | 42 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.203 | PJM SOUTH | Install a 2nd 500-230 kV 1440MVA transformer at Mars substation | Baseline | 500/230 | 42.19 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Mars |  | Install | UC | 42.19 |  | 5/20/2027 |  | No | 10/31/2023 | 12/5/2023 | 50 |  |  |  | 2023-10-31
b3800.204 | PJM SOUTH | Reconductor 0.5 mile section of 230kV Line #2150 Golden - Paragon Park Circuit 1 to achieve a summer rating of 1573 MVA. | Baseline | 230 | 1.44 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Golden, Paragon Park |  | Rebuild | EP | 1.44 |  | 6/1/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.205 | PJM SOUTH | Reconductor 0.5 mile section of 230kV Line #2081 Golden - Paragon Park Circuit 2 to achieve a summer rating of 1573 MVA. | Baseline | 230 | 1.44 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Golden, Paragon Park |  | Rebuild | EP | 1.44 |  | 6/1/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.206 | PJM SOUTH | Upgrade Paragon Park substation line conductors to 4000A continuous current rating for 230kV Lines #2081 & Line #2150. | Baseline | 230 | 0.09 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Paragon Park |  | Upgrade | EP | 0.09 |  | 6/1/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.207 | PJM SOUTH | Reconductor 230kV Line #2207 Paragon Park - Beco to achieve a summer rating of 1573 MVA. | Baseline | 230 | 3.36 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Paragon Park, BECO |  | Rebuild | EP | 3.36 |  | 6/1/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.208 | PJM SOUTH | Upgrade Paragon Park substation conductor and line leads to 4000A continuous current rating for 230kV Line #2207. | Baseline | 230 | 0.1 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Paragon Park |  | Upgrade | EP | 0.1 |  | 6/1/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.209 | PJM SOUTH | Upgrade BECO substation equipment to 4000A continuous current rating for 230kV Line #2207. | Baseline | 230 | 1.86 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | BECO |  | Upgrade | EP | 1.86 |  | 6/1/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.21 | PJM MA | Reid-Ringgold 138 kV – Replace line trap, substation conductor, breaker, relaying and CTs at Ringgold. | Baseline | 138 | 3.8 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:100 |  | MD |  |  | Replace | EP | 3.8 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 10 |  |  |  | 2023-12-05
b3800.210 | PJM SOUTH | Build a new 230kV line from Mars - Lockridge on 500/230kV double circuit structures to achieve a summer rating of 1573 MVA. Install 230kV equipment at Mars and Lockridge. Remove 230 kV line No. 2095 Mars-Shellhorn and 230 kV line No. 2292 Mars-Sojourner in the existing transmission corridor between Sojourner and Mars substations so that they can be rerouted to the south side of Mars substation, adding approximately 2 miles of new conductor. This is to allow for termination of the line No.2413 and 5003 Golden-Mars 230 and 500 kV circuits into Mars substation. Cut 230 kV line No. 2095 Mars-Shellhorn into Sojourner substation, creating 230 kV line No. 2427 (Mars-Sojourner) and 230 kV line No. 2095 (Sojourner-Shellhorn). Upgrade 4 230 kV breakers at Sojourner substation from 63 kA to 80 kA. | Baseline | 230 | 57.95 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Mars, Lockridge |  | Build | EP | 154.95 |  | 6/1/2028 |  | No | 10/31/2023 | 4/1/2025 | 10 |  |  |  | 2023-10-31
b3800.211 | PJM SOUTH | Build a new 230kV line from Lockridge - Golden on 500/230kV double circuit structures to achieve a summer rating of 1573 MVA. Install 230kV equipment at Golden and Lockridge. | Baseline | 230 | 56.93 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Lockridge, Golden |  | Build | EP | 56.93 |  | 6/1/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.212 | PJM SOUTH | Build a new 500kV Line from Mars-Golden on 500/230kV double circuit structures with substation upgrades at Golden and Mars. New conductor to have a monimum summer normal rating of 4357 MVA. | Baseline | 500 | 228.04 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | APS:99.96,Dominion:0.04 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Mars, Golden |  | Build | EP | 228.04 |  | 6/1/2028 |  | No | 10/31/2023 | 4/1/2025 | 10 |  |  |  | 2023-10-31
b3800.213 | PJM SOUTH | Cut 500kV Line # 558 Brambleton - Goose Creek into Aspen substation. Upgrade 500kV terminal equipment at Aspen and Goose Creek to 5000A continuous rating current. At Goose Creek, replace circuit breakers 59582 and 55882, and associated disconnect switches, breaker leads, bus, and line risers to accommodate 5000A rating. | Baseline | 500 | 50.12 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | APS:99.39,Dominion:0.61 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Brambleton, Goose Creek |  | Modify | EP | 50.12 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 25 |  |  |  | 2023-10-31
b3800.214 | PJM SOUTH | Build a new 500kV Line from Aspen - Goose Creek to achieve a summer rating of 4357 MVA. Install new 500kV terminal equipment at Aspen. | Baseline | 500 | 38.53 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | APS:99.39,Dominion:0.61 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Aspen, Goose Creek |  | Build | EP | 38.53 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.215 | PJM SOUTH | Cut 230kV Line #2150 Sterling Park - Paragon Park Circuit 1 into Golden substation and install 230kV equipment at Golden. Upgrade relay settings at Golden substation for upgrading 230kV Line #2150 to 4000A continuous current rating. | Baseline | 230 | 57.62 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Sterling Park, Paragon Park |  | Modify | EP | 57.62 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.216 | PJM SOUTH | Cut 230kV Line #2081 Sterling Park - Paragon Park Circuit 2 into Golden substation and install 230kV equipment at Golden. Upgrade relay settings at Golden substation for upgrading 230kV Line #2081 to 4000A continuous current rating. | Baseline | 230 | 57.62 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Sterling Park, Paragon Park |  | Modify | EP | 57.62 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.217 | PJM SOUTH | Build a new 230kV line from Aspen - Sycolin Creek on 500/230kV double circuit structures to achieve a summer rating of 1573 MVA. Install 230kV equipment at Golden and Sycolin Creek. | Baseline | 230 | 60.42 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:86.28,PEPCO:13.72 |  | VA | Aspen, Sycolin Creek |  | Rebuild | EP | 60.42 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.218 | PJM SOUTH | Build a new 230kV line from Sycolin Creek - Golden on 500/230kV double circuit structures to achieve a summer rating of 1573 MVA. Install 230kV equipment at Golden and Sycolin Creek. | Baseline | 230 | 69.83 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Sycolin Creek, Golden |  | Rebuild | EP | 69.83 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.219 | PJM SOUTH | Replace 7 overdutied 230kV breakers at Beaumeade substation with 80kA breakers | Baseline | 230 | 3.03 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Beaumeade |  | Replace | EP | 3.03 |  | 12/3/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.22 | PJM MA | Install DTT relaying at Straban substation. | Baseline | 115 | 0.67 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  |  | Install | EP | 0.67 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.220 | PJM SOUTH | Replace 4 overdutied 230kV breakers at BECO substation with 80kA breakers | Baseline | 230 | 1.81 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | BECO |  | Replace | EP | 1.81 |  | 8/16/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.221 | PJM SOUTH | Replace 4 overdutied 230kV breakers at Belmont substation with 80kA breakers | Baseline | 230 | 1.9 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Belmont |  | Replace | EP | 1.9 |  | 10/28/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.222 | PJM SOUTH | Replace 1 overdutied 230kV breaker at Discovery substation with 80kA breaker | Baseline | 230 | 0.49 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Discovery |  | Replace | EP | 0.49 |  | 3/15/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.223 | PJM SOUTH | Replace 1 overdutied 230kV breaker at Pleasant View substation with 80kA breaker | Baseline | 230 | 0.51 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Pleasant View |  | Replace | EP | 0.51 |  | 3/15/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.224 | PJM SOUTH | Replace 2 overdutied 230kV breakers at Shellhorn substation with 80kA breakers | Baseline | 230 | 0.93 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Shellhorn |  | Replace | EP | 0.93 |  | 2/12/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.225 | PJM SOUTH | Change 500kV Line #558 destination at Brambleton to Aspen Substation and upgrade line protection relays | Baseline | 500 | 0.23 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | APS:5.20,DL:0.46,Dominion:91.40,ME:0.59,PEPCO:2.35 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Brambleton |  | Modify | EP | 0.23 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.226 | PJM SOUTH | Change 230kV Lines # 2081 and 2150 at Paragon Park substation destination to Golden Substation and upgrade line protection relays | Baseline | 230 | 0.3 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Paragon Park |  | Modify | EP | 0.3 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.227 | PJM SOUTH | Change 230kV Lines # 2081 and 2150 at Sterling Park substation destination to Golden Substation and upgrade line protection relays | Baseline | 230 | 0.3 | 6/1/2027 | Dominion | 2022-W3-692 | Appendix A | Dominion:100 |  | VA | Sterling Park |  | Modify | EP | 0.3 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.228 | PJM SOUTH | Reconductor 1.47 miles of 230kV circuits 2081 and 2150 from Sterling Park to Golden substation. Upgrade terminal equipment at Sterling Park to 4000A continuous current | Baseline | 230 | 7.97 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Sterling Park, Golden |  | Reconductor | EP | 7.97 |  | 6/1/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.229 | PJM SOUTH | Reconductor 0.67 miles of 230kV circuits 2194 and 9231 from Davis Drive to Sterling Park substation. Terminal equipment at remote end substations will be installed or upgraded to 4000A continuous current rating to support new conductor ratings | Baseline | 230 | 5.53 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Davis Drive, Sterling Park |  | Reconductor | EP | 5.53 |  | 6/1/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.23 | PJM MA | Revise Relay Settings at Lincoln substation. | Baseline | 115 | 0.31 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  |  | Modify | EP | 0.31 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.230 | PJM SOUTH | Reset relays at Breezy Knoll for the revised current rating of 230kV Line #2098 Plesant View - Hamilton | Baseline | 230 | 0.02 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | Dominion:100 |  | VA | Breezy Knoll |  | Modify | EP | 0.02 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.231 | PJM SOUTH | Reset relays at Dry Mill for the revised current rating of 230kV Line #2098 Plesant View - Hamilton | Baseline | 230 | 0.02 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | Dominion:100 |  | VA | Dry Mill |  | Modify | EP | 0.02 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.232 | PJM SOUTH | Reset relays at Hamilton for the revised current rating of 230kV Line #2098 Plesant View - Hamilton | Baseline | 230 | 0.01 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | Dominion:100 |  | VA | Hamilton |  | Modify | EP | 0.01 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.233 | PJM SOUTH | Upgrade equipment to 4000A continuous current rating at Pleasant View substation in support of 230kV Line #2098 wreck and rebuild. Replace circuit breakers 274T2098 & 2098T2180 and associated disconnect switches, breaker leads, bus, and line risers to accommodate 4000A rating | Baseline | 230 | 6.24 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | Dominion:100 |  | VA | Pleasant View |  | Modify | EP | 1.81 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.234 | PJM SOUTH | Wreck and rebuild approximately one (1) mile of 230kV Line #2098 between Pleasant View and structure 2098/9, where Line #2098 turn towards Hamilton substation | Baseline | 230 | 3.44 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | Dominion:100 |  | VA | Pleasant View |  | Reconductor | EP | 3.44 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.235 | PJM SOUTH | Replace 5 overdutied 230kV breakers at Loudoun substation with 80kA breakers | Baseline | 230 | 2.32 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | Dominion:100 |  | VA | Loudoun |  | Replace | EP | 2.32 |  | 10/5/2031 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.236 | PJM SOUTH | Replace 2 overdutied 500kV breakers at Ox substation with 63kA breakers | Baseline | 500 | 2.51 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | Dominion:100 |  | VA | Ox |  | Replace | EP | 2.51 |  | 1/5/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.237 | PJM SOUTH | Replace 1 overdutied 500kV breaker at Pleasant View substation with a 63kA breaker | Baseline | 500 | 1.29 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | Dominion:100 |  | VA | Pleasant View |  | Replace | EP | 1.29 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.238 | PJM SOUTH | Upgrade equipment to 4000A continuous current rating at Pleasant View substation in support of 230kV Line #203 rebuild. Replace circuit breakers 203T274 & L3T203 and associated disconnect switches, breaker leads, bus, and line risers to accommodate 4000A rating | Baseline | 230 | 1.81 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | APS:8.09,BGE:8.25,Dominion:64.87,PEPCO:18.79 |  | VA | Pleasant View |  | Modify | EP | 1.81 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.239 | PJM SOUTH | Wreck and rebuild 230kV Line #203 between Pleasant View and structure 203/15 using double circuit 500/230kV structures. The 500kV line is from Aspen - Doubs. | Baseline | 230 | 6.87 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | APS:8.09,BGE:8.25,Dominion:64.87,PEPCO:18.79 |  | VA | Pleasant View |  | Rebuild | EP | 6.87 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.24 | PJM MA | Revise Relay Settings at Germantown substation. | Baseline | 115 | 0.47 | 6/1/2027 | ME | 2022-W3-837 | Appendix A | ME:100 |  | PA |  |  | Modify | EP | 0.47 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.240 | PJM SOUTH | Build a new 500kV line from Aspen - Doubs using double circuit 500/230kV structures. The 230kV line is from Pleasant View - structure 203/15. Install terminal equipment at Aspen for a 5000A line to Doubs (First Energy). This includes GIS breakers, GIS-to-AIS transition equipment, and metering CCVTs and CTs for the tie line. | Baseline | 500 | 41.68 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | APS:0.09,Dominion:99.89,PEPCO:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Aspen, Doubs |  | Build | EP | 41.68 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.241 | PJM SOUTH | Rebuild 500kV Line #514 from Goose Creek - Doubs using 500/230kV double circiut structures. The new double circuit towers will accommodate 230kV Line #2098 between Pleasant View substation and structure 2098/9. Upgrade equipment at Goose Creek to 5000A continuous current rating in support of Line #514 wreck and rebuild. Replace circuit breakers 514T595 & 51482 and associated disconnect switches, breaker leads, bus, and line risers to accommodate 5000A rating. | Baseline | 500 | 16.11 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | APS:0.08,Dominion:99.90,PEPCO:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Goose Creek |  | Rebuild | EP | 16.11 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.242 | PJM SOUTH | Upgrading switches 20366M and 20369M and line leads to 4000A continuous current rating of 230kV Line #203 at Edwards Ferry substation | Baseline | 230 | 0.51 | 6/1/2027 | Dominion | 2022-W3-516 | Appendix A | APS:11.45,BGE:14.14,Dominion:42.82,PEPCO:31.59 |  | VA | Edwards Ferry |  | Modify | EP | 0.51 |  | 9/13/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.243 | PJM SOUTH | Rebuild 7.26 miles of existing 500 kV circuit from Dickerson Station H to Ed's Ferry area to accommodate the new 500 kV circuit between Doubs and Aspen. (The 500 kV portion of the work) | Baseline | 500 | 37.2 | 6/1/2027 | PEPCO | 2022-W3-660 | Appendix A | APS:0.09,Dominion:99.89,PEPCO:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Dickerson, Edwards Ferry |  | Rebuild | UC | 37.2 |  | 12/31/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.244 | PJM SOUTH | Rebuild 7.26 miles of existing 230 kV circuit from Dickerson Station H to Ed's Ferry area to accommodate the new 500 kV circuit between Doubs and Aspen. (The 230kV portion of the project) | Baseline | 230 | 18.6 | 6/1/2027 | PEPCO | 2022-W3-660 | Appendix A | APS:9.78,BGE:12.07,Dominion:51.18,PEPCO:26.97 |  | VA | Dickerson, Edwards Ferry |  | Rebuild | UC | 18.6 |  | 12/31/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.245 | PJM SOUTH | Reconfigure Dickerson H 230 kV Substation and upgrade terminal equipment. | Baseline | 230 | 10.58 | 6/1/2027 | PEPCO | 2022-W3-660 | Appendix A | APS:9.78,BGE:12.07,Dominion:51.18,PEPCO:26.97 |  | VA | Dickerson |  | Modify | UC | 10.58 |  | 12/31/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.25 | PJM MA | Taneytown substation terminal upgrade. | Baseline | 138 | 0.53 | 6/1/2027 | APS | 2022-W3-837 | Appendix A | APS:100 |  | MD |  |  | Upgrade | EP | 0.53 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.26 | PJM MA | Build High Ridge 500 kV substation - Three bay breaker and half configuration. | Baseline | 500 | 0 | 6/1/2027 | BGE | 2022-W3-660 |  |  |  | MD |  |  | Build | UC | 0 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.27 | PJM MA | High Ridge 500 kV substation (cut into Brighton-Waugh Chapel 500 kV line) - Waugh Chapel side. | Baseline | 500 | 33.67 | 6/1/2027 | BGE | 2022-W3-660 | Appendix A | BGE:70.66,PEPCO:29.34 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Build | UC | 33.67 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.28 | PJM MA | High Ridge 500 kV substation (cut into Brighton-Waugh Chapel 500 kV line) -Brighton side. | Baseline | 500 | 33.67 | 6/1/2027 | BGE | 2022-W3-660 | Appendix A | APS:0.68,BGE:97.41,Dominion:1.91 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Build | UC | 33.67 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.29 | PJM MA | High Ridge termination for the North Delta-High Ridge 500 kV line. | Baseline | 500 | 33.67 | 6/1/2027 | BGE | 2022-W3-660 | Appendix A | BGE:2.58,Dominion:59.28,DPL:0.02,PEPCO:28.48,PSEG:9.24,RE:0.40 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Build | UC | 33.67 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.3 | PJM MA | Build New 500kV AC line from the new Otter Creek (Chanceford) 500 kV switchyard – towards PA/MD border ~12.5 miles Ø Rebuild the existing Otter Creek - Conastone 230 kV line to become a double-circuit 500 kV line, operate Conastone circuit at 230 kV initially | Baseline | 500 | 102.8 | 6/1/2027 | PPL | 2022-W3-374 | Appendix A | APS:13.16,BGE:0.71,Dominion:74.28,DPL:0.36,PECO:0.68,PEPCO:10.59,PPL:0.22 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Build | EP | 102.8 |  | 4/30/2027 |  | No | 12/6/2023 | 5/1/2024 | 5 |  |  |  | 2023-12-06
b3800.30 | PJM MA | High Ridge - Install two 500/230 kV transformers. | Baseline | 500/230 | 22.11 | 6/1/2027 | BGE | 2022-W3-660 | Appendix A | BGE:62.75,PEPCO:37.25 |  | MD |  |  | Install | UC | 22.11 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.300 | PJM SOUTH | Wreck/Rebuild 230kV Line #2135 segment Hollymeade Junction – Cash’s Corner using double-circuit capable 230 kV poles. (The second 230kV circuit will be wired but not have terminal ends.) | Baseline | 230 | 32.45 | 6/1/2027 | Dominion | 2022-W3-211 | Appendix A | Dominion:100 |  | VA | Hollymeade Junction, Cash's Corner |  | Rebuild | EP | 19.42 |  | 6/30/2028 |  | No | 10/31/2023 | 5/6/2025 | 0 |  |  |  | 2023-10-31
b3800.301 | PJM SOUTH | Wreck/Rebuild 230kV Line #2135 Cash’s Corner – Gordonsville using double-circuit capable 230 kV poles. (The second 230kV circuit will be wired but not have terminal ends.) | Baseline | 230 | 21.51 | 6/1/2027 | Dominion | 2022-W3-211 | Appendix A | Dominion:100 |  | VA | Cash's Corner, Gordonsville |  | Rebuild | EP | 12.57 |  | 6/30/2028 |  | No | 10/31/2023 | 5/6/2025 | 10 |  |  |  | 2023-10-31
b3800.302 | PJM SOUTH | Upgrade Cash's Corner switches 213576 and 213579 and line leads to 4000A continuous current rating of 230kV Line #2135. | Baseline | 230 | 0.51 | 6/1/2027 | Dominion | 2022-W3-211 | Appendix A | Dominion:100 |  | VA | Cash's Corner |  | Upgrade | EP | 0.51 |  | 6/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.303 | PJM SOUTH | Upgrade Gordonsville substation line leads to 4000A continuous current rating of 230kV Line #2135. | Baseline | 230 | 0.08 | 6/1/2027 | Dominion | 2022-W3-211 | Appendix A | Dominion:100 |  | VA | Gordonsville |  | Upgrade | EP | 0.08 |  | 6/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.304 | PJM SOUTH | Upgrade Charlottesville substation switch 205415 and line leads to 4000A continuous current rating of 230 kV line No. 2054 | Baseline | 230 | 0.3 | 6/1/2027 | Dominion | 2022-W3-211 | Appendix A | Dominion:100 |  | VA | Hollymeade |  | Upgrade | EP | 0.3 |  | 12/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.305 | PJM SOUTH | Install one (1) 300 MVAR Static synchronous Compensator (STATCOM) & associated equipment at Beaumeade substation. | Baseline | 230 | 52 | 6/1/2027 | Dominion | 2022-W3-231 | Appendix A | Dominion:100 |  | VA | Beaumeade |  | Install | EP | 43.57 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 5 |  |  |  | 2023-10-31
b3800.306 | PJM SOUTH | Install one (1) 500KV, 150 MVAr Shunt Capacitor Bank & associated equipment at Morrisville substation. This addition will require a control house expansion to accommodate for two new panels. | Baseline | 500 | 3.63 | 6/1/2027 | Dominion | 2022-W3-231 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Morrisville |  | Install | EP | 3.63 |  | 2/28/2027 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.307 | PJM SOUTH | Install one (1) 500kV, 300 MVAR Static synchronous Compensator (STATCOM) & associated equipment at Mars substation. | Baseline | 500 | 50 | 6/1/2027 | Dominion | 2022-W3-231 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Mars |  | Install | EP | 41.27 |  | 12/31/2027 |  | No | 10/31/2023 | 12/5/2023 | 5 |  |  |  | 2023-10-31
b3800.308 | PJM SOUTH | Install one (1) 230kV, 150MVAr Shunt Capacitor Bank & associated equipment at Mars substation. | Baseline | 230 | 7 | 6/1/2027 | Dominion | 2022-W3-231 | Appendix A | Dominion:100 |  | VA | Mars |  | Install | EP | 5.26 |  | 6/20/2027 |  | No | 10/31/2023 | 12/5/2023 | 5 |  |  |  | 2023-10-31
b3800.309 | PJM SOUTH | Install one (1) 230kV, 150MVAr Shunt Capacitor Bank & associated equipment at Wishing Star Substation. | Baseline | 230 | 6.09 | 6/1/2027 | Dominion | 2022-W3-231 | Appendix A | Dominion:100 |  | VA | Wishing Star |  | Install | EP | 6.09 |  | 11/30/2027 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.31 | PJM MA | Build new North Delta-High Ridge 500 kV line. | Baseline | 500 | 42.06 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | Dominion:60.85,DPL:0.01,PECO:0.01,PEPCO:29.24,PSEG:9.48,RE:0.41 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Build | EP | 13.36 |  | 12/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 5 |  |  |  | 2023-12-05
b3800.310 | PJM SOUTH | install one (1) 500kV, 293.8MVAr Shunt Capacitor Bank & associated equipment at Wishing Star Substation. | Baseline | 500 | 3.97 | 6/1/2027 | Dominion | 2022-W3-231 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Wishing Star |  | Install | EP | 3.97 |  | 11/30/2027 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.311 | PJM SOUTH | Rebuild 500kV Line #545 Bristers - Morrisville as a single circuit monopole line to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 4357 MVA. | Baseline | 500 | 65.86 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:91.07,PEPCO:8.93 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Bristers, Morrisville |  | Rebuild | EP | 65.86 |  | 1/31/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.312 | PJM SOUTH | Rebuild 500kV Line #569 Loudoun - Morrisville to accommodate the new 500 kV line in the existing right-of-way. New conductor to have a summer rating of 4357 MVA. | Baseline | 500 | 175.62 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:11.72,Dominion:88.28 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Loudoun, Morrisville |  | Rebuild | EP | 175.62 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.313 | PJM SOUTH | Rebuild approximately 10.29 miles line segment of Line #535 (Meadow Brook to Loudoun) to accommodate the new 500 kV line in the existing ROW. | Baseline | 500 | 65.86 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:13.93,BGE:6.86,Dominion:70.92,PEPCO:8.29 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Meadow Brook, Loudoun |  | Rebuild | EP | 65.86 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.314 | PJM SOUTH | Rebuild approximately 4.83 miles of 500kV Line #546 Mosby - Wishing Star to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 4357 MVA. Upgrade and install equipment at Mosby substation to upgrade terminal equipment to be rated for 5000A for 500kV Lines #546. | Baseline | 500 | 49.78 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:41.98,Dominion:34.03,PEPCO:23.99 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Mosby, Wishing Star |  | Rebuild | EP | 49.78 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.315 | PJM SOUTH | Rebuild approximately 4.59 miles of 500kV Line #590 Mosby - Wishing Star to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 4357 MVA. Upgrade and install equipment at Mosby substation to upgrade terminal equipment to be rated for 5000A for 500kV Lines #590. | Baseline | 500 | 49.78 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:41.98,Dominion:34.03,PEPCO:23.99 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Mosby, Wishing Star |  | Rebuild | EP | 49.78 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.316 | PJM SOUTH | Rebuild approximately 6.17 miles of 230kV Line #2030 Gainesville - Mint Springs to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 13.98 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Gainesville, Mint Springs |  | Rebuild | EP | 13.98 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.317 | PJM SOUTH | Rebuild approximately 1.58 miles of 230kV Line #2030 Mint Springs - Loudoun to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 3.59 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Mint Springs, Loudoun |  | Rebuild | EP | 3.59 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.318 | PJM SOUTH | Rebuild approximately 4.2 miles of 230kV Line #2045 Loudoun - North Star to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 14.52 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Loudoun, North Star |  | Rebuild | EP | 14.52 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.319 | PJM SOUTH | Rebuild approximately 0.88 miles of 230kV Line #2045 North Star - Brambleton to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 3.04 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | North Star, Brambleton |  | Rebuild | EP | 3.04 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.32 | PJM MA | Build new North Delta-High Ridge 500 kV line. (~59 miles). | Baseline | 500 | 407.11 | 6/1/2027 | BGE | 2022-W3-660 | Appendix A | BGE:2.58,Dominion:59.28,DPL:0.02,PEPCO:28.48,PSEG:9.24,RE:0.40 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Build | UC | 407.11 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.320 | PJM SOUTH | Rebuild approximately 1.22 miles of 230kV Line #2227 Brambleton - Racefield to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 4.36 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Brambleton, Racefield |  | Rebuild | EP | 4.36 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.321 | PJM SOUTH | Rebuild approximately 3.69 miles of 230kV Line #2094 Racefield - Loudoun to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 13.2 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Racefield, Loudoun |  | Rebuild | EP | 13.2 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.322 | PJM SOUTH | Rebuild approximately 9.16 miles of 230kV Line #2101 Bristers - Nokesville to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 12.99 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Bristers, Nokesville |  | Rebuild | EP | 12.99 |  | 6/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.323 | PJM SOUTH | Rebuild approximately 2.89 miles of 230kV Line #2101 Nokesville - Vint Hill TP to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 4.1 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Nokesville, Vint Hill TP |  | Rebuild | EP | 4.1 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.324 | PJM SOUTH | Rebuild approximately 0.33 miles of 230kV Line #2101 Vint Hill TP - Vint Hill to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 0.47 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Vint Hill TP, Vint Hill |  | Rebuild | EP | 0.47 |  | 6/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.325 | PJM SOUTH | Rebuild approximately 3.32 miles of 230kV Line #2114 Rollins Ford - Vint Hill to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 4.35 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Rollins Ford, Vint Hill |  | Rebuild | EP | 4.35 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.326 | PJM SOUTH | Rebuild approximately 10.09 miles of 230kV Line #2114 Vint Hill - Elk Run to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 13.21 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Vint Hill, Elk Run |  | Rebuild | EP | 13.21 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.327 | PJM SOUTH | Rebuild approximately 4.43 miles of 230kV Line #2140 Heathcote - Catharpin to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 10.64 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Heathcote, Catharpin |  | Rebuild | EP | 10.64 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.328 | PJM SOUTH | Rebuild approximately 2.88 miles of 230kV Line #2140 Catharpin - Loudoun to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 6.92 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Catharpin, Loudoun |  | Rebuild | EP | 6.92 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.329 | PJM SOUTH | Rebuild approximately 0.25 miles of 230kV Line #2151 Railroad DP - Gainesville to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 4.39 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Railroad DP, Gainesville |  | Rebuild | EP | 4.39 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.33 | PJM MA | Replace terminal equipment limitations at Brighton 500 kV - on the existing Brighton-Waugh Chapel 500 kV (5053) or new Brighton-High Ridge 500 kV. | Baseline | 500 | 4.13 | 6/1/2027 | PEPCO | 2022-W3-660 | Appendix A | APS:0.68,BGE:86.77,Dominion:1.91,PEPCO:10.64 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Replace | UC | 4.13 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.330 | PJM SOUTH | Rebuild approximately 4.14 miles of 230kV Line #2163 Vint Hill - Liberty to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 17.56 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Vint Hill, Liberty |  | Rebuild | EP | 17.56 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.331 | PJM SOUTH | Rebuild approximately 0.48 miles of Line #2176 Heathcote - Gainesville to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 8.78 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Heathcote, Gainesville |  | Rebuild | EP | 8.78 |  | 2/28/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.332 | PJM SOUTH | Rebuild approximately 1.11 miles of Line #2222 Rollins Ford - Gainesville to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 230 | 13.17 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Rollins Ford, Gainesville |  | Rebuild | EP | 13.17 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.333 | PJM SOUTH | Rebuild approximately 1.65 miles of Line #183 Bristers - Ox to accommodate the new 500 kV line in the existing ROW. New conductor to have a summer rating of 1573 MVA. | Baseline | 115 | 8.78 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Bristers, Ox |  | Rebuild | EP | 8.78 |  | 6/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.334 | PJM SOUTH | Replace 4 overdutied 230kV breakers at Loudoun Substation with 80kA breakers | Baseline | 230 | 1.72 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Loudoun |  | Replace | EP | 1.72 |  | 10/5/2031 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.335 | PJM SOUTH | Replace 1 overdutied 500kV breaker at Ox Substation with a 63kA breaker | Baseline | 500 | 1.29 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Ox |  | Replace | EP | 1.29 |  | 12/15/2031 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.336 | PJM SOUTH | Upgrade and install equipment at Bristers substation to support the new conductor 5000A rating for 500kV Line #545. | Baseline | 500 | 5.72 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:91.07,PEPCO:8.93 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Bristers |  | Upgrade | EP | 5.72 |  | 1/31/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.337 | PJM SOUTH | Upgrade and install equipment at Brambleton substation to support the new conductor termination. All terminal equipment for 230kV Lines #2045 & #2094 to be rated for 4000A continuous current rating. | Baseline | 230 | 4.65 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Brambleton |  | Upgrade | EP | 4.65 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.338 | PJM SOUTH | Revise relay settings at Dawkins Branch | Baseline | 230 | 0.02 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Dawkins Branch |  | Modify | EP | 0.02 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.339 | PJM SOUTH | Upgrade and install equipment at Gainesville substation to support the new conductor termination. All terminal equipment for 230kV Line #2030 to be rated for 4000A continuous current rating. | Baseline | 230 | 3.71 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Gainesville |  | Upgrade | EP | 3.71 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.34 | PJM MA | Rebuild 5012 (existing Peach Bottom-Conastone) (new Graceton-Conastone) 500 kV line on single circuit structures within existing ROW and cut into North Delta 500 kV and Gracetone 500 kV stations. | Baseline | 500 | 70 | 6/1/2027 | BGE | 2022-W3-660 | Appendix A | BGE:12.36,Dominion:24.57,DPL:25.17,JCPL:7.90,Neptune:0.88,PENELEC:1.60,PEPCO:12.32,PSEG:14.57,RE:0.63 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Rebuild | UC | 70 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.340 | PJM SOUTH | Revise relay settings at Heathcote | Baseline | 230 | 0.02 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Heathcote |  | Modify | EP | 0.02 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.341 | PJM SOUTH | Upgrade and install equipment at Loudoun substation for 230kV Line #2094 Loudoun - Racefield to be rated for 4000A continuous current rating. | Baseline | 230 | 2.5 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Loudoun |  | Upgrade | EP | 2.5 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.342 | PJM SOUTH | Upgrade and install equipment at Loudoun substation for 230kV Line #2045 Loudoun - North Star to be rated for 4000A continuous current rating. | Baseline | 230 | 2.5 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Loudoun |  | Upgrade | EP | 2.5 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.343 | PJM SOUTH | Upgrade and install equipment at Loudoun substation for 230kV Line #2030 Loudoun - Mint Springs to be rated for 4000A continuous current rating. | Baseline | 500 | 1 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Loudoun |  | Upgrade | EP | 1 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.344 | PJM SOUTH | Upgrade and install equipment at Loudoun substation to support the new conductor 5000A rating for 500kV Line #569 Loudoun - Morrisville. | Baseline | 500 | 10.7 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:11.72,Dominion:88.28 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Loudoun |  | Upgrade | EP | 10.7 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.345 | PJM SOUTH | Revise relay settings at Mint Springs | Baseline | 230 | 0.03 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Mint Springs |  | Modify | EP | 0.03 |  | 6/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.346 | PJM SOUTH | Upgrade and install equipment at Morrisville substation to support the new 500kV conductor termination. All terminal equipment to be rated for 5000 A for 500kV Line #545 & #569. Upgrade 500 kV bus 2 to 5000 A. | Baseline | 500 | 17.54 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:11.72,Dominion:88.28 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Morrisville |  | Upgrade | EP | 17.54 |  | 6/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.347 | PJM SOUTH | Revise relay settings at North Star | Baseline | 230 | 0.03 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | North Star |  | Modify | EP | 0.03 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.348 | PJM SOUTH | Revise relay settings at Racefield | Baseline | 230 | 0.03 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Racefield |  | Modify | EP | 0.03 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.349 | PJM SOUTH | Revise relay settings at Railroad | Baseline | 230 | 0.02 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Railroad |  | Modify | EP | 0.02 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.35 | PJM MA | Rebuild 5012 (existing Peach Bottom-Conastone) (new North Delta-Graceton PECO) 500 kV line on single circuit structures within existing ROW and cut into North Delta 500 kV and Gracetone 500 kV stations. | Baseline | 500 | 43.78 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | BGE:49.42,Dominion:31.22,DPL:0.01,JCPL:0.01,PECO:3.75,PEPCO:15.57,PSEG:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Rebuild | EP | 29.86 |  | 12/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 6 |  |  |  | 2023-12-05
b3800.350 | PJM SOUTH | Install terminal equipment at Vint Hill substation to support a 5000A line to Morrisville. Update relay settings for 230kV Lines #2101, #2163, and 500kV Line #535. | Baseline | 500 | 23.64 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:9.79,Dominion:90.21 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Vint Hill |  | Upgrade | EP | 23.64 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.351 | PJM SOUTH | Update relay settings at Vint Hill for 230kV Line #2101 Vint Hill - Bristers | Baseline | 230 | 0.03 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Vint Hill |  | Modify | EP | 0.03 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.352 | PJM SOUTH | Update relay settings at Vint Hill for 230kV Line #2163 Vint Hill - Liberty | Baseline | 230 | 0.03 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Vint Hill |  | Modify | EP | 0.03 |  | 6/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.353 | PJM SOUTH | Update relay settings at Vint Hill for 500kV Line #535 Vint Hill - Loudoun | Baseline | 500 | 0.03 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:13.93,BGE:6.86,Dominion:70.92,PEPCO:8.29 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Vint Hill |  | Modify | EP | 0.03 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.354 | PJM SOUTH | Install terminal equipment at Wishing Star substation to support a 5000A line to Vint Hill. Update relay settings for 500kV Lines #546 and #590. | Baseline | 500 | 12.3 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:21.45,Dominion:78.55 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Wishing Star |  | Upgrade | EP | 12.3 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.355 | PJM SOUTH | Revise relay settings at Youngs Branch | Baseline | 230 | 0.02 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | Dominion:100 |  | VA | Youngs Branch |  | Modify | EP | 0.02 |  | 12/31/2029 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.356 | PJM SOUTH | Build a new 500kV line from Vint Hill to Wishing Star. The line will be supported on single circuit monopoles. New conductor to have a summer rating of 4357 MVA. Line length is approximately 16.59 miles. | Baseline | 500 | 87.81 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:21.45,Dominion:78.55 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Vint Hill, Wishing Star |  | Build | EP | 87.81 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.357 | PJM SOUTH | Build a new 500kV line from Morrisville to Vint Hill. New conductor to have a summer rating of 4357 MVA. Line length is approximately 19.71 miles. | Baseline | 500 | 101.89 | 6/1/2027 | Dominion | 2022-W3-711 | Appendix A | APS:9.79,Dominion:90.21 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Morrisville, Vint Hill |  | Build | EP | 101.89 |  | 6/30/2030 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.358 | PJM SOUTH | Replace single unit Locks 230/115 kV 168MVA transformer TX #7 with new single unit transformer with a rating of 224 MVA. Lead lines at the 115 kV level will be upgraded to 2000 A. | Baseline | 230/115 | 7.14 | 6/1/2027 | Dominion | 2022-W3-731 | Appendix A | Dominion:100 |  | VA | Locks |  | Replace | EP | 7.14 |  | 12/30/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.359 | PJM SOUTH | Wreck and rebuild Line #2090 Ladysmith CT – Summit D.P. segment as a double circuit 230kV line to achieve a summer rating of 1573 MVA. Only one circuit will be wired at this stage. Upgrade circuit breaker leads, switches and line leads at Ladysmith CT to 4000A | Baseline | 230 | 32 | 6/1/2027 | Dominion | 2022-W3-74 | Appendix A | Dominion:100 |  | VA | Ladysmith CT, Summit DP |  | Rebuild | EP | 36.5 |  | 1/15/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.36 | PJM MA | Rebuild 5012 (existing Peach Bottom-Conastone) (new North Delta-Graceton BGE) 500 kV line on single circuit structures within existing ROW and cut into North Delta 500 kV and Gracetone 500 kV stations. | Baseline | 500 | 10.44 | 6/1/2027 | BGE | 2022-W3-660 | Appendix A | BGE:51.35,Dominion:32.44,DPL:0.01,JCPL:0.01,PEPCO:16.17,PSEG:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Rebuild | UC | 10.44 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.360 | PJM SOUTH | Wreck/Rebuild 230kV Line #2054 segment Charlottesville – Hollymeade Junction using double-circuit capable 230 kV poles. (The second 230kV circuit will be wired but not have terminal ends.) | Baseline | 230 | 70.14 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Charlottesville, Proffit |  | Rebuild | EP | 46.53 |  | 12/29/2027 |  | No | 10/31/2023 | 5/6/2025 | 10 |  |  |  | 2023-10-31
b3800.361 | PJM SOUTH | Rebuild 230kV Line #233 Charlottesville – Hydraulic Rd – Barracks Road – Crozet – Dooms | Baseline | 230 | 54.54 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Charlottesville, Hydraulic Road, Barracks Road, Crozet, Dooms |  | Rebuild | EP | 54.54 |  | 11/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.362 | PJM SOUTH | Rebuild 230kV Line #291 segment from Charlottesville – Barracks Road | Baseline | 230 | 22.5 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Charlottesville, Barracks Road |  | Rebuild | EP | 22.5 |  | 11/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.363 | PJM SOUTH | Rebuild 230kV Line #291 segment from Barracks Road – Crozet | Baseline | 230 | 20.81 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Barracks Road, Crozet |  | Rebuild | EP | 20.81 |  | 11/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.364 | PJM SOUTH | Rebuild 230kV Line #291 segment Crozet – Dooms | Baseline | 230 | 11.23 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Crozzet, Dooms |  | Rebuild | EP | 11.23 |  | 11/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.365 | PJM SOUTH | Hollymeade Substation Relay Revision for 230kV Line #2054 Charlottsville - Hollymeade | Baseline | 230 | 0.01 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Charlottesville, Hollymeade |  | Modify | EP | 0.01 |  | 12/29/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.366 | PJM SOUTH | Upgrade the terminal equipment at Charlottesville to 4000A for 230kV Line #2054 (Charlottsville – Hollymeade). | Baseline | 230 | 0.97 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Charlottesville |  | Upgrade | EP | 0.97 |  | 12/29/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.367 | PJM SOUTH | Proffit DP Substation Relay Revision for 230kV Line #2054 Charlottesville - Hollymeade | Baseline | 230 | 0.02 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Proffit DP |  | Modify | EP | 0.02 |  | 12/29/2027 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3800.368 | PJM SOUTH | Barracks Rd Substation Relay Reset to accommodate the rebuilt line 230kV Lines #233 and #291. | Baseline | 230 | 0.03 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Barracks Road |  | Modify | EP | 0.03 |  | 11/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.369 | PJM SOUTH | Crozet Substation Relay Reset to accommodate the rebuilt line 230kV Lines #233 and #291. | Baseline | 230 | 0.03 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Crozet |  | Modify | EP | 0.03 |  | 11/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.37 | PJM MA | Replace terminal equipment limitations at Conastone 500 kV - on the (existing Peach Bottom-Conastone) or (new Graceton-Conastone) 500 kV line. | Baseline | 500 | 4.93 | 6/1/2027 | BGE | 2022-W3-660 | Appendix A | BGE:12.36,Dominion:24.57,DPL:25.17,JCPL:7.90,Neptune:0.88,PENELEC:1.60,PEPCO:12.32,PSEG:14.57,RE:0.63 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Replace | UC | 4.93 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.370 | PJM SOUTH | Charlottesville Substation Terminal Equipment Upgrade for 230kV Lines #233 & #291 Rebuild | Baseline | 230 | 1.5 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Charlottesville |  | Upgrade | EP | 1.5 |  | 11/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.371 | PJM SOUTH | Upgrade Hydraulic Rd Substation Equipment for 230kV Line #233 & #291 Rebuild | Baseline | 230 | 0.65 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Hydraulic Road |  | Upgrade | EP | 0.65 |  | 11/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.372 | PJM SOUTH | Dooms Substation Terminal Equipment Upgrade for 230kV Linex #233 & #291 Rebuild | Baseline | 230 | 1.06 | 6/1/2027 | Dominion | 2022-W3-967 | Appendix A | Dominion:100 |  | VA | Dooms |  | Upgrade | EP | 1.06 |  | 11/30/2028 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.38 | PJM MA | Chalk Point-Cheltanham 500 kV (5073) - Replace relay at Chalk Point 500 kV. | Baseline | 500 | 0.34 | 6/1/2027 | PEPCO | 2022-W3-660 | Appendix A | BGE:39.75,Dominion:59.03,PEPCO:1.22 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Replace | UC | 0.34 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.39 | PJM MA | Red Lion - Hope Creek 500 kV - Replace four 500kV breakers and the stranded bus at Red Lion 500 kV substation | Baseline | 500 | 6 | 6/1/2027 | DPL | 2022-W3-344 | Appendix A | AEC:0.02,BGE:22.89,Dominion:48.61,DPL:9.46,JCPL:0.03,PEPCO:18.96,PSEG:0.03 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | DE |  |  | Replace | EP | 6 |  | 12/31/2030 |  | No | 12/5/2023 | 2/6/2024 | 0 |  |  |  | 2023-12-05
b3800.4 | PJM MA | New Otter Creek to Doubs 500 kV line (MD Border-PSEG Demarcation Point). Rebuild and expand existing ~1.6 miles of Otter Creek-Conastone 230 kV line to become a double-circuit 500 and 230 kV lines. | Baseline | 500 | 11.11 | 6/1/2027 | BGE | 2022-W3-374 | Appendix A | APS:13.16,BGE:0.79,Dominion:74.28,DPL:0.41,PECO:0.77,PEPCO:10.59 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Build | UC | 11.11 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.40 | PJM MA | Conastone-Brighton 500 kV (5011 circuit) - Replace terminal equipment limitations at Brighton 500 kV. | Baseline | 500 | 4.13 | 6/1/2027 | PEPCO | 2022-W3-660 | Appendix A | BGE:9.65,Dominion:63.04,DPL:0.02,PEPCO:27.29 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Replace | UC | 4.13 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.401 | PJM SOUTH | Replace Ashburn 230 kV breaker SC432 with a breaker rated 63 kA. | Baseline | 230 | 0.79 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Ashburn Substation |  | Replace | EP | 0.79 |  | 11/12/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.402 | PJM SOUTH | Replace Beaumeade 230 kV breaker 227T2152 with a breaker rated 80 kA. | Baseline | 230 | 2.31 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Beaumeade Substation |  | Replace | EP | 2.31 |  | 12/3/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.403 | PJM SOUTH | Replace BECO 230 kV breakers 215012 and H12T2150 with breakers rated 63kA. | Baseline | 230 | 4.21 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | BECO Substation |  | Replace | EP | 4.21 |  | 12/24/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.404 | PJM SOUTH | Replace Belmont 230 kV breaker 227T2180 with a breaker rated 80 kA. | Baseline | 230 | 2.24 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Belmont Substation |  | Replace | EP | 2.24 |  | 10/28/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.405 | PJM SOUTH | Replace Brambleton 230 kV breakers 20102, 20602, 204502, 209402, 201T2045, 206T2094 with breakers rated 80 kA. | Baseline | 230 | 9.38 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Brambleton Substation |  | Replace | EP | 9.38 |  | 1/8/2031 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.406 | PJM SOUTH | Replace Gainesville 230 kV breaker 216192 with a breaker rated 80 kA. | Baseline | 230 | 3.11 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Gainesville Substation |  | Replace | EP | 3.11 |  | 3/15/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.407 | PJM SOUTH | Replace Loudoun 230 kV breakers 204552, 217352 with breakers rated 80 kA. | Baseline | 230 | 5.57 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Loudoun Substation |  | Replace | EP | 5.57 |  | 10/5/2031 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.408 | PJM SOUTH | Replace Ox 230 kV breakers 22042, 24342, 24842, 220T2063, 243T2097, 248T2013, H342 with breakers rated 80 kA. | Baseline | 230 | 9.02 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Ox Substation |  | Replace | EP | 9.02 |  | 4/21/2031 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.409 | PJM SOUTH | Replace Paragon Park 230 kV breakers 208132, 215032, 2081T2206, 2150T2207 with breakers rated 80 kA. | Baseline | 230 | 4.96 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Paragon Park Substation |  | Replace | EP | 4.96 |  | 2/16/2031 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.41 | PJM MA | Conastone-Brighton 500 kV (5011 circuit) - Replace terminal equipment limitations at Conastone 500 kV. | Baseline | 500 | 7.16 | 6/1/2027 | BGE | 2022-W3-660 | Appendix A | BGE:9.65,Dominion:63.04,DPL:0.02,PEPCO:27.29 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Replace | UC | 7.16 |  | 12/31/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.410 | PJM SOUTH | Replace Reston 230 kV breaker 264T2015 with a breaker rated 63 kA. | Baseline | 230 | 0.79 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Reston Substation |  | Replace | EP | 0.79 |  | 10/13/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.411 | PJM SOUTH | Replace Stonewater 230 kV breakers 20662-1, 20662-2, 217862-1, 217862-2 with breakers rated 80 kA. | Baseline | 230 | 4.95 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Stonewater Substation |  | Replace | EP | 4.95 |  | 8/16/2030 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.412 | PJM SOUTH | Replace Waxpool 230 kV breakers 214922-5, 214922-6, 216622-5, 216622-6 with breakers rated 63 kA. | Baseline | 230 | 2.93 | 6/1/2027 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Waxpool Substation |  | Replace | EP | 2.93 |  | 12/16/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.413 | PJM WEST | Replace Double Toll Gate 138 kV breaker MDT 138 OCB with a breaker rated 40 kA. | Baseline | 138 | 3 | 6/1/2027 | APS | Additional Identified Upgrades | Appendix A | APS:100 |  | VA | Double Toll Gate Substation |  | Replace | EP | 3 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 10 |  |  |  | 2023-12-05
b3800.414 | PJM WEST | Replace Doubs 500 kV breaker DL-55 522LIN with a breaker rated 60 kA. | Baseline | 500 | 10.01 | 6/1/2027 | APS | Additional Identified Upgrades | Appendix A | APS:100 |  | MD | Doubs Substation |  | Replace | EP | 10.01 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.42 | PJM MA | Peach Bottom North bus upgrade - Replace 11 – Instances of strain bus conductor used for breaker drops or CT drops, 7 – 500 kV disconnect switches, 7 – Free Standing CTs, 1 – 500 kV breaker, 2 – Breaker relays or meters. | Baseline | 500 | 7.27 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | BGE:62.82,DPL:7.25,JCPL:0.09,Neptune:0.01,PECO:0.01,PEPCO:29.63,PSEG:0.18,RE:0.01 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Upgrade | EP | 2.7 |  | 12/1/2030 |  | No | 12/5/2023 | 12/5/2023 | 15 |  |  |  | 2023-12-05
b3800.43 | Not Specified | Construct 31.6 miles of 500 kV overhead AC line between the Conastone vicinity and the Doubs substations (APS zone portion). | Baseline | 500 | 183.8 | 6/1/2027 | PSEG | 2022-W3-637 | Appendix A | APS:13.16,BGE:0.79,Dominion:74.28,DPL:0.41,PECO:0.77,PEPCO:10.59 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Construct | EP | 176.8 |  | 6/1/2027 |  | No | 10/31/2023 | 12/5/2023 | 2 |  |  |  | 2023-10-31
b3800.44 | Not Specified | North Delta termination for the North Delta-High Ridge 500 line (PECO work). | Baseline | 500 | 4.76 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | Dominion:60.85,DPL:0.01,PECO:0.01,PEPCO:29.24,PSEG:9.48,RE:0.41 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Construct | EP | 3.4 |  | 12/1/2030 |  | No | 10/31/2023 | 12/5/2023 | 11 |  |  |  | 2023-10-31
b3800.45 | PJM MA | North Delta 500 kV termination for the Rock Springs 500 kV line (5034/5014 line) (PECO work). | Baseline | 500 | 1.45 | 6/1/2027 | PECO | 2022-W3-344, DENL | Appendix A | AEC:17.65,BGE:4.43,Dominion:9.87,DPL:22.25,JCPL:3.16,Neptune:0.36,PECO:2.98,PENELEC:0.44,PEPCO:3.80,PPL:5.99,PSEG:27.86,RE:1.21 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Construct | EP | 0.8 |  | 12/1/2030 |  | No | 10/31/2023 | 1/9/2024 | 12 |  |  |  | 2023-10-31
b3800.46 | Not Specified | North Delta 500 kV termination for the new Peach Bottom-North Delta 500 kV line (PECO work). | Baseline | 500 | 2.7 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | AEC:11.03,BGE:37.40,DPL:22.91,PEPCO:28.66 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Construct | EP | 2.6 |  | 12/1/2030 |  | No | 10/31/2023 | 12/5/2023 | 21 |  |  |  | 2023-10-31
b3800.47 | Not Specified | Build new Peach Bottom South-North Delta 500 kV line – cut in to Peach Bottom tie No. 1 and extending line to North Delta (~1.25 miles new ROW). | Baseline | 500 | 8.4 | 6/1/2027 | PECO | 2022-W3-344 | Appendix A | AEC:11.03,BGE:37.40,DPL:22.91,PEPCO:28.66 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Construct | EP | 5.5 |  | 12/1/2030 |  | No | 10/31/2023 | 12/5/2023 | 10 |  |  |  | 2023-10-31
b3800.48 | Not Specified | North Delta termination for the North Delta-High Ridge 500 line (Transource work). | Baseline | 500 | 4.38 | 6/1/2027 | Transource | 2022-W3-344 | Appendix A | Dominion:60.85,DPL:0.01,PECO:0.01,PEPCO:29.24,PSEG:9.48,RE:0.41 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Construct | EP | 0.96 |  | 12/15/2030 |  | No | 10/31/2023 | 12/5/2023 | 15 |  |  |  | 2023-10-31
b3800.49 | Not Specified | North Delta 500 kV termination for the Calpine generator (Calpine/Transource work). | Baseline | 500 | 4.05 | 6/1/2027 | Transource | 2022-W3-344 | Appendix A | PECO:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Construct | EP | 4.05 |  | 10/6/2027 |  | No | 10/31/2023 | 12/5/2023 | 15 |  |  |  | 2023-10-31
b3800.5 | PJM MA | Peach Bottom-TMI 500 kV – Replace terminal equipment at Peach Bottom (install new line terminal relays and communication infrastructure within Peach Bottom and along the 5007) | Baseline | 500 | 6.11 | 6/1/2027 | PECO | 2022-W3-374 | Appendix A | AEC:6.40,BGE:20.32,DPL:9.76,JCPL:17.57,Neptune:1.73,PECO:6.33,PEPCO:7.48,PSEG:29.15,RE:1.26 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Replace | EP | 2.5 |  | 6/1/2027 |  | No | 12/7/2023 | 5/1/2024 | 3 |  |  |  | 2023-12-07
b3800.50 | Not Specified | North Delta 500 kV termination for the Rock Springs 500 kV line (5034/5014 line) (Transource work). | Baseline | 500 | 3.55 | 6/1/2027 | Transource | 2022-W3-344 | Appendix A | AEC:17.65,BGE:4.43,Dominion:9.87,DPL:22.25,JCPL:3.16,Neptune:0.36,PECO:2.98,PENELEC:0.44,PEPCO:3.80,PPL:5.99,PSEG:27.86,RE:1.21 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Construct | EP | 0.49 |  | 1/23/2028 |  | No | 10/31/2023 | 12/5/2023 | 15 |  |  |  | 2023-10-31
b3800.51 | Not Specified | North Delta 500 kV termination for the new Peach Bottom-North Delta 500 kV line (Transource work). | Baseline | 500 | 3.68 | 6/1/2027 | Transource | 2022-W3-344 | Appendix A | AEC:11.03,BGE:37.40,DPL:22.91,PEPCO:28.66 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Construct | EP | 0.29 |  | 5/31/2028 |  | No | 10/31/2023 | 12/5/2023 | 15 |  |  |  | 2023-10-31
b3800.52 | PJM MA | Reconfigure Peach Bottom North and South yards to allow for termination of 500 kV lines from Peach Bottom to North Delta. North Delta 500 kV termination for the new Peach Bottom-North Delta 500 kV line. | Baseline | 500 | 14.25 | 6/1/2027 | PECO | 2022-W3-344/660 | Appendix A | AEC:11.03,BGE:37.40,DPL:22.90,PEPCO:28.67 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Peach Bottom |  | Modify | EP | 7.86 |  | 12/1/2030 |  | No | 10/31/2023 | 1/9/2024 | 8 |  |  |  | 2023-10-31
b3800.53 | PJM MA | Construct a double circuit 500 kV line from the existing TMI-Peach Bottom 500 kV right-of-way to the proposed Chanceford switchyard ~1.0 miles in length. | Baseline | 500 | 12.59 | 6/1/2027 | PPL | 2022-W3-374 | Appendix A | APS:13.37,Dominion:75.27,PEPCO:11.36 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Voltage |  |  | EP | 12.59 |  | 4/30/2027 |  | No | 5/1/2024 | 5/1/2024 | 0 |  |  |  | 2024-05-01
b3800.6 | PJM MA | Peach Bottom-TMI 500 kV - Replace terminal equipment at TMI. | Baseline | 500 | 0 | 6/1/2027 | ME | 2022-W3-374 | Appendix A | APS:7.41,BGE:15.50,Dominion:45.08,DPL:2.46,JCPL:0.80,ME:0.34,Neptune:0.09,PECO:10.72,PEPCO:15.72,PPL:0.43,PSEG:1.39,RE:0.06 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA |  |  | Replace | On Hold | 0 |  | 6/1/2027 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3800.7 | PJM MA | Construct 35.8 miles of 500 kV overhead AC line between the Conastone vicinity and the Doubs substations (BGE zone portion). | Baseline | 500 | 206.5 | 6/1/2027 | PSEG | 2022-W3-637 | Appendix A | APS:13.16,BGE:0.79,Dominion:74.28,DPL:0.41,PECO:0.77,PEPCO:10.59 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Construct | EP | 213.2 |  | 6/1/2027 |  | No | 10/31/2023 | 12/5/2023 | 2 |  |  |  | 2023-10-31
b3800.8 | PJM MA | Reconfigure Doubs 500 kV station and upgrade terminal equipment to terminate new line. | Baseline | 500 | 57.5 | 6/1/2027 | APS | 2022-W3-637 | Appendix A | APS:13.16,BGE:0.79,Dominion:74.28,DPL:0.41,PECO:0.77,PEPCO:10.59 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD |  |  | Rebuild | EP | 57.5 |  | 6/1/2027 |  | No | 12/6/2023 | 12/6/2023 | 0 |  |  |  | 2023-12-06
b3800.9 | PJM MA | Rebuild the existing Hunterstown-Carroll 115/138 kV Corridor as Double Circuit using 230 kV construction standards. New circuit will be operated at 230 kV. Existing circuit to remain at 115/138 kV. | Baseline | 230 | 0 | 6/1/2027 | APS | 2022-W3-837 |  |  |  | MD |  |  | Rebuild | EP | 0 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3851.1 | PJM WEST | Rebuild Allen –R.P. Mone 345kV line (18.6 miles). | Baseline | 345 | 49.88 | 6/1/2027 | AEP | 2023-W2-819 | Appendix A | AEP:0.71,Dayton:99.28,OVEC:0.01 |  | IN | Allen - R.P. Mone |  | Rebuild | EP | 49.88 |  | 6/1/2027 |  | Yes | 7/10/2024 | 7/10/2024 | 10 |  |  |  | 2024-07-10
b3851.2 | PJM WEST | Rebuild R.P. Mone – Maddox Creek 345kV line (9.4 miles). | Baseline | 345 | 39.03 | 6/1/2027 | AEP | 2023-W2-957 | Appendix A | AEP:78.50,Dayton:21.50 |  | OH | R.P. Mone - Maddox Creek |  | Rebuild | EP | 39.03 |  | 6/1/2027 |  | Yes | 7/9/2024 | 7/9/2024 | 10 |  |  |  | 2024-07-09
b3851.3 | PJM WEST | Replace breakers 'B1' and 'B' at Maddox Creek. | Baseline | 345 | 1.8 | 6/1/2027 | AEP | 2023-W2-334 | Appendix A | AEP:80.97,Dayton:19.03 |  | OH | Moddox Creek |  | Replace | EP | 1.8 |  | 6/1/2027 |  | Yes | 7/9/2024 | 7/9/2024 | 10 |  |  |  | 2024-07-09
b3851.4 | PJM WEST | Replace two 345kV breakers 'M' and 'M2' at East Lima Station. | Baseline | 345 | 1.76 | 6/1/2027 | AEP | 2023-W2-334 | Appendix A | AEP:80.97,Dayton:19.03 |  | OH | East Lima |  | Replace | EP | 1.76 |  | 6/1/2027 |  | Yes | 7/9/2024 | 7/9/2024 | 10 |  |  |  | 2024-07-09
b3852.1 | PJM WEST | Connect and energize a second 765/345 kV bank at Vassell station. | Baseline | 345 | 30.83 | 6/1/2027 | AEP | 2023-W2-117 | Appendix A | AEP:88.81,Dayton:6.22,DEOK:4.89,OVEC:0.08 |  | OH | Vassell |  | Install | UC | 30.83 |  | 7/15/2026 |  | Yes | 7/9/2024 | 7/9/2024 | 75 |  |  |  | 2024-07-09
b3852.2 | PJM WEST | Replace 765 kV breaker D at Maliszewski station. | Baseline | 345 | 2.9 | 6/1/2027 | AEP | 2023-W2-117 | Appendix A | AEP:68.04,ATSI:9.61,Dayton:1.92,DL:3.35,Dominion:17.06,EKPC:0.02 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | OH | Maliszewski |  | Replace | EP | 2.9 |  | 6/1/2027 |  | Yes | 7/9/2024 | 7/9/2024 | 0 |  |  |  | 2024-07-09
b3925.3 | PJM WEST | Rebuild the 6.5 miles of Avery-Hayes 138 kV Line with 795 kcmil 26/7 ACSS conductor | Baseline | 138 | 11.01 | 6/1/2027 | ATSI | 2024-W1-605 | Appendix A | ATSI:100 |  | OH | Avery-Hayes |  | Rebuild | EP | 11.01 |  | 6/1/2027 |  | No | 1/7/2025 | 1/7/2025 | 0 | 6/1/2027 |  |  | 2025-01-07
b3722 | PJM WEST | Rebuild the existing Darrah-Barnett 69 kV line, approximately 2.8 miles and replace a riser at Darrah station. | Baseline | 69 | 6.98 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | WV | Darrah - Barnett |  | Rebuild | EP | 6.98 |  | 3/29/2028 |  | No | 10/14/2022 | 10/14/2022 | 10 |  |  |  | 2022-10-14
b3725 | PJM WEST | Replace the 1600A bus disconnect switch at Goodings Grove on L11622 Elwood-Goodings Grove 345 kV. | Baseline | 345 | 0.5 | 12/1/2027 | ComEd |  | Appendix A | ComEd:100 |  | IL | Goodings Grove |  | Replace | On Hold | 0.5 |  | 12/1/2027 |  | No | 10/4/2022 | 10/4/2022 | 0 |  |  |  | 2022-10-04
b3728.1 | PJM MA | Upgrade two Breaker bushings on the 500 kV Line 5012 (Conastone-Peach Bottom) at Conastone substation. | Baseline | 500 | 2 | 12/1/2027 | BGE |  | Appendix A | APS:3.98,ATSI:0.03,BGE:20.98,DL:0.01,Dominion:32.06,DPL:0.02,JCPL:7.05,Neptune:0.81,PEPCO:17.70,PPL:2.72,PSEG:14.07,RE:0.57 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Conastone |  | Replace | Cancelled | 2 |  | 12/1/2027 |  | No | 10/4/2022 | 2/6/2024 | 0 |  |  |  | 2022-10-04
b3728.2 | PJM MA | Replace 4 meters and bus work inside Peach Bottom substation on the 500 kV Line 5012 (Conastone-Peach Bottom). | Baseline | 500 | 3.8 | 12/1/2027 | PECO |  | Appendix A | APS:3.94,ATSI:0.03,BGE:20.78,DL:0.01,Dominion:31.75,DPL:0.02,JCPL:6.99,Neptune:0.80,PECO:0.98,PEPCO:17.52,PPL:2.69,PSEG:13.93,RE:0.56 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Peach Bottom |  | Replace | Cancelled | 3.8 |  | 12/1/2027 |  | No | 10/4/2022 | 2/6/2024 | 0 |  |  |  | 2022-10-04
b3736.1 | PJM WEST | Establish 69kV bus and new 69 kV line CB at Dorton substation. | Baseline | 69 | 1.13 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Dorton |  | Construct | EP | 1.13 |  | 3/16/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.10 | PJM WEST | Henry Clay S.S Retirement: | Baseline | 46 | 0.3 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Henry Clay |  | Retire | EP | 0.3 |  | 9/1/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.11 | PJM WEST | Cedar Creek substation work | Baseline | 46 | 0.44 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Cedar Creek |  | Modify | EP | 0.44 |  | 11/15/2029 |  | No | 11/18/2022 | 11/18/2022 | 10 |  |  |  | 2022-11-18
b3736.12 | PJM WEST | Breaks substation retire 46kV equipment: | Baseline | 46 | 0.25 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Breaks |  | Retire | EP | 0.25 |  | 5/18/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.13 | PJM WEST | Retire Pike 29 SS and Rob Fork SS | Baseline | 46 | 0.42 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Pike 29, Rob Fork |  | Retire | EP | 0.42 |  | 11/15/2029 |  | No | 11/18/2022 | 11/18/2022 | 10 |  |  |  | 2022-11-18
b3736.14 | PJM WEST | Serve Pike 29 and Rob Fork customers from nearby 34kV Distribution sources. | Baseline | 46 | 0 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Pike 29 load, Rob Fork load |  | Provide | EP | 0 |  | 11/15/2029 |  | No | 11/18/2022 | 11/18/2022 | 10 |  |  |  | 2022-11-18
b3736.15 | PJM WEST | Poor Bottom substation install | Baseline | 69 | 0 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Poor Bottom |  | Install | EP | 0 |  | 3/16/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.16 | PJM WEST | Henry Clay 46kV substation retirement | Baseline | 46 | 0 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Henry Clay |  | Retire | EP | 0 |  | 3/16/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.17 | PJM WEST | New Draffin 69kV substation install | Baseline | 69 | 0 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | New Draffin |  | Install | EP | 0 |  | 3/23/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.18 | PJM WEST | Draffin 46kV substation retirement | Baseline | 46 | 0 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Draffin |  | Retire | EP | 0 |  | 9/1/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.2 | PJM WEST | At Breaks substation, reuse 72kV breaker A as the new 69kV line breaker. | Baseline | 69 | 0.71 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Breaks |  | Modify | EP | 0.71 |  | 5/18/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.3 | PJM WEST | Rebuild ~16.7 mi Dorton – Breaks 46kV line to 69kV | Baseline | 69 | 58.52 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Dorton - Breaks |  | Rebuild | EP | 58.52 |  | 3/16/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.4 | PJM WEST | Retire ~17.2 mi Cedar Creek – Elwood 46kV circuit. | Baseline | 46 | 11.15 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Cedar Creek - Elwood |  | Retire | EP | 11.15 |  | 8/1/2030 |  | No | 11/18/2022 | 11/18/2022 | 10 |  |  |  | 2022-11-18
b3736.5 | PJM WEST | Retire ~ 6.2 mi Henry Clay – Elwood 46kV line section. | Baseline | 46 | 4.3 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Henry Clay - Elwood |  | Retire | EP | 4.3 |  | 11/8/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.6 | PJM WEST | Retire Henry Clay 46 kV substation and replace with Poor Bottom 69 kV station. Install a new 0.7 mi double circuit extension to Poor Bottom 69kV. | Baseline | 69 | 3.42 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Henry clay, Poor Bottom |  | Replace | EP | 3.42 |  | 3/16/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.7 | PJM WEST | Retire Draffin substation and replace with a new substation. Install a new 0.25 mi double circuit extension to New Draffin substation. | Baseline | 69 | 2.01 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Draffin, New Darffin |  | Replace | EP | 2.01 |  | 9/1/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.8 | PJM WEST | Remote End work at Jenkins substation | Baseline | 69 | 0.03 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Jenkins |  | Modify | EP | 0.03 |  | 3/16/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3736.9 | PJM WEST | Provide Transition fiber to Dorton, Breaks, Poor Bottom, Jenkins and New Draffin substations | Baseline | 69 | 0.41 | 12/1/2027 | AEP |  | Appendix A | AEP:100 |  | KY | Dorton, Breaks, Poor bottom, Jenkins, New Draffin |  | Provide | EP | 0.41 |  | 3/16/2028 |  | No | 11/18/2022 | 11/18/2022 | 50 |  |  |  | 2022-11-18
b3737.22 | PJM MA | Construct the Larrabee Collector station AC switchyard, composed of a 230 kV 3 x breaker and a half substation with a nominal current rating of 4000 A and four single phase 500/230 kV 480 MVA autotransformers to step up the voltage for connection to the Smithburg substation. Procure land adjacent to the AC switchyard, and prepare the site for construction of future AC to DC converters for future interconnection of DC circuits from offshore wind generation. Land should be suitable to accommodate installation of four individual converters to accommodate circuits with equivalent rating of 1400 MVA at 400 kV. Additional scope includes three sets of AC collector lines from the LCS to the offshore wind converter station area. | Baseline | 500/230 | 220.5 | 12/31/2027 | MAOD | 2021_SAA-550, DENL | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee Collector Station |  | Construct | EP | 208.9 |  | 12/31/2027 |  | No | 11/5/2022 | 4/3/2024 | 14 |  |  |  | 2022-11-05
b3737.30 | PJM MA | Add third Smithburg 500/230 kV transformer. | Baseline | 500/230 | 13.4 | 12/31/2027 | JCPL | 2021_SAA-17 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Smithburg |  | Install | EP | 13.4 |  | 12/31/2027 |  | No | 11/4/2022 | 11/4/2022 | 10 |  |  |  | 2022-11-04
b3737.32 | PJM MA | Rebuild Larrabee-Smithburg No. 1 230 kV. | Baseline | 230 | 44.77 | 12/31/2027 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee-Smithburg |  | Rebuild | EP | 44.77 |  | 12/31/2027 |  | No | 11/4/2022 | 11/4/2022 | 30 |  |  |  | 2022-11-04
b3737.38 | PJM MA | Linden subproject: Install a new 345/230 kV transformer at the Linden 345 kV Switching station, and relocate the Linden-Tosco 230 kV (B-2254) line from the Linden 230 kV to the existing 345/230 kV transformer at Linden 345 kV. | Baseline | 345/230 | 37.2 | 12/31/2027 | PSEG | 2021_SAA-180 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Linden |  | Install | UC | 35.3 |  | 12/31/2027 |  | No | 11/4/2022 | 5/9/2023 | 49 |  |  |  | 2022-11-04
b3737.39 | PJM MA | Bergen subproject: Upgrade the Bergen 138 kV ring bus by installing a 80 kA breaker along with the foundation, piles, and relays to the existing ring bus, install breaker isolation switches on existing foundations and modify and extend bus work. | Baseline | 138 | 6 | 12/31/2027 | PSEG | 2021_SAA-180 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Bergen |  | Install | EP | 5.53 |  | 12/31/2027 |  | No | 11/4/2022 | 11/4/2022 | 47 |  |  |  | 2022-11-04
b3737.53 | PJM MA | Remove the existing E83 line 115 kV (not in-service) to accommodate the new 500 kV/230 kV lines (~ 7.7 miles). | Baseline | 115 | 8.47 | 12/31/2027 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee-Smithburg |  | Remove | EP | 8.47 |  | 12/31/2027 |  | No | 5/9/2023 | 5/9/2023 | 20 |  |  |  | 2023-05-09
b3737.54 | PJM MA | Remove the existing H2008 Larrabee-Smithburg No. 2 230 kV to accommodate the new 500 kV/230 kV lines. | Baseline | 230 | 8.47 | 12/31/2027 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee-Smithburg |  | Remove | EP | 8.47 |  | 12/31/2027 |  | No | 5/9/2023 | 5/9/2023 | 20 |  |  |  | 2023-05-09
b3737.6 | PJM MA | Larrabee Collector station-Smithburg No. 1 500 kV line (new asset). New 500 kV line will be built double circuit to accommodate a 500 kV line and a 230 kV line. | Baseline | 500 | 150.35 | 12/31/2027 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee Collector Station-Smithburg |  | Install | EP | 150.35 |  | 12/31/2027 |  | No | 11/4/2022 | 11/4/2022 | 20 |  |  |  | 2022-11-04
b3737.7 | PJM MA | Rebuild G1021 Atlantic-Smithburg 230 kV line between the Larrabee and Smithburg substations as a double circuit 500 kV/230 kV line. | Baseline | 230 | 62.85 | 12/31/2027 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Atlantic-Smithburg |  | Rebuild | EP | 62.85 |  | 12/31/2027 |  | No | 11/4/2022 | 11/4/2022 | 20 |  |  |  | 2022-11-04
b3737.8 | PJM MA | Smithburg substation 500 kV expansion to 4-breaker ring. | Baseline | 500 | 68.25 | 12/31/2027 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Smithburg |  | Upgrade | EP | 68.25 |  | 12/31/2027 |  | No | 11/4/2022 | 11/4/2022 | 10 |  |  |  | 2022-11-04
b3737.24 | PJM MA | Upgrade Cardiff-Lewis 138 kV by replacing 1590 kcmil strand bus inside Lewis substation. | Baseline | 138 | 0.1 | 4/30/2028 | AEC | 2021_SAA-127 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Cardiff-Lewis |  | Upgrade | EP | 0.1 |  | 4/30/2028 |  | No | 11/4/2022 | 11/4/2022 | 0 |  |  |  | 2022-11-04
b3737.25 | PJM MA | Upgrade Lewis No. 2-Lewis No. 1 138 kV by replacing its bus tie with 2000 A circuit breaker. | Baseline | 138 | 0.5 | 4/30/2028 | AEC | 2021_SAA-127 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Lewis No. 2-Lewis No. 1 |  | Replace | EP | 0.5 |  | 4/30/2028 |  | No | 11/4/2022 | 11/4/2022 | 0 |  |  |  | 2022-11-04
b3845.1 | PJM MA | Add a second breaker next to Nottingham 895 circuit breaker to eliminate stuck breaker contingency. | Baseline | 230 | 1.28 | 5/31/2028 | PECO |  | Appendix A | PECO:100 |  |  | Nottingham--(39.761,-76.0321)-{3C903188-014A-433C-9F7C-103F7D2849E0} |  | Install | EP | 1.28 |  | 12/31/2027 |  | No | 11/16/2023 | 11/16/2023 | 5 |  |  |  | 2023-11-16
b3784.1 | PJM WEST | Replace 138kV breaker 5 at Canal St station with a new 3000A 63kA breaker | Baseline | 138 | 0.5 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | OH | Canal Street--(39.9539,-83.0037)-new |  | Replace | EP | 0.5 |  | 2/24/2028 |  | Yes | 11/17/2023 | 11/17/2023 | 10 |  |  |  | 2023-11-17
b3785.1 | PJM WEST | Replace existing 3000A wave trap at Mountaineer 765 kV, on the Belmont-Mountaineer 765 kV line, with a new 5000 A wave trap. | Baseline | 765 | 0.46 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | WV | Mountaineer--(38.9761,-81.9418)-{025BB5E3-5A02-446C-9CBB-CBE3B1E1D244} |  | Replace | EP | 0.46 |  | 10/7/2026 |  | No | 12/5/2023 | 12/5/2023 | 25 |  |  |  | 2023-12-05
b3786.1 | PJM WEST | Rebuild ~4.5 miles of 69 kV line between Abert and Reusens substations. Update line settings at Reusens and Skimmer. | Baseline | 34.5 | 14.4 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | VA | Abert--(37.5088,-79.2215)-{A18A1616-B91E-4646-A88B-0A5E63CC7550}, Reusens--(37.4623,-79.1893)-{9CD09531-8BD0-4595-83B6-6E2B6667E15E} |  | Rebuild | EP | 14.4 |  | 11/16/2029 |  | No | 11/17/2023 | 11/17/2023 | 10 |  |  |  | 2023-11-17
b3788.1 | PJM WEST | Replace AEP-owned station takeoff riser and breaker BB risers at OVEC-owned Kyger Creek station. | Baseline | 345 | 0.41 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | OH | Kyger Creek--(38.9122,-82.131)-{3C9F378E-8BA4-4FA8-8960-B7E684E56A48} |  | Replace | EP | 0.41 |  | 11/18/2027 |  | No | 12/5/2023 | 12/5/2023 | 10 |  |  |  | 2023-12-05
b3788.2 | PJM WEST | Replace OVEC-owned breaker AA risers, bus work, and breaker AA disconnect switches at OVEC-owned Kyger Creek station. | Baseline | 345 | 0.75 | 6/1/2028 | OVEC |  | Appendix A | OVEC:100 |  | WV | Kyger Creek--Sporn |  | Replace | EP | 0.75 |  | 6/1/2028 |  | No | 12/5/2023 | 12/5/2023 | 0 |  |  |  | 2023-12-05
b3789.0 | PJM WEST | A 69 kV, 60 MVAR shunt reactor will be installed at the Salt Springs substation. The reactor terminal will be connected to the existing 69 kV bus, and an independent-pole operation, 1200A circuit breaker will be installed for reactor switching. | Baseline | 69 | 5.45 | 6/1/2028 | ATSI |  | Appendix A | ATSI:100 |  | OH | Salt Springs |  | Replace | EP | 5.45 |  | 6/1/2028 |  | No | 11/17/2023 | 11/17/2023 | 0 |  |  |  | 2023-11-17
b3790.0 | PJM WEST | Replace the overdutied Olive 345 kV circuit breaker "D" with a 5000A 63 kA circuit breaker. Reuse existing cables and a splice box to support the circuit breaker install. | Baseline | 345 | 1.08 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | OH | Olive Substation |  | Replace | EP | 1.08 |  | 11/19/2026 |  | No | 12/5/2023 | 12/5/2023 | 50 |  |  |  | 2023-12-05
b3791.0 | PJM MA | Rebuild the North Meshoppen-Mehoopany No. 1 115 kV line with 795 ACSR 26/7 STR conductor. Upgrade terminal equipment to exceed transmission line ratings. | Baseline | 115 | 17.4 | 6/1/2028 | PENELEC | 2023-W1-746 | Appendix A | PENELEC:100 |  |  | Meshoppen - Mehoopany |  | Rebuild | EP | 17.4 |  | 6/11/2027 |  | No | 10/19/2023 | 11/16/2023 | 3 |  |  |  | 2023-10-19
b3792.0 | PJM MA | Rebuild the North Meshoppen-Mehoopany No. 2 115 kV line using 795 ACSR 26/7 STR conductor, and upgrade terminal equipment to exceed the transmission line rating. | Baseline | 115 | 17.7 | 6/1/2028 | PENELEC | 2023-W1-158 | Appendix A | PENELEC:100 |  |  | Meshoppen - Mehoopany |  | Rebuild | EP | 17.7 |  | 12/17/2027 |  | No | 10/19/2023 | 11/16/2023 | 3 |  |  |  | 2023-10-19
b3793.1 | PJM MA | Reconductor Silver Run-Cedar Creek 230 kV line. Reconductor 8.8 miles of 230 kV circuit with 1594-T11/ACCR “Lapwing” conductor and replace all insulators with high-temp. hardware. | Baseline | 230 | 7.68 | 6/1/2028 | DPL | 2023-W1-573 | Appendix A | DPL:100 |  | MD | Silver Run - Cedar Creek |  | Reconductor | EP | 7.68 |  | 6/1/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3793.2 | PJM MA | Replace three (3) standalone CTs, disconnect switch, stranded bus and rigid bus to achieve higher rating at Cedar Creek. | Baseline | 230 | 0.45 | 6/1/2028 | DPL | 2023-W1-573 | Appendix A | DPL:100 |  | MD | Cedar Creek |  | Replace | EP | 0.45 |  | 6/1/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3793.3 | PJM MA | Replace three (3) 1-1590 ACSR jumpers and one (1) air disconnect switch at Silver Run. | Baseline | 230 | 0.58 | 6/1/2028 | DPL | 2023-W1-573 | Appendix A | DPL:100 |  | MD | Silver Run |  | Replace | Cancelled | 0.58 |  | 6/1/2028 |  | No | 10/31/2023 | 12/5/2023 | 0 |  |  |  | 2023-10-31
b3793.4 | PJM MA | Replace three (3) 1-1590 ACSR jumpers and one (1) air disconnect switch at Silver Run 230 kV substation. | Baseline | 230 | 0.58 | 6/1/2028 | DPL | 2023-W1-573 |  |  |  | MD | Silver Run |  | Replace | PL | 0.58 |  |  |  | No | 5/6/2025 | 5/6/2025 | 0 |  |  |  | 2025-05-06
b3794.1 | PJM MA | Replace existing Waldwick 230 kV 50 MVAR fixed shunt reactor with a 230 kV 150 MVAR variable shunt reactor. | Baseline | 230 | 32.8 | 6/1/2028 | PSEG | 2023-W1-107 | Appendix A | PSEG:100 |  | NJ | Waldwick |  | Replace | UC | 13.6 |  | 6/1/2028 |  | No | 10/31/2023 | 12/5/2023 | 29 |  |  |  | 2023-10-31
b3794.2 | PJM MA | Replace existing Waldwick 345 kV 100 MVAR fixed shunt reactor with a 345 kV 150 MVAR variable shunt reactor. | Baseline | 345 | 0 | 6/1/2028 | PSEG | 2023-W1-107 | Appendix A | PSEG:100 |  | NJ | Waldwick |  | Replace | UC | 16 |  | 6/1/2028 |  | No | 10/31/2023 | 12/5/2023 | 29 |  |  |  | 2023-10-31
b3796.0 | PJM WEST | Replace the Belmont 765/500 kV transformer No. 5 with a new transformer bank consisting of three single-phase transformers and an additional single phase spare transformer. The project will also replace 500 kV disconnect switches at the Belmont substation. | Baseline | 765/500 | 42.05 | 6/1/2028 | APS | 2023-W1-903 | Appendix A | AEP:0.28,APS:0.15,Dayton:0.10,DEOK:0.18,DL:6.57,Dominion:92.68,EKPC:0.04 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | WV | Belmont |  | Replace | EP | 42.05 |  | 6/1/2028 |  | No | 1/9/2024 | 1/9/2024 | 0 |  |  |  | 2024-01-09
b3800.373 | PJM SOUTH | Wreck and rebuild approximately 7.14 miles of 230kV line #256 from St. Johns to structure 256/108 to achieve a summer rating of 1573 MVA. Line switch 25666 at St. Johns to be upgraded to 4000A. | Baseline | 230 | 21.69 | 6/1/2028 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | St. Johns |  | Rebuild | EP | 21.75 |  | 6/15/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3800.374 | PJM SOUTH | Reconductor approximately 5.30 miles of 230kV line #256 from Ladysmith CT to structure 256/107 to achieve a summer rating of 1573 MVA. Terminal equipment at remote end substations will be upgraded to 4000A. | Baseline | 230 | 10 | 6/1/2028 | Dominion | Additional Identified Upgrades | Appendix A | Dominion:100 |  | VA | Ladysmith CT |  | Reconductor | EP | 16.14 |  | 6/15/2027 |  | No | 10/31/2023 | 12/5/2023 | 20 |  |  |  | 2023-10-31
b3810.0 | PJM WEST | Add three 345 kV circuit breakers to Cherry Valley substation. | Baseline | 345 | 7.75 | 6/1/2028 | ComEd | 2023-W1-771, single zone allocation; DENL & CRL | Appendix A | ComEd:100 |  | IL | Cherry Valley |  | Install | EP | 7.75 |  | 6/1/2028 |  | No | 1/9/2024 | 1/9/2024 | 0 |  |  |  | 2024-01-09
b3812.1 | PJM WEST | Reconductor 345 kV lines 11620 and 11622 from Elwood to Goodings Grove. | Baseline | 345 | 56.18 | 6/1/2028 | ComEd | 2023-W1-35 | Appendix A | ComEd:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | IL | Elwood-Goodings Grove |  | Reconductor | On Hold | 56.18 |  | 6/1/2028 |  | No | 3/5/2024 | 3/5/2024 | 0 |  |  |  | 2024-03-05
b3812.2 | PJM WEST | Upgrade Goodings Grove 345 kV circuit breakers, disconnects and associated equipment. | Baseline | 345 | 5.16 | 6/1/2028 | ComEd | 2023-W1-35 | Appendix A | ComEd:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | IL | Goodings Grove |  | Upgrade | On Hold | 5.16 |  | 6/1/2028 |  | No | 3/5/2024 | 3/5/2024 | 0 |  |  |  | 2024-03-05
b3812.3 | PJM WEST | Upgrade station conductor at Elwood 345 kV. | Baseline | 345 | 0.5 | 6/1/2028 | ComEd | 2023-W1-35 | Appendix A | ComEd:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | IL | Elwood |  | Upgrade | On Hold | 0.5 |  | 6/1/2028 |  | No | 3/5/2024 | 3/5/2024 | 0 |  |  |  | 2024-03-05
b3812.4 | PJM WEST | Adjust reclosing cycle on for Goodings Grove 345 kV circuit breaker “116 9806” to eliminate the reclosing derating. | Baseline | 345 | 0 | 6/1/2028 | ComEd | 2023-W1-35 | Appendix A | ComEd:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | IL | Goodings Grove |  | Modify | On Hold | 0 |  | 6/1/2028 |  | No | 3/5/2024 | 3/5/2024 | 0 |  |  |  | 2024-03-05
b3836.1 | PJM WEST | Rebuild approximately 1.7 miles of line on the Chemical-Washington Street 46 kV circuit. | Baseline | 34.5 | 7.6 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | WV | Chemical--(38.3929,-81.641)-{7B0F11BA-505D-4C5A-905B-1DDA59CC21D5}, Washington Street--(38.3550,-81.6350)-new |  | Rebuild | EP | 7.6 |  | 6/1/2028 |  | No | 11/17/2023 | 11/17/2023 | 10 |  |  |  | 2023-11-17
b3837.1 | PJM WEST | Replace existing 34.5 kV, 25 kA circuit breaker B at West Huntington station with new 69 kV, 40 kA circuit breaker. | Baseline | 138 | 0.36 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | WV | West Huntington--(38.4054,-82.4797)-{14E583CB-4F1F-4DB2-8EF0-121BE93384CD} |  | Replace | EP | 0.36 |  | 11/6/2028 |  | No | 11/17/2023 | 11/17/2023 | 10 |  |  |  | 2023-11-17
b3838.1 | PJM WEST | Replace breaker A and B at Timken station with 40 kA breakers. | Baseline | 138 | 1.2 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | OH | Timken--(40.7724,-81.3966)-{7348D055-9FCF-4F5C-A633-D2FE252A40F9} |  | Replace | EP | 1.2 |  | 6/1/2028 |  | No | 11/17/2023 | 11/17/2023 | 10 |  |  |  | 2023-11-17
b3839.1 | PJM WEST | Replace 69 kV breaker C at Haviland station with a new 3000A 40 kA breaker. | Baseline | 69 | 0.4 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | OH | Haviland--(41.0164,-84.5935)-{EBB11588-294F-443B-9AF9-15B088F44C16} |  | Replace | EP | 0.4 |  | 6/1/2028 |  | No | 11/17/2023 | 11/17/2023 | 0 |  |  |  | 2023-11-17
b3840.1 | PJM WEST | Replace structures 382-66 and 382-63 on Darrah-East Huntington 34.5 kV line to bypass 24th Street station. Retire structures 1 through 5 on 24th Street 34.5 kV extension. Retire 24th Street station. Remove conductors from BASF tap to BASF. | Baseline | 138 | 1.8 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | WV | East Huntington--(38.411,-82.4636)-{7D662475-C100-4F59-9DBB-7B13C56A4FE6}, 23rd Street--(38.4275,-82.4193)-new, BASF--(38.4241,-82.4151)-new, 24th Street--(38.4263,-82.4158)-new, 26th Street--(38.4237,-82.4083)-new |  | Reconfigure | IS | 1.8 |  | 6/1/2028 | 3/22/2024 | No | 11/17/2023 | 11/17/2023 | 100 |  |  |  | 2023-11-17
b3843.1 | PJM WEST | Rebuild the underground portion of the Ohio University-West Clark 69 kV line, approximately 0.65 miles. | Baseline | 69 | 4.6 | 6/1/2028 | AEP |  | Appendix A | AEP:100 |  | OH | West Clark--(39.3366,-82.1159)-new, Ohio University--(39.3275,-82.1091)-new |  | Rebuild | EP | 4.6 |  | 6/1/2028 |  | No | 11/17/2023 | 11/17/2023 | 10 |  |  |  | 2023-11-17
b3846.1 | PJM MA | Rebuild 6.25 miles of 69 kV circuit 6708 (Vienna-Mardela) with new single pole steel structures and with 954.0 45/7 "Rail" conductor. This new rebuild will be from the dead-end structure on the east side of the Nanticoke River to the Mardela tap. | Baseline | 230 | 18.63 | 6/1/2028 | DPL |  | Appendix A | DPL:100 |  |  | Mardela--(38.4498,-75.7436)-{F3304B78-4D4B-4925-9A01-2DEE12DBCE9A}, Vienna--(38.4872,-75.8207)-{DCC13F75-DBA2-4D9D-ADBA-76852F0AAAA4} |  | Rebuild | EP | 18.63 |  | 6/1/2028 |  | No | 11/16/2023 | 11/16/2023 | 0 |  |  |  | 2023-11-16
b3846.2 | PJM MA | Upgrade disconnect switch at Vienna to increase ratings of existing Vienna-Mardela transmission facility. | Baseline | 230 | 1 | 6/1/2028 | DPL |  | Appendix A | DPL:100 |  |  | Vienna--(38.4872,-75.8207)-{DCC13F75-DBA2-4D9D-ADBA-76852F0AAAA4} |  | Upgrade | EP | 1 |  | 12/31/2026 |  | No | 11/16/2023 | 11/16/2023 | 0 |  |  |  | 2023-11-16
b3846.3 | PJM MA | Upgrade three disconnect switches at Mardela to increase ratings of existing Vienna-Mardela transmission facility. | Baseline | 230 | 1.75 | 6/1/2028 | DPL |  | Appendix A | DPL:100 |  |  | Mardela--(38.4498,-75.7436)-{F3304B78-4D4B-4925-9A01-2DEE12DBCE9A} |  | Upgrade | EP | 1.75 |  | 6/1/2028 |  | No | 11/16/2023 | 11/16/2023 | 0 |  |  |  | 2023-11-16
b3848.1 | PJM MA | Open East Rutherford 69kV Tie Breaker [26K] | Baseline | 69 | 0 | 6/1/2028 | PSEG | 2023-W1-Short Circuit | Appendix A | PSEG:100 |  | NJ | East Rutherford 69kV |  | Reconfigure | EP | 0 |  | 6/1/2028 |  | Yes | 6/13/2024 | 6/13/2024 | 0 |  |  |  | 2024-06-13
b3848.2 | PJM MA | Move line U-775 [ East Rutherford to Hasbrouck Heights] currently on section 2 to section 7 of the ring bus. | Baseline | 69 | 2.14 | 6/1/2028 | PSEG | 2023-W1-Short Circuit | Appendix A | PSEG:100 |  | NJ | East Rutherford 69kV,Hasbrouck Heights |  | Re-route | EP | 2.14 |  | 6/1/2028 |  | Yes | 6/13/2024 | 6/13/2024 | 0 |  |  |  | 2024-06-13
b3849.1 | PJM MA | Perform all necessary engineering design and evaluation to increase Fairlawn 69kV GIS from 50kA to 55kA. | Baseline | 69 | 1.49 | 6/1/2028 | PSEG | 2023-W1-Short Circuit | Appendix A | PSEG:100 |  | NJ | Fairlawn |  | Modify | IS | 1.49 |  | 6/1/2028 | 5/26/2025 | Yes | 6/13/2024 | 6/13/2024 | 100 |  |  |  | 2024-06-13
b3850.1 | PJM SOUTH | Rebuild approximately 13.51 miles of 500 kV line #588 from structure 588/184 inside Yadkin substation to structure 588/254 outside of Fentress substation. | Baseline | 500 | 78.6 | 6/1/2028 | Dominion | 2023-W2-367 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Fentress, Yadkin |  | Rebuild | EP | 78.6 |  | 12/31/2026 |  | Yes | 6/4/2024 | 6/4/2024 | 40 |  |  |  | 2024-06-04
b3850.2 | PJM SOUTH | Line #588 terminal equipment at Yadkin substation will be upgraded to a rating of 5000A. Since the new 500kV line will be using fiber, the wave trap will be removed and the line protection scheme will be updated. | Baseline | 500 | 0.96 | 6/1/2028 | Dominion | 2023-W2-367 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Yadkin |  | Upgrade | EP | 0.96 |  | 12/31/2026 |  | Yes | 6/4/2024 | 6/4/2024 | 25 |  |  |  | 2024-06-04
b3850.3 | PJM SOUTH | At Fentress substation, since the new 500kV line will be using fiber, the wave trap will be removed and the line protection scheme will be updated. | Baseline | 500 | 0.14 | 6/1/2028 | Dominion | 2023-W2-367 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Fentress |  | Upgrade | EP | 0.14 |  | 12/31/2026 |  | Yes | 6/4/2024 | 6/4/2024 | 40 |  |  |  | 2024-06-04
b3855.1 | PJM MA | Build 4 miles new 230 kV XLPE circuit using (345 kV rated 5000 kcmil cable) from Jackson Road 230 kV station to Cedar Grove 230 kV station. | Baseline | 230 | 77.15 | 6/1/2028 | PSEG | 2023-W2-627 | Appendix A | PSEG:95.85,RE:4.15 |  | NJ | Jackson Road |  | Build | EP | 77.15 |  | 6/1/2028 |  | No | 7/9/2024 | 7/9/2024 | 19 |  |  |  | 2024-07-09
b3855.2 | PJM MA | Expand a new 230 kV bay at the existing Cedar Grove station with one line position by adding two 230 kV circuit breakers and associated disconnect switches. | Baseline | 230 | 6.61 | 6/1/2028 | PSEG | 2023-W2-627 | Appendix A | PSEG:95.85,RE:4.15 |  | NJ | Cedar Grove |  | Expand | EP | 6.61 |  | 6/1/2028 |  | No | 7/9/2024 | 7/9/2024 | 19 |  |  |  | 2024-07-09
b3855.3 | PJM MA | Replace the existing HPFF termination structure with a new XLPE termination structure to connect to spare GIS bay position at Jackson 230 kV. | Baseline | 230 | 0.82 | 6/1/2028 | PSEG | 2023-W2-627 | Appendix A | PSEG:95.85,RE:4.15 |  | NJ | Jackson Road |  | Replace | EP | 0.82 |  | 6/1/2028 |  | No | 7/9/2024 | 7/9/2024 | 19 |  |  |  | 2024-07-09
b3858.1 | PJM MA | Rebuild the Windsor Substation 115 kV yard to convert from a straight bus configuration into a six-breaker ring bus configuration. Install two (2) 21.62 MVAR, 115 kV capacitor banks. | Baseline | 115 | 12.36 | 6/1/2028 | ME |  | Appendix A | ME:100 |  | PA | Windsor |  | Rebuild | EP | 12.36 |  | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3858.2 | PJM MA | Rebuild the Yorkana Substation 115 kV yard converting from a straight bus configuration to a (9) breaker, breaker-and-a-half configuration. | Baseline | 115 | 20.8 | 6/1/2028 | ME |  | Appendix A | ME:100 |  | PA | Yorkana |  | Rebuild | EP | 20.8 |  | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3870.1 | PJM WEST | At Federal Street Substation: - Install (3) 138 kV CCVTs on the 138 kV bus. - Remove the Transformer 1 CO-6 138 kV Phase relay Overcurrent Relays. - Install (1) SEL-421 relay on the high side of Transformer 1. - Install foundations, conduit, and grounding for new CCVTs. - Install cables between CCVTs and relay. | Baseline | 138 | 0.69 | 6/1/2028 | APS |  | Appendix A | APS:100 |  | PA | Federal St. |  | Replace | EP | 0.69 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3907.2 | PJM MA | Richmond to Waneeta 230kV Line: Rebuild entire 0.95 miles of existing UGT, and rebuild entire 2.23 miles of existing OHT | Baseline | 230 | 29.4 | 6/1/2028 | PECO | 2024-W1-12 | Appendix A | AEC:9.99,JCPL:8.34,PECO:55.62,PSEG:24.31,RE:0.94,Neptune:0.80 |  | PA | Richmond |  | Rebuild | EP | 29.4 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 3 |  |  |  | 2024-12-03
b3907.3 | PJM MA | Reconductor 2.12 miles of North Philadelphia to Waneeta 230 kV line | Baseline | 230 | 7.33 | 6/1/2028 | PECO | 2024-W1-12 | Appendix A | AEC:10.75,JCPL:14.26,PECO:38.58,PSEG:33.62,RE:1.31,Neptune:1.48 |  | PA | Waneeta |  | Rebuild | EP | 7.33 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 3 |  |  |  | 2024-12-03
b3909.1 | PJM MA | Juniata 500 kV yard expansion/reconfiguration to include one new bay and eliminate the line fault stuck breaker | Baseline | 500 | 23.73 | 6/1/2028 | PPL | 2024-W1-935 | Appendix A | PPL:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | PA | Juniata |  | Expand | PL | 22.2 |  | 6/1/2028 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3787.1 | PJM WEST | Install a CCVT on three-phase stand and remove the single phase existing CCVT on the 69 kV Coalton to Bellefonte line exit. The existing CCVT is mounted to lattice on a single-phase CCVT stand, which will be replaced with the three-phase CCVT stand. The line riser between line disconnect and line takeoff is being replaced. This remote end work changes the MLSE of the line section between Coalton-Princess 69 kV line section. | Baseline | 69 | 0 | 12/1/2028 | AEP |  | Appendix A | AEP:100 |  | KY | Coalton--(38.3634,-82.7586)-{274FA529-5A8D-4542-9893-5AD1E756E319} |  | Replace | EP | 0 |  | 12/1/2028 |  | No | 11/17/2023 | 11/17/2023 | 0 |  |  |  | 2023-11-17
b3811.1 | PJM WEST | Expand Haumesser Road 138 kV substation as a four-circuit breaker ring bus. | Baseline | 138 | 15.91 | 12/1/2028 | ComEd | 2023-W1-972 | Appendix A | ComEd:100 |  | IL | Haumesser Road |  | Upgrade | EP | 15.91 |  | 12/1/2028 |  | No | 2/6/2024 | 2/6/2024 | 0 |  |  |  | 2024-02-06
b3811.2 | PJM WEST | Add one 138 kV circuit breaker at H-452 to complete a three-circuit breaker ring bus. | Baseline | 138 | 1.98 | 12/1/2028 | ComEd | 2023-W1-972 | Appendix A | ComEd:100 |  | IL | H-452 (Enridge-DeKalb) |  | Install | EP | 1.98 |  | 12/1/2028 |  | No | 2/6/2024 | 2/6/2024 | 0 |  |  |  | 2024-02-06
b3811.3 | PJM WEST | Rebuild 3 miles of 138 kV line 11323 from Haumesser Road to the H-452 tap with double circuit towers. Cut the H-452 tap over to the second circuit from Haumesser Road. Both circuits to use twisted pair 556 ACSR Parakeet conductor. | Baseline | 138 | 10.22 | 12/1/2028 | ComEd | 2023-W1-972 | Appendix A | ComEd:100 |  | IL | Haumesser Road-H-452 (Enridge-DeKalb) Tap |  | Rebuild | EP | 10.22 |  | 12/1/2028 |  | No | 2/6/2024 | 2/6/2024 | 0 |  |  |  | 2024-02-06
b3737.29 | PJM MA | Convert the six-wired East Windsor-Smithburg E2005 230 kV line (9.0 mi.) to two circuits. One a 500 kV line and the other a 230 kV line. | Baseline | 500/230 | 206.48 | 12/31/2028 | JCPL | 2021_SAA-17 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | East Windsor-Smithburg |  | Modify | EP | 206.48 |  | 12/31/2028 |  | No | 11/4/2022 | 11/4/2022 | 15 |  |  |  | 2022-11-04
b3900.1 | PJM WEST | Replace 300 copper conductor with 1113 kcmil ACSR conductor on Kewanee 138 kV Bus No. 1. | Baseline | 138 | 0.2 | 4/1/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | Kewanee |  | Replace | EP | 0.2 |  | 4/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3872.1 | PJM WEST | Adjust the tertiary tap on the Hartford 138/69/34.5 kV transformer 1 and on Hartford 138/69/12 kV transformer 4 to eliminate the high voltage issues and avoid circulating current. | Baseline | 138 | 0.1 | 4/15/2029 | AEP |  | Appendix A | AEP:100 |  | MI | Hartford |  | Modify | EP | 0.1 |  | 4/15/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3904.1 | PJM WEST | Rebuild and reconductor 7.7 miles of 69kV line with our standard 1351 AAC conductor from Rockford substation to the POI. | Baseline | 69 | 25 | 4/15/2029 | Dayton |  | Appendix A | Dayton:100 |  | OH | Rockford |  | Rebuild | PL | 25 |  | 6/1/2029 |  | No | 1/17/2025 | 1/17/2025 | 0 |  |  |  | 2025-01-17
b3914.1 | PJM WEST | Change No-load Tap of 2 Autotransformers at Fisk from 338.25 kV to 346.5 kV. | Baseline | 345,138 | 0.03 | 4/15/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | Fisk |  | Modify | EP | 0.03 |  | 4/15/2029 |  | No | 12/13/2024 | 12/13/2024 | 0 |  |  |  | 2024-12-13
b3914.2 | PJM WEST | Change No-load Tap of 4 Autotransformers at Crawford from 338.25 kV to 3456.5 kV. | Baseline | 138,345 | 0.07 | 4/15/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | Crawford |  | Modify | EP | 0.07 |  | 4/15/2029 |  | No | 12/13/2024 | 12/13/2024 | 0 |  |  |  | 2024-12-13
b3914.3 | PJM WEST | Change No-load Tap of 3 Autotransformers at Elmhurst from 338.25kV to 346.5 kV. | Baseline | 345,138 | 0.05 | 4/15/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | Elmhurst |  | Modify | EP | 0.05 |  | 4/15/2029 |  | No | 12/13/2024 | 12/13/2024 | 0 |  |  |  | 2024-12-13
b3914.4 | PJM WEST | Change No-load Tap of 2 Autotransformers at West Loop from 338.25kV to 346.5kV. | Baseline | 138,345 | 0.03 | 4/15/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | West Loop |  | Modify | EP | 0.03 |  | 4/15/2029 |  | No | 12/13/2024 | 12/13/2024 | 0 |  |  |  | 2024-12-13
b3914.5 | PJM WEST | Change No-load Tap of 2 Autotransformers at Taylor from 338.25kV to 346.5kV. | Baseline | 345,138 | 0.03 | 4/15/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | Taylor |  | Modify | EP | 0.03 |  | 4/15/2029 |  | No | 12/13/2024 | 12/13/2024 | 0 |  |  |  | 2024-12-13
b3914.6 | PJM WEST | Change No-load Tap of 4 Autotransformers at Skokie from 338.25 kV to 345.65 kV. | Baseline | 138,345 | 0.07 | 4/15/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | Skokie |  | Modify | EP | 0.07 |  | 4/15/2029 |  | No | 12/13/2024 | 12/13/2024 | 0 |  |  |  | 2024-12-13
b3737.1 | PJM MA | Larrabee substation – Reconfigure substation. | Baseline | 230 | 4.24 | 6/1/2029 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee |  | Modify | IS | 4.24 |  | 6/1/2029 | 12/13/2024 | No | 11/4/2022 | 11/4/2022 | 100 |  |  |  | 2022-11-04
b3737.2 | PJM MA | Larrabee substation – 230 kV equipment for direct connection. | Baseline | 230 | 4.77 | 6/1/2029 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee |  | Modify | EP | 4.77 |  | 1/1/2026 |  | No | 11/4/2022 | 11/4/2022 | 30 |  |  |  | 2022-11-04
b3737.23 | PJM MA | Rebuild the underground portion of Richmond-Waneeta 230 kV. | Baseline | 230 | 16 | 6/1/2029 | PECO | 2021_SAA-127 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Richmond-Waneeta |  | Rebuild | EP | 16 |  | 6/1/2029 |  | No | 11/4/2022 | 11/4/2022 | 0 |  |  |  | 2022-11-04
b3737.26 | PJM MA | Upgrade Cardiff-New Freedom 230 kV by modifying existing relay setting to increase relay limit. | Baseline | 230 | 0.3 | 6/1/2029 | AEC | 2021_SAA-127 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Cardiff-New Freedom |  | Modify | EP | 0.3 |  | 4/30/2029 |  | No | 11/4/2022 | 11/4/2022 | 0 |  |  |  | 2022-11-04
b3737.27 | PJM MA | Rebuild approximately 0.8 miles of the D1018 (Clarksville-Lawrence 230 kV) line between Lawrence substation (PSEG) and structure No. 63. | Baseline | 230 | 14.58 | 6/1/2029 | JCPL | 2021_SAA-17 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Clarksville-Lawrence |  | Rebuild | EP | 14.58 |  | 12/17/2026 |  | No | 11/4/2022 | 5/9/2023 | 10 |  |  |  | 2022-11-04
b3737.28 | PJM MA | Reconductor Kilmer I-Lake Nelson I 230 kV. | Baseline | 230 | 4.42 | 6/1/2029 | JCPL | 2021_SAA-17 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Kilmer I-Lake Nelson I |  | Reconductor | EP | 4.42 |  | 6/1/2029 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.3 | PJM MA | Lakewood Generator substation – Update relay settings on the Larrabee 230 kV line. | Baseline | 230 | 0.03 | 6/1/2029 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Lakewood |  | Modify | EP | 0.03 |  | 6/1/2029 |  | No | 11/4/2022 | 11/4/2022 | 20 |  |  |  | 2022-11-04
b3737.31 | PJM MA | Additional reconductoring required for Lake Nelson I-Middlesex 230 kV. | Baseline | 230 | 3.3 | 6/1/2029 | JCPL |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Lake Nelson I-Middlesex |  | Reconductor | EP | 3.3 |  | 6/1/2029 |  | No | 11/4/2022 | 11/4/2022 | 10 |  |  |  | 2022-11-04
b3737.33 | PJM MA | Reconductor Red Oak A-Raritan River 230 kV. | Baseline | 230 | 12.53 | 6/1/2029 | JCPL |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Red Oak A-Raritan River |  | Reconductor | EP | 12.53 |  | 6/1/2029 |  | No | 11/4/2022 | 5/9/2023 | 5 |  |  |  | 2022-11-04
b3737.34 | PJM MA | Reconductor Red Oak B-Raritan River 230 kV. | Baseline | 230 | 3.9 | 6/1/2029 | JCPL |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Red Oak B-Raritan River |  | Reconductor | EP | 3.9 |  | 6/1/2029 |  | No | 11/4/2022 | 11/4/2022 | 5 |  |  |  | 2022-11-04
b3737.35 | PJM MA | Reconductor small section of Raritan River-Kilmer I 230 kV. | Baseline | 230 | 27.3 | 6/1/2029 | JCPL |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Raritan River-Kilmer I |  | Reconductor | EP | 27.3 |  | 6/1/2029 |  | No | 11/4/2022 | 5/9/2023 | 5 |  |  |  | 2022-11-04
b3737.36 | PJM MA | Replace substation conductor at Kilmer and reconductor Raritan River-Kilmer W 230 kV. | Baseline | 230 | 25.88 | 6/1/2029 | JCPL |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Raritan River-Kilmer W |  | Reconductor | EP | 25.88 |  | 6/1/2029 |  | No | 11/4/2022 | 11/4/2022 | 5 |  |  |  | 2022-11-04
b3737.37 | PJM MA | Add a third set of submarine cables, rerate the overhead segment, and upgrade terminal equipment to achieve a higher rating for the Silver Run-Hope Creek 230 kV line. | Baseline | 230 | 61.2 | 6/1/2029 | LS POWER | 2021_SAA-229 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Silver Run-Hope Creek |  | Upgrade | EP | 61.2 |  | 6/1/2029 |  | No | 11/4/2022 | 11/4/2022 | 8 |  |  |  | 2022-11-04
b3737.4 | PJM MA | B54 Larrabee-South Lockwood 34.5 kV line transfer. | Baseline | 34.5 | 0.31 | 6/1/2029 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee-South Lockwood |  | Modify | EP | 0.31 |  | 6/1/2029 |  | No | 11/4/2022 | 11/4/2022 | 0 |  |  |  | 2022-11-04
b3737.40 | PJM MA | Windsor to Clarksville subproject: Reconductor one span of the C1017 (Clarksville-Windsor) 230kV line from structure #126 to Windsor Substation with double bundled 1590 ACSR conductor, approximately (0.1) mile. | Baseline | 230 | 1.72 | 6/1/2029 | JCPL | 2021_SAA-180 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Windsor, Clarksville |  | Upgrade | EP | 1.72 |  | 11/13/2026 |  | No | 11/4/2022 | 5/9/2023 | 5 |  |  |  | 2022-11-04
b3737.41 | PJM MA | Windsor to Clarksville subproject: Upgrade terminal equipment at Clarksville 230 kV. | Baseline | 230 | 0 | 6/1/2029 | PSEG | 2021_SAA-180 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Clarksville |  | Upgrade | Cancelled | 1.49 |  | 6/1/2029 |  | No | 11/4/2022 | 5/9/2023 | 0 |  |  |  | 2022-11-04
b3737.42 | PJM MA | Upgrade inside plant equipment at Lake Nelson I 230 kV. | Baseline | 230 | 8.2 | 6/1/2029 | PSEG |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Lake Nelson |  | Upgrade | UC | 4.8 |  | 6/1/2029 |  | No | 11/4/2022 | 5/9/2023 | 36 |  |  |  | 2022-11-04
b3737.43 | PJM MA | Upgrade Kilmer W-Lake Nelson W 230 kV line drop and strain bus connections at Lake Nelson 230 kV. | Baseline | 230 | 1.5 | 6/1/2029 | PSEG |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Lake Nelson |  | Upgrade | UC | 0.57 |  | 6/1/2029 |  | No | 11/4/2022 | 5/9/2023 | 36 |  |  |  | 2022-11-04
b3737.44 | PJM MA | Upgrade Lake Nelson-Middlesex-Greenbrook W 230 kV line drop and strain bus connections at Lake Nelson 230 kV. | Baseline | 230 | 0.7 | 6/1/2029 | PSEG |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Lake Nelson |  | Upgrade | UC | 0.58 |  | 6/1/2029 |  | No | 11/4/2022 | 5/9/2023 | 36 |  |  |  | 2022-11-04
b3737.46 | PJM MA | Install a new breaker at Graceton 230 kV substation to terminate a new 230 kV line from the new greenfield North Delta station | Baseline | 230 | 1.55 | 6/1/2029 | BGE | 2021_SAA-63, DENL | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | MD | Graceton |  | Install | Cancelled | 1.55 |  | 6/1/2029 |  | No | 11/4/2022 | 1/9/2024 | 0 |  |  |  | 2022-11-04
b3737.48 | PJM MA | Build a new North Delta-Graceton 230 kV line by rebuilding 6.26 miles of the existing Cooper-Graceton 230 kV line to double circuit. Cooper-Graceton is jointly owned by PECO & BGE. This subproject is for PECO's portion of the line rebuild which is 4.1 miles. | Baseline | 230 | 18.82 | 6/1/2029 | PECO | 2021_SAA-63, DENL | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | PA | Cooper-Graceton |  | Rebuild | Cancelled | 18.82 |  | 6/1/2029 |  | No | 11/4/2022 | 1/9/2024 | 0 |  |  |  | 2022-11-04
b3737.49 | PJM MA | Bring the Cooper-Graceton 230 kV line “in and out” of North Delta by constructing a new double-circuit North Delta-Graceton 230 kV (0.3 miles) and a new North Delta-Cooper 230 kV (0.4 miles) cut-in lines. | Baseline | 230 | 1.56 | 6/1/2029 | PECO | 2021_SAA-63, DENL | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | PA | Copper- Graceton, North Delta |  | Modify | Cancelled | 1.56 |  | 6/1/2029 |  | No | 11/4/2022 | 1/9/2024 | 0 |  |  |  | 2022-11-04
b3737.5 | PJM MA | Larrabee Collector station-Larrabee 230 kV new line. | Baseline | 230 | 7.52 | 6/1/2029 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee Collector Station-Larrabee |  | Install | EP | 7.52 |  | 6/1/2026 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.50 | PJM MA | Bring the Peach Bottom-Delta York 500 ‘5034’ kV line “in and out” of Bramah substation by partially demolishing the 5034 line to construct a new Peach Bottom-Bramah-Delta York 500 kV line, with 0.87 miles of cut-in and cut-out lines. | Baseline | 500 | 1.56 | 6/1/2029 | PECO | 2021_SAA-63 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | PA | Peach Bottom-Delta Power Plant |  | Modify | EP | 12 |  | 6/1/2029 |  | No | 11/4/2022 | 5/6/2025 | 0 |  |  |  | 2022-11-04
b3737.51 | PJM MA | Replace four 63 kA circuit breakers "205," "235," "225" and "255" at Peach Bottom 500 kV with 80 kA. | Baseline | 500 | 5.6 | 6/1/2029 | PECO |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | PA | Peach Bottom |  | Replace | Cancelled | 5.6 |  | 6/1/2029 |  | No | 11/4/2022 | 11/4/2022 | 0 |  |  |  | 2022-11-04
b3737.52 | PJM MA | Replace one 63 kA circuit breaker "B4" at Conastone 230 kV with 80 kA. | Baseline | 230 | 1.3 | 6/1/2029 | BGE |  | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | MD | Conastone |  | Replace | Cancelled | 1.3 |  | 6/1/2029 |  | No | 11/4/2022 | 7/8/2025 | 0 |  |  |  | 2022-11-04
b3737.55 | PJM MA | Middlesex substation 230 kV – Replace the 2000A circuit switcher at Middlesex switch point for the Lake Nelson I1023 230 kV exit. | Baseline | 230 | 0.53 | 6/1/2029 | JCPL | 2021_SAA-17 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Middlesex |  | Upgrade | EP | 0.53 |  | 6/1/2029 |  | No | 5/9/2023 | 5/9/2023 | 2 |  |  |  | 2023-05-09
b3737.56 | PJM MA | Build a new North Delta-Graceton 230 kV line by rebuilding 6.26 miles of the existing Cooper-Graceton 230 kV line to double circuit. Cooper-Graceton is jointly owned by PECO & BGE. This subproject is for BGE's portion of the line rebuild, which is 2.16 miles. | Baseline | 230 | 9.92 | 6/1/2029 | BGE | 2021_SAA-63, DENL | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | MD | Cooper-Graceton |  | Rebuild | Cancelled | 9.92 |  | 6/1/2029 |  | No | 5/9/2023 | 1/9/2024 | 0 |  |  |  | 2023-05-09
b3737.59 | PJM MA | Windsor to Clarksville subproject: Upgrade terminal equipment at Windsor 230 kV. | Baseline | 230 | 1.58 | 6/1/2029 | JCPL | 2021_SAA-180 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Clarksville |  | Upgrade | EP | 1.58 |  | 6/1/2029 |  | No | 5/9/2023 | 5/9/2023 | 10 |  |  |  | 2023-05-09
b3800.375 | PJM SOUTH | Construct new Woodside-Goose Creek 500 kV line for ~3 miles on single circuit monopole structures within the Doubs-Goose Creek Corridor. (DOM Portion) | Baseline | 500 | 15.6 | 6/1/2029 | Dominion | 2022-W3-853 | Appendix A | APS:9.26,BGE:7.30,Dominion:72.31,PEPCO:11.13 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Goose Creek |  | Construct | EP | 15.6 |  | 9/30/2030 |  | No | 7/10/2024 | 7/10/2024 | 10 |  |  |  | 2024-07-10
b3857.1 | PJM MA | Conastone 230kV Breaker #5 | Baseline | 500 | 1.92 | 6/1/2029 | BGE |  | Appendix A | BGE:100 |  | MD | Conastone |  | Upgrade | PL | 1.92 |  | 6/1/2029 |  | No | 11/6/2024 | 11/6/2024 | 0 |  |  |  | 2024-11-06
b3860.1 | PJM MA | Replace the 34.5 kV bus tie breaker at Chester Substation with a new 34.5 kV breaker that has an interruption capability of 40 kA. | Baseline | 230 | 0.54 | 6/1/2029 | JCPL |  | Appendix A | JCPL:100 |  | NJ | Chester |  | Replace | EP | 0.54 |  | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3861.1 | PJM MA | Replace the W101 34.5 kV breaker at Werner Substation with a new 34.5 kV breaker that has an interruption capability of 40 kA. | Baseline | 230 | 0.54 | 6/1/2029 | JCPL |  | Appendix A | JCPL:100 |  | NJ | Werner |  | Replace | EP | 0.54 |  | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3862.1 | PJM MA | Upgrade two (2) 500kV free standing CTs, one (1) disconnect switch, and four (4) sections of tube bus at Elroy 500kV Substation. | Baseline | 500 | 1.5 | 6/1/2029 | PECO |  | Appendix A | PECO:100 |  | PA | Elroy |  | Upgrade | EP | 1.5 |  | 12/31/2028 |  | No | 12/3/2024 | 12/3/2024 | 12 |  |  |  | 2024-12-03
b3864.1 | PJM MA | Replace station cable at Tacony 69kv Station | Baseline | 69 | 0.18 | 6/1/2029 | PECO |  | Appendix A | PECO:100 |  | PA | Tacony |  | Upgrade | EP | 0.18 |  | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3864.2 | PJM MA | Replace station cable at Richmond 230kV Station | Baseline | 69 | 0.18 | 6/1/2029 | PECO |  | Appendix A | PECO:100 |  | PA | Richmond |  | Upgrade | EP | 0.18 |  | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3867.1 | PJM MA | Upgrade a circuit switcher at Mickleton substation. | Baseline | 230 | 1.03 | 6/1/2029 | ACE |  | Appendix A | AEC:100 |  | NJ | Mickleton |  | Replace | EP | 1.03 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3868.1 | PJM MA | Cut existing Carlstadt to River Road 69kV line and extend Carlstadt line side to Penhorn 69kV. Extend the other end of the line by constructing a new portion and connecting it to Kingsland 69kV Switch. | Baseline | 69 | 14.62 | 6/1/2029 | PSEG |  | Appendix A | PSEG:100 |  | NJ | Penhorn 69kV,Carlstad |  | Reconfigure | PL | 14.62 |  | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3868.2 | PJM MA | Extend the other end of L-636 to Kingsland Switch by constructing new 5.5 miles portion utilizing existing I-2314 Transmission towers from H-A 5/4 to H-A 2/3. New 69kV line to be routed along County Ave pass Secaucus Rd in Secaucus NJ. | Baseline | 69 | 30.87 | 6/1/2029 | PSEG |  | Appendix A | PSEG:100 |  | NJ | Tonnelle,Kingsland 69kV |  | Reconfigure | PL | 30.87 |  | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3868.3 | PJM MA | Reconfigure former River Road to Carlstadt 69kV and Tonnelle Ave to Union City 69kV lines at the intersection Tonnelle Ave and Granton Ave in North Bergen, NJ. by connecting Union City to River Road and Tonnelle Ave to Kingsland. | Baseline | 69 | 0.51 | 6/1/2029 | PSEG |  | Appendix A | PSEG:100 |  | NJ | River Road,Union City |  | Reconfigure | PL | 0.51 |  | 6/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3871.1 | PJM WEST | Replace two 138 kV disconnect switches with 3000 amp disconnect switches and replace a portion of the stranded conductor on the #2 138 kV Bus with aluminum pipe bus. | Baseline | 138 | 8 | 6/1/2029 | DL |  | Appendix A | DL:100 |  | PA | Brunot Island |  | Modify | PL | 8 |  | 12/31/2028 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3873.1 | PJM WEST | Install 12 MVAR 34.5 kV cap bank at Greenleaf | Baseline | 34.5 | 1.31 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | IN | Greenleaf |  | Install | EP | 1.31 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3875.1 | PJM WEST | Reconductor ~3.95 miles of ACSR 6/1 Penguin (4/0) on the Firebrick-Jefferson Switch 69 kV branch with ACSR 556.6 26/7. Remote End (Line setting) would need to be updated at Firebrick and Lick. Replace 600A Switches at Jefferson and replace 477 AA 19 sub conductor at Firebrick. | Baseline | 138,69 | 8.5 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | Firebrick,Jefferson |  | Reconductor | EP | 8.5 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3877.1 | PJM WEST | Project will replace station conductor and switches in the 345 kV yard at Beatty that are currently limiting the 345 kV lines to Adkins and Chenoweth | Baseline | 345 | 0.5 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | Beatty |  | Replace | EP | 0.5 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3877.2 | PJM WEST | Project will upgrade 345 kV circuit breakers 'A' and 'A1' to 4000A 63 kA breakers at Adkins station along with some station conductor that is currently limiting the 345 kV line to Beatty. | Baseline | 345 | 4.5 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | Adkins |  | Replace | EP | 4.5 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3878.1 | PJM WEST | Proposal will upgrade 765 kV circuit breakers 'B' and 'B2' 'to 5000A 50 kA breakers at Marysville station. In addition, the project will upgrade the existing wavetrap towards Sorenson. | Baseline | 765 | 10 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | Marysville |  | Replace | EP | 10 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b3879.1 | PJM WEST | Replace line conductor, ~0.11 miles of 4/0 ACSR 6/1 conductor with 556.5 26/7 between South Toronto and the South Toronto Tap. | Baseline | 138 | 0.5 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | South Toronto |  | Reconductor | EP | 0.5 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3879.2 | PJM WEST | Upgrade the wave trap, CCVTs, switches, and station conductor at South Toronto station currently limiting the line to South Toronto Tap. | Baseline | 138 | 0.6 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | South Toronto |  | Replace | EP | 0.6 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3880.1 | PJM WEST | At Beatty Road substation, install a 69 kV 23 MVAR capacitor bank along with the 69kV Cap bank breaker. | Baseline | 345 | 2.25 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | Beatty |  | Install | EP | 2.25 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3888.1 | PJM WEST | Preform sag study and complete mitigations on the 138 kV line between East Leipsic and the AE2-072 tap (Lammer) to allow line's conductor to operate to its maximum operating temperature (MOT). | Baseline | 138 | 2.5 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | East Leipsic,Lammer |  | Sag Study | EP | 2.5 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3889.1 | PJM WEST | Project will replace limiting station equipment at Tiltonsville station to increase the rating on the branch to Windsor | Baseline | 138 | 0.8 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | Tiltonsville |  | Replace | EP | 0.8 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3890.1 | PJM WEST | Replace station conductor at South Coshocton station currently limiting the branch to Ohio Central | Baseline | 138 | 0.2 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | South Coshocton |  | Replace | EP | 0.2 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3891.1 | PJM WEST | Project will perform relay upgrades at Kenny 138 kV to raise the CT & Relay thermal limits that are currently limiting the line to Roberts. | Baseline | 138 | 0.4 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | Kenny |  | Upgrade | EP | 0.4 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3894.1 | PJM WEST | Replace limiting station conductor at Tidd on the line to Carnegie (FE). | Baseline | 345 | 0.5 | 6/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | Tidd |  | Replace | EP | 0.5 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3899.1 | PJM WEST | Replace OVEC owned station equipment at Kyger Creek to raise the rating of the Kyger Creek-Sporn 345 kV line. Equipment to be replaced includes station conductor and a wavetrap at Kyger Creek. | Baseline | 345 | 0.8 | 6/1/2029 | OVEC |  | Appendix A | OVEC:100 |  | OH | Kyger Creek |  | Replace | EP | 0.8 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b3901.1 | PJM WEST | Reconductor 138 kV line from Electric Junction to W541. | Baseline | 138 | 1.38 | 6/1/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | W541,Electric Junction |  | Reconductor | EP | 1.38 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3901.2 | PJM WEST | Replace 2" tubular bus, 2-500 KCMIL Cu and 1113 KCMIL ACSR/AA on bus 2 and line terminal of 138kV L11106 at TSS 111 Electric Junction with bus that meets or exceeds a minimum thermal capability of 2036/2236/2690A (487/534/643MVA) SN/SE/SLD. | Baseline | 138 | 0.28 | 6/1/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | Electric Junction |  | Replace | EP | 0.28 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3906.1 | PJM MA | Construct new Marley Neck 115 kV substation. Marley Neck 115kV portion will accommodate 10 breaker-and-a-half bays, with only 6 bays planned for initial service while accommodating 4 future bays. Two Standard 230/115kV transformers will be connected between the 230 and 115 kV equipment with appropriate isolation methods. | Baseline | 230/115 | 107.62 | 6/1/2029 | BGE | 2024-W1-295 | Appendix A | BGE:100 |  | MD | Marley Neck |  | Build | EP | 107.62 |  | 12/31/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3907.1 | PJM MA | Reconductor entire 2.5 miles of North Philadelphia to Master 230 kV line | Baseline | 230 | 6.49 | 6/1/2029 | PECO | 2024-W1-12 | Appendix A | AEC:0.76,JCPL:1.45,PECO:94.22,PSEG:3.29,RE:0.13,Neptune:0.15 |  | PA | North Philadelphia |  | Rebuild | EP | 6.49 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 3 |  |  |  | 2024-12-03
b3908.1 | PJM MA | Install one 80 MVAr 230 kV capacitor bank at Pocono 230kV Substation | Baseline | 230 | 4.97 | 6/1/2029 | PPL | 2024-W1-850 | Appendix A | PPL:100 |  | PA | Pocono |  | Install | PL | 4.93 |  | 4/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3910.1 | PJM MA | Susquehanna T10 230 kV Station Reconfiguration. Break the existing Susquehanna - Glen Brook 230 kV line and loop it 0.2 miles in and out of the Susquehanna T10 230 kV Station. | Baseline | 230 | 10.07 | 6/1/2029 | PPL | 2024-W1-549 | Appendix A | PPL:100 |  | PA | Susquehanna |  | Reconfigure | PL | 9.5 |  | 12/31/2028 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3911.1 | PJM WEST | Rebuild the existing 1.1 mile Canal - Gay 138 kV oil filled pipe-type underground line to address overloads on the existing cable utilizing 5000 MCM XLPE cable. | Baseline | 138 | 15.6 | 6/1/2029 | AEP | 2024-W1-940 | Appendix A | AEP:100 |  | OH | Canal - Gay |  | Rebuild | EP | 15.6 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3912.1 | PJM WEST | Rebuild the existing 2.2-mile Canal-Mound St 138 kV oil filled pipe-type underground line to address overloads on the existing cable utilizing 5000 MCM XLPE cable. | Baseline | 138 | 31.09 | 6/1/2029 | AEP | 2024-W1-856 | Appendix A | AEP:100 |  | OH | Canal - Mound |  | Rebuild | EP | 31.09 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3913.1 | PJM WEST | Rebuild 138 kV line section between Beatty and White Road stations (approximately 4.5 miles). Update remote end relay settings as needed. | Baseline | 138 | 18.8 | 6/1/2029 | AEP | 2024-W1-769 | Appendix A | AEP:100 |  | OH | Beatty - White Road |  | Rebuild | EP | 18.8 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3913.2 | PJM WEST | Rebuild 138 kV line section between White Road and Cyprus stations (approximately 3.34 miles). Update remote end relay settings as needed. | Baseline | 138 | 14.31 | 6/1/2029 | AEP | 2024-W1-769 | Appendix A | AEP:100 |  | OH | White Road - Cyprus |  | Rebuild | EP | 14.31 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3915.1 | PJM WEST | Reconductor 1.5 miles of 345 kV lines 1202 and 1227 from Dresden to Mulberry with two conductor bundled 1033.5 ACSS conductor. Modify and replace towers as necessary to accommodate the higher mechanical loads of the bundled conductor. | Baseline | 345 | 12.33 | 6/1/2029 | ComEd | 2024-W1-135 | Appendix A | ComEd:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | IL | Dresden-Mulberry |  | Reconductor | EP | 12.33 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3915.2 | PJM WEST | Install 345 kV circuit breaker on line 1202 (Dresden-Mulberry 345 kV) and upgrade disconnects and associated equipment at Dresden 345 kV substation. | Baseline | 345 | 3.77 | 6/1/2029 | ComEd | 2024-W1-135 | Appendix A | ComEd:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | IL | Dresden |  | Install | EP | 3.77 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3915.3 | PJM WEST | Upgrade disconnects and associated equipment at Mulberry 345 kV substation. | Baseline | 345 | 0.17 | 6/1/2029 | ComEd | 2024-W1-135 | Appendix A | ComEd:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | IL | Mulberry |  | Upgrade | EP | 0.17 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3916.1 | PJM WEST | Install a new 420 MVA 345/138 kV autotransformer and associated 345 kV and 138 kV circuit breakers at Itasca substation. | Baseline | 345/138 | 14.31 | 6/1/2029 | ComEd | 2024-W1-816 | Appendix A | ComEd:100 |  | IL | Itasca |  | Install | EP | 14.31 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3918.1 | PJM WEST | Add one additional breaker, a 2nd 138/69kV transformer, replace five 69kV breakers & four 138kV breakers at the Miami substation. | Baseline | 345 | 12 | 6/1/2029 | Dayton |  | Appendix A | Dayton:100 |  | OH | Miami |  | Modify | PL | 12 |  | 6/30/2028 |  | No | 1/17/2025 | 1/17/2025 | 0 |  |  |  | 2025-01-17
b3919.1 | PJM WEST | Reconfigure Maliszewski 765 kV station from 2 breakers to a 6 breaker ring bus. Install a new 765/345 kV transformer. Establish new 345 kV breaker yard with 3 string breaker and a half to include a line exit to Hyatt and a line exit to Corridor. Loop the existing Hyatt - West Millersport 345 kV line into the new established 345 kV yard at the Maliszewski station. | Baseline | 765 | 79.74 | 6/1/2029 | AEP | 2024-W1-408 | Appendix A | AEP:85.10,Dayton:9.33,DEOK:5.48,OVEC:0.09 |  | OH | Maliszewski |  | Reconfigure | EP | 79.74 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3919.10 | PJM WEST | Rebuild ~19.0 miles of Hyatt - Marysville 345 kV line using 4-bundled 795 ACSR conductor Bold construction (This is an EOL rebuild) | Baseline | 345 | 116.7 | 6/1/2029 | AEP | 2024-W1- Supplemental conversion | Appendix A | AEP:100 |  | OH | Hyatt - Marysville |  | Rebuild | EP | 116.7 |  | 6/1/2027 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b3919.2 | PJM WEST | Establish a 0.18 mile double circuit 345 kV line extension to cut the existing Hyatt – West Millersport 345 kV line in and out of Corridor station. | Baseline | 345 | 3.1 | 6/1/2029 | AEP | 2024-W1-408 | Appendix A | AEP:100 |  | OH | Hyatt - Corridor - West Millersport |  | Cut In | EP | 3.1 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3919.3 | PJM WEST | Install three new 345 kV breakers at Corridor station in order to accommodate the cut in of the Hyatt- West Millersport 345 kV line. | Baseline | 345 | 5.52 | 6/1/2029 | AEP | 2024-W1-408 | Appendix A | AEP:100 |  | OH | Corridor |  | Install | EP | 5.52 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3919.4 | PJM WEST | Reconductor 10.2-mile of Maliszewski-Corridor 345 kV line. | Baseline | 345 | 18.3 | 6/1/2029 | AEP | 2024-W1-408 | Appendix A | AEP:100 |  | OH | Maliszewski - Corridor |  | Reconductor | EP | 18.3 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3919.5 | PJM WEST | Reconductor 4.75-miles of the existing Bokes Creek-Marysville 345 kV circuit. Update the associated relay settings. | Baseline | 345 | 6.67 | 6/1/2029 | AEP | 2024-W1-408 | Appendix A | AEP:100 |  | OH | Bokes Creek - Marysville |  | Reconductor | EP | 6.67 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3919.6 | PJM WEST | Rebuild 4.4-miles of the existing Marysville - Hyatt 345 kV double circuit line where it extends into Marysville station. | Baseline | 345 | 26.26 | 6/1/2029 | AEP | 2024-W1-408 | Appendix A | AEP:100 |  | OH | Marysville - Hyatt |  | Rebuild | EP | 26.26 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3919.7 | PJM WEST | Upgrade 345 kV breakers K & K1 along with associated switches and conductor to 5000A at Hyatt Station. | Baseline | 345 | 2.94 | 6/1/2029 | AEP | 2024-W1-408 | Appendix A | AEP:100 |  | OH | Hyatt |  | Upgrade | EP | 2.94 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3919.8 | PJM WEST | Upgrade the relaying and associated equipment at West Millersport stationto coordinate with the cut in work to Corridor station. | Baseline | 345 | 0.41 | 6/1/2029 | AEP | 2024-W1-408 | Appendix A | AEP:100 |  | OH | West Millersport |  | Upgrade | EP | 0.41 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3919.9 | PJM WEST | Upgrade 3000A 345 kV breaker 'L2' along with associated terminal elements to 5000A at Marysville. | Baseline | 345 | 2.56 | 6/1/2029 | AEP | 2024-W1-408 | Appendix A | AEP:100 |  | OH | Marysville |  | Upgrade | EP | 2.56 |  | 6/1/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3921.1 | PJM SOUTH | Wreck and rebuild 115kV line 119 from structure 119/305 (Merck #5 substation) to 119/411A (Port Republic Substation). The existing structures shall be replaced one for one within the existing ROW using primarily custom engineered double circuit 115kV steel structures on concrete foundations. The line will be rebuilt with 3-phase 1-768.2 ACSS/TW/HS (20/7) 250 MOT “Maumee” conductor and two (2) DNO-11410 OPGW. The rebuild includes the installation of double circuit structures but assumes the second circuit will not be installed as part of this project, and that the vacant conductor arms should not be utilized without acquiring additional ROW. This scope assumes project GITAE2029C will be completed prior to the construction of this project. Project GITAE2029C serves to install Port Republic Substation, which will split Line 119 in between existing Structures 119/411 and 119/412. | Baseline | 115 | 44.84 | 6/1/2029 | Dominion |  | Appendix A | Dominion:100 |  | VA | Merck,Elkton D.P. |  | Rebuild | EP | 41.87 |  | 6/1/2029 |  | No | 12/12/2024 | 12/12/2024 | 0 |  |  |  | 2024-12-12
b3921.2 | PJM SOUTH | Uprate the 397.5 ACSR jumpers and associated equipment to meet the line conductor rating of 393MVA. | Baseline | 115 | 0.49 | 6/1/2029 | Dominion |  | Appendix A | Dominion:100 |  | VA | Merck |  | Upgrade | EP | 0.46 |  | 6/1/2029 |  | No | 12/12/2024 | 12/12/2024 | 0 |  |  |  | 2024-12-12
b3922.1 | PJM SOUTH | This project serves to wreck and rebuild 115kV line 1031 from structure 1031/220 to structure 1031/329. The existing structures to be removed are primarily single circuit wood, steel or concrete monopoles. The existing structures to be removed were primarily constructed in 1993 with the weathering steel structures being constructed in 2011. See Figure 1 for the project location. The existing structures shall be replaced one for one within the existing ROW using single circuit steel monopoles on foundations. The line will be rebuilt with single circuit 3-phase 768.2 ACSS/TW/HS (20/7) “Maumee” conductor and single (1) DNO-11410 OPGW, respectively. | Baseline | 115 | 29.37 | 6/1/2029 | Dominion |  | Appendix A | Dominion:100 |  | NC | Pantego,Terra Ceia |  | Rebuild | EP | 29.37 |  | 6/1/2029 |  | No | 12/12/2024 | 12/12/2024 | 0 |  |  |  | 2024-12-12
b3925.1 | PJM WEST | Rebuild the 7.46 miles of Avery - Shinrock 138 kV Line with 795 kcmil 26/7 ACSS (7.46 miles) | Baseline | 138 | 15.2 | 6/1/2029 | ATSI | 2024-W1-605 | Appendix A | ATSI:100 |  | OH | Avery - Shinrock |  | Rebuild | EP | 15.2 |  | 12/10/2027 |  | No | 1/7/2025 | 1/7/2025 | 0 | 6/1/2029 |  |  | 2025-01-07
b3925.2 | PJM WEST | Rebuild the 13.45 miles of Greenfield - Lakeview 138 kV Line from 2 x 336.4 kcmil 26/7 ACSR to 1 x 795 kcmil 26/7 ACSS | Baseline | 138 | 59.68 | 6/1/2029 | ATSI | 2024-W1-605 | Appendix A | ATSI:100 |  | OH | Greenfield - Lakeview |  | Rebuild | EP | 59.68 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 | 6/1/2029 |  |  | 2025-01-07
b3925.4 | PJM WEST | Rebuild the Greenfield - Beaver 138 kV corridor (32 miles) with 795 kcmil 26/7 ACSS. This corridor encompasses multiple 138 kV lines that are constructed on common towers. | Baseline | 138 | 131.43 | 6/1/2029 | ATSI | 2024-W1-605 | Appendix A | ATSI:100 |  | OH | Greenfield - Beaver Corridor |  | Rebuild | EP | 131.43 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 | 6/1/2029 |  |  | 2025-01-07
b3928.1 | PJM SOUTH | Install (1) 230kV, 50 MVAr Shunt Capacitor Bank & associated equipment including breaker at Navy North substation. | Baseline | 230 | 3 | 6/1/2029 | Dominion | 2024-W1-527 | Appendix A | Dominion:100 |  | VA | Navy North |  | Install | EP | 3 |  | 3/31/2026 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b3929.1 | PJM SOUTH | Rebuild approximately 33.09 miles of 500 kV line #579 from structure 579/1 inside Septa substation to structure 579/193 inside Yadkin substation. | Baseline | 500 | 191.25 | 6/1/2029 | Dominion | 2024-W1-980 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Septa, Yadkin |  | Rebuild | EP | 191.25 |  | 12/31/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b3929.2 | PJM SOUTH | At Septa substation, upgrade CB (579T586), breaker switches (56288, 57985, 58688 & 57988), and line leads to 5000A rating to support Line #579 rebuild. | Baseline | 500 | 3.84 | 6/1/2029 | Dominion | 2024-W1-980 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Septa |  | Upgrade | EP | 3.84 |  | 12/31/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b3929.3 | PJM SOUTH | At Yadkin substation, upgrade line leads to 5000A rating to support Line #579 rebuild. | Baseline | 500 | 0.44 | 6/1/2029 | Dominion | 2024-W1-980 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Yadkin |  | Upgrade | EP | 0.44 |  | 12/31/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b3929.4 | PJM SOUTH | Rebuild approximately 7.7 miles of 230kV Line #2110 Suffolk – Thrasher that share the double circuit towers under Line #579. | Baseline | 230 | 21.25 | 6/1/2029 | Dominion | 2024-W1-980 | Appendix A | Dominion:100 |  | VA | Suffolk, Thrasher |  | Rebuild | EP | 21.25 |  | 12/31/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.1 | PJM WEST | Add two 765 kV breakers at Amos Substation to expand the breaker and a half scheme to accommodate the new Amos-Welton Spring 765 kV line. | Baseline | 765 | 30.87 | 6/1/2029 | AEP | 2024-W1-708 | Appendix A | APS:14.67,BGE:8.11,Dominion:66.09,DPL:2.15,PEPCO:8.98 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | WV | John Amos |  | Install | EP | 30.87 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.10 | PJM WEST | Install four 250 MVAR cap banks (two on 765 and two on 500 kV side) and a +/-500 MVAR STATCOM on the 765 kV Rocky Point yard | Baseline | 765 | 121 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Rocky Point |  | Install | EP | 121 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.100 | PJM SOUTH | Ashburn Sub 230kV - replace 50kA breaker SC332 with 63kA | Baseline | 230 | 0.5 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Ashburn Sub |  | Replace | EP | 0.5 |  | 7/15/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.101 | PJM SOUTH | Beaumeade Sub 230kV - replace 63kA breaker 274T2206 with 80kA | Baseline | 230 | 0.66 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Beaumeade Sub |  | Replace | EP | 0.66 |  | 12/15/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.102 | PJM SOUTH | Braddock Sub 230kV - replace 40kA breakers 207T294, 237T294, 237T297, 281T297 with 63kA | Baseline | 230 | 2 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Braddock Sub |  | Replace | EP | 2 |  | 10/18/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.103 | PJM SOUTH | Brambleton Sub 230kV - replace 63kA breakers 217202, 2172T2183, L102, L202 with 80kA | Baseline | 230 | 2.64 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Brambleton Sub |  | Replace | EP | 2.64 |  | 6/1/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.104 | PJM SOUTH | Bristers Sub 230kV - replace 40kA and 50kA breakers H1TH2, H2TH3, L1T2101 with 63kA | Baseline | 230 | 1.5 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Bristers Sub |  | Replace | EP | 1.5 |  | 8/2/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.105 | PJM SOUTH | Bull Run Sub 230kV - replace 50kA breaker H362 with 63kA | Baseline | 230 | 0.5 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Bull Run Sub |  | Replace | EP | 0.5 |  | 7/12/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.106 | PJM SOUTH | Buttermilk Sub 230kV - replace 63kA breakers 215212, 217012, 220312, 221412, 2152T2203 with 80kA | Baseline | 230 | 3.3 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Buttermilk Sub |  | Replace | EP | 3.3 |  | 7/11/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.107 | PJM SOUTH | Cabin Run Sub 230kV - replace 63kA breakers 209512, 221312, T122 with 80kA | Baseline | 230 | 1.98 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Cabin Run Sub |  | Replace | EP | 1.98 |  | 2/15/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.108 | PJM SOUTH | Carson Sub 230kV - replace 40kA breaker 23872 with 63kA | Baseline | 230 | 0.5 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Carson Sub |  | Replace | EP | 0.5 |  | 7/12/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.109 | PJM SOUTH | Clifton Sub 230kV - replace 63kA breakers 201182, SR182, XT2011 with 80kA | Baseline | 230 | 1.98 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Clifton Sub |  | Replace | EP | 1.98 |  | 5/10/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.11 | PJM WEST | Expand Black Oak Substation to accommodate the connection of the 502 Jct-Woodside 500 kV line and loop the 502 Jct-Woodside 500 kV line into the Black Oak substation by constructing ~0.85 miles of new 500 kV line into and out of Black Oak 500 kV substation | Baseline | 500 | 19.23 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:8.93,BGE:13.63,Dominion:61.66,PEPCO:15.78 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Black Oak |  | Expand | PL | 19.23 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.110 | PJM WEST | Doubs Sub 500kV - replace 50kA breaker DL-59 #2CAP with 63kA | Baseline | 500 | 11.5 | 6/1/2029 | APS | 2024-W1-Short Circuit | Appendix A | APS:100 |  | MD | Doubs Sub |  | Replace | PL | 10.6 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.111 | PJM SOUTH | Evergreen Mills Sub 230kV - replace 63kA breakers H132, H232 with 80kA | Baseline | 230 | 1.32 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Evergreen Mills Sub |  | Replace | EP | 1.32 |  | 2/3/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.112 | PJM SOUTH | Goose Creek Sub 230kV - replace 63kA breaker L1T227 with 80kA | Baseline | 230 | 0.66 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Goose Creek Sub |  | Replace | EP | 0.66 |  | 12/12/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.113 | PJM SOUTH | Goose Creek Sub 500kV - replace 50kA breaker SC182 with 63kA | Baseline | 500 | 1.01 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Goose Creek Sub |  | Replace | EP | 1.01 |  | 2/27/2031 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.114 | PJM SOUTH | Ladysmith S1 Sub 230kV - replace 40kA breakers 25672, 209072, 256T2090, GT172, GT272, GT372, GT472, GT572 with 63kA | Baseline | 230 | 4 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Ladysmith Sub |  | Replace | EP | 4 |  | 7/18/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.115 | PJM SOUTH | Ladysmith Sub 500kV - replace 40kA breaker 574T581 with 63kA | Baseline | 500 | 1.01 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Ladysmith Sub |  | Replace | EP | 1.01 |  | 11/27/2031 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.116 | PJM SOUTH | Liberty Sub 230kV - replace 50kA breaker SC112 with 63kA | Baseline | 230 | 0.5 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Liberty Sub |  | Replace | EP | 0.5 |  | 7/15/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.117 | PJM SOUTH | Lockridge Sub 230kV - replace 63kA breakers 218872, H12T2188, 222372, H12T2223 with 80kA | Baseline | 230 | 2.64 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Lockridge Sub |  | Replace | EP | 2.64 |  | 6/15/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.118 | PJM SOUTH | Loudoun Sub 230kV - replace 63kA breakers 209452, L152, L252 with 80kA | Baseline | 230 | 1.98 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Loudoun Sub |  | Replace | EP | 1.98 |  | 3/20/2031 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.119 | PJM SOUTH | Loudoun Cap Sub 230kV - replace 50kA breaker SC352 with 63kA | Baseline | 230 | 0.5 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Loudoun Sub |  | Replace | EP | 0.5 |  | 10/31/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.12 | PJM WEST | Upgrade the terminal equipment on the Doubs No. 1 500/230 kV transformer. | Baseline | 500/230 | 0.43 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:74.10,PEPCO:25.90 |  | MD | Doubs |  | Upgrade | PL | 0.43 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.120 | PJM SOUTH | Loudoun Sub 500kV - replace 50kA breakers 502T535, 569T584, H1T569, H2T502, H2T584, SC152 with 63kA | Baseline | 500 | 6.09 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Loudoun Sub |  | Replace | EP | 6.09 |  | 3/4/2032 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.121 | PJM SOUTH | Marsh Run Sub 230kV - replace 50kA breaker 28002, 29902, 280T2039, 299T2040, 203902, 204002 with 63kA | Baseline | 230 | 3 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Marsh Run Sub |  | Replace | EP | 3 |  | 6/20/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.122 | PJM SOUTH | Morrisville Sub 230kV - replace 50kA breaker L1T2039, L1T2040, L2T2039, L2T2040 with 63kA | Baseline | 230 | 2 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Morrisville Sub |  | Replace | EP | 2 |  | 10/31/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.123 | PJM SOUTH | Morrisville Sub 500kV - replace 50kA breakers H1T541, H1T594, H2T545, H2T569, SC122 with 63kA | Baseline | 500 | 5.08 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Morrisville Sub |  | Replace | EP | 5.08 |  | 8/21/2031 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.124 | PJM SOUTH | Mosby Sub 500kV - replace 50kA breakers 50272, 54672, 55972, 58472, 59072, 502T546, 559T584, SC172, SV172, SV272, XT590 with 63kA | Baseline | 500 | 11.16 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Mosby Sub |  | Replace | EP | 11.16 |  | 7/7/2033 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.125 | PJM SOUTH | Mt Storm Sub 500kV - replace 40kA breaker G3T572X with 63kA | Baseline | 500 | 1.01 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Mt Storm Sub |  | Replace | EP | 1.01 |  | 11/27/2031 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.126 | PJM SOUTH | Nimbus Sub 230kV - replace 63kA breakers 215282, 225532-5, 225532-6, 226034 with 80kA | Baseline | 230 | 2.64 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Nimbus Sub |  | Replace | EP | 2.64 |  | 12/13/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.127 | PJM SOUTH | NIVO 1 Sub 230kV - replace 63kA breaker 2116T2130 with 80kA (4-breaker ring bus) | Baseline | 230 | 0.66 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Nivo Sub |  | Replace | EP | 0.66 |  | 12/13/2032 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.128 | PJM SOUTH | North Anna Sub 500kV - replace 40kA breakers 57502, G102-1, G102-2, G202, G2T575, XT573 with 63kA | Baseline | 500 | 6.09 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | North Anna Sub |  | Replace | EP | 6.09 |  | 10/13/2032 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.129 | PJM SOUTH | Ox Sub 230kV - replace 50kA and 63kA breakers 201342, 209742, 206342, SC242 with 80kA | Baseline | 230 | 2.64 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Ox Sub |  | Replace | EP | 2.64 |  | 6/20/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.130 | PJM SOUTH | Ox Sub 500kV - replace 40kA breakers 56142, H1T539, H2T539 with 63kA | Baseline | 500 | 3.04 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Ox Sub |  | Replace | Cancelled | 3.04 |  | 6/20/2030 |  | No | 1/7/2025 | 4/1/2025 | 0 |  |  |  | 2025-01-07
b4000.131 | PJM SOUTH | Paragon Park Sub 230kV - replace 63kA breakers 220632, 220732 with 80kA | Baseline | 230 | 1.32 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Paragon Park Sub |  | Replace | EP | 1.32 |  | 2/7/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.132 | PJM SOUTH | Pleasantview Sub 230kV - replace 63kA breakers 203T274, 274T2098 with 80kA | Baseline | 230 | 1.32 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Pleasantview Sub |  | Replace | EP | 1.32 |  | 2/6/2031 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.133 | PJM SOUTH | Pleasantview Sub 500kV - replace 40kA breaker H322 with 63kA | Baseline | 500 | 1.01 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Pleasantview Sub |  | Replace | EP | 1.01 |  | 4/3/2031 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.134 | PJM SOUTH | Remington Sub 230kV - replace 40kA and 50kA breakers 211462, GT162, GT262, GT362, GT462, 2077T2086, 208662, H962, H9T299 with 63kA | Baseline | 230 | 4.5 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Remington Sub |  | Replace | EP | 4.5 |  | 1/9/2031 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.135 | PJM SOUTH | Roundtable Sub 230kV - replace 63kA breakers 203102, 214902, 221402, 222302, 2031T2223, 2149T2214 with 80kA | Baseline | 230 | 3.96 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Roundtable |  | Replace | EP | 3.96 |  | 7/24/2031 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.136 | PJM SOUTH | Vint Hill Sub 230kV - replace 63kA breakers 2101T2174, 2163T2174, 2101T2163 with 80kA | Baseline | 230 | 1.98 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Vint Hill Sub |  | Replace | EP | 1.98 |  | 2/14/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.137 | PJM SOUTH | Yardley Sub 230kV - replace 63kA breakers WT2209, WT2213, XT2209, XT2213 with 80kA | Baseline | 230 | 2.64 | 6/1/2029 | Dominion | 2024-W1-Short Circuit | Appendix A | Dominion:100 |  | VA | Yardley Sub |  | Replace | EP | 2.64 |  | 5/31/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.14 | PJM WEST | Install two new 500 kV dead-end structures near Black Oak substation to interconnect the 502 Junction – Woodside 500 kV transmission line. Adjust Woodside protection scheme for Black Oak loop-in and remove 502 Junction tie. (NEET Scope) | Baseline | 500 | 3 | 6/1/2029 | NEET | 2024-W1-PJM |  |  |  | MD | Black Oak 500 kV substation |  | Build | PL | 3 |  | 12/31/2031 |  | No | 6/5/2025 | 6/5/2025 | 0 |  |  |  | 2025-06-05
b4000.15 | PJM WEST | Construct a new 86 miles Welton Spring to Rocky Point 765 kV line (Welton Spring to DVP local area, roughly 50 miles) (WV Portion) | Baseline | 765 | 248.5 | 6/1/2029 | APS | 2024-W1-708 |  |  |  | WV | Welton Springs - Rocky Point |  | Build | EP | 248.5 |  | 6/1/2029 |  | No | 6/5/2025 | 6/5/2025 | 0 |  |  |  | 2025-06-05
b4000.2 | PJM WEST | Construct a new 175 miles Amos to Welton Spring 765 kV line. (AEP Section of the line is 30 miles) | Baseline | 765 | 150 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:14.67,BGE:8.11,Dominion:66.09,DPL:2.15,PEPCO:8.98 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | WV | John Amos - Welton Springs |  | Build | EP | 150 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.200 | PJM WEST | Broadford 765 kV Upgrade: Replace Jackson's Ferry CB Q2 | Baseline | 765 | 4.5 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:21.60,APS:12.36,BGE:8.28,Dominion:46.81,PEPCO:10.95 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | OH | Broadford |  | Replace | EP | 4.5 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.201 | PJM WEST | Smith Mountain 138 kV Upgrade: Replace 795 KCM AAC, 37-Str. 795 KCM AAC, 37-Str. PH A B2S1 B2S2 BS1 BS2 | Baseline | 138 | 0.4 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Smith Mountain |  | Replace | EP | 0.4 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.202 | PJM WEST | Rebuild 12.5 miles of Smith Mountain - Redeye 138 kV line | Baseline | 138 | 14.9 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Smith Mountain - Redeye |  | Reconductor | EP | 14.9 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.203 | PJM WEST | Rebuild 17.5 miles of Redeye - Candler's Mountain 138 kV line | Baseline | 138 | 21 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Redeye - Candler's Mountain |  | Reconductor | EP | 21 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.204 | PJM WEST | Rebuild 4 miles of Candler's Mountain - Opossum Creek 138 kV line | Baseline | 138 | 4.9 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Candler's Mountain - Opossum Creek |  | Reconductor | EP | 4.9 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.205 | PJM WEST | Candler's Mountain 138 kV: Replace 1590 KCM AAC, 61-Str. Replace MOAB "Y" SMITH MTN LINE | Baseline | 138 | 0.2 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Candler's Mountain |  | Replace | EP | 0.2 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.206 | PJM WEST | Opposum Creek 138 kV: Replace Opossum Creek Switch | Baseline | 138 | 0.1 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Opposum Creek |  | Replace | EP | 0.1 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.207 | PJM WEST | Leesville Station Upgrade 138 kV: Replace 795 KCM AAC, 37-Str. IPS Sch. 40 1272 KCM AAC, 61-Str. 1272 KCM AAC, 61-Str. PH A,B,C ALTA VISTA CB-A BUS DISC ALTA VISTA CB-A LINE DISC Wavetrap (1200A) Relay Thermal Limit 1356 Amps | Baseline | 138 | 0.6 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Leesville |  | Replace | EP | 0.6 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.208 | PJM WEST | Otter 138 kV Station Upgrade: Replace 795 KCM AAC, 37-Str. | Baseline | 138 | 0.1 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Otter |  | Replace | EP | 0.1 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.209 | PJM WEST | Rebuild 0.9 miles of Altavista - Otter 138 kV line | Baseline | 138 | 1.2 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Altavista - Otter - Johnson Mountain |  | Reconductor | EP | 1.2 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.210 | PJM WEST | Rebuild 7 miles of Otter - Johnson Mountain 138 kV line | Baseline | 138 | 8.4 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Otter - Johnson Mountain |  | Reconductor | EP | 8.4 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.211 | PJM WEST | Rebuild 6.5 miles of Johnson Mountain - New London 138 kV line | Baseline | 138 | 7.68 | 6/1/2029 | AEP | 2024-W1-81 | Appendix A | AEP:100 |  | OH | Johnson Mountain - New London |  | Reconductor | EP | 7.68 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.251 | PJM WEST | Replace the wave trap and upgrade the relay at Cloverdale 765kV substation | Baseline | 765 | 1 | 6/1/2029 | AEP | 2024-W1-617 | Appendix A | AEP:3,APS:8.96,BGE:6.53,Dominion:72.75,PEPCO:8.76 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | OH | Cloverdale |  | Replace | EP | 1 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.252 | PJM WEST | Replace the wave trap and upgrade the relay at Joshua Falls 765kV substation | Baseline | 765 | 1 | 6/1/2029 | AEP | 2024-W1-617 | Appendix A | AEP:3,APS:8.96,BGE:6.53,Dominion:72.75,PEPCO:8.76 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | OH | Joshua Falls |  | Replace | EP | 1 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.3 | PJM WEST | Construct a new 175 miles Amos to Welton Spring 765 kV line. (APS/FE Section of the line is 145 miles) | Baseline | 765 | 725 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:14.67,BGE:8.11,Dominion:66.09,DPL:2.15,PEPCO:8.98 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | WV | John Amos - Welton Springs |  | Build | EP | 725 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.300 | PJM SOUTH | Rebuild approximately 1.71 miles of 230kV line 299 from the Marsh Run substation to the Remington CT substation. New conductor has a summer rating of 1573 MVA. | Baseline | 230 | 5.35 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Marsh Run, Remington CT |  | Reconductor | EP | 5.35 |  | 5/30/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.301 | PJM SOUTH | Reconductor approximately 1.24 miles of 230kV line 280 from Remington - the Marsh Run CT substation to the Remington substation. New conductor has a summer rating of 1573 MVA. | Baseline | 230 | 3.89 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Marsh Run, Remington CT |  | Reconductor | EP | 3.89 |  | 5/30/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.302 | PJM SOUTH | Uprate line #299 terminal equipment, line leads, and bus at Marsh Run substation to be rated to 4000A. | Baseline | 230 | 2.53 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Marsh Run |  | Uprate | EP | 2.53 |  | 5/30/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.303 | PJM SOUTH | Uprate line #299 terminal equipment, line leads, and bus at Remington CT substation to be rated to 4000A. | Baseline | 230 | 2.44 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Remington CT |  | Uprate | EP | 2.44 |  | 5/30/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.304 | PJM SOUTH | Partial reconductor/partial wreck & rebuild of 230kV Line #2161 Gainesville – Wheeler. New conductor has a summer rating of 1573 MVA. (Wheeler - Linton Tap segment) | Baseline | 230 | 17.72 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Wheeler, Linton |  | Reconductor | EP | 17.72 |  | 5/30/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.305 | PJM SOUTH | Partial reconductor/partial wreck & rebuild of 230kV Line #2161 Gainesville – Wheeler. New conductor has a summer rating of 1573 MVA. (Linton Tap - Atlantic segment) | Baseline | 230 | 3.49 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Linton, Atlantic |  | Reconductor | EP | 3.49 |  | 5/16/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.306 | PJM SOUTH | Partial reconductor/partial wreck & rebuild of 230kV Line #2161 Gainesville – Wheeler. New conductor has a summer rating of 1573 MVA. (Atlantic - Trident segment) | Baseline | 230 | 1.72 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Atlantic, Trident |  | Reconductor | EP | 1.72 |  | 5/16/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.307 | PJM SOUTH | Partial reconductor/partial wreck & rebuild of 230kV Line #2161 Gainesville – Wheeler. New conductor has a summer rating of 1573 MVA. (Trident - Gainesville segment) | Baseline | 230 | 6.16 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Trident, Gainesville |  | Reconductor | EP | 6.16 |  | 5/16/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.308 | PJM SOUTH | Upgrade all line #2161 terminal equipment at Gainesville to 4000A. A CCVT will also be replaced due to aging. | Baseline | 230 | 1.78 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Gainesville |  | Upgrade | EP | 1.78 |  | 5/16/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.309 | PJM SOUTH | Upgrade all line #2161 terminal equipment Wheeler substation to 4000A. | Baseline | 230 | 2.25 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Wheeler |  | Upgrade | EP | 2.25 |  | 5/16/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.310 | PJM SOUTH | Revise relay settings at Trident substation. | Baseline | 230 | 0.03 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Trident |  | Revise | EP | 0.03 |  | 5/16/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.311 | PJM SOUTH | Rebuild 230kV Line #213 and #225 from Thelma – Lakeview. New conductor has a summer rating of 1573 MVA. | Baseline | 230 | 44.69 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Thelma, Lakeview |  | Rebuild | EP | 44.69 |  | 5/16/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.312 | PJM SOUTH | At Thelma subsation, upgrade line lead, wave traps (213WT & 225WT), circuit breaker leads to 4000A. CB switches 22535, 23235, 23238 and 21335 will also be upgrade to 4000A DEB switches. CCVTs 213P1, 213P2 and 213P3 will be replaced due to aging. | Baseline | 230 | 2.3 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Thelma, Lakeview |  | Upgrade | EP | 2.3 |  | 5/26/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.313 | PJM SOUTH | At Lakeview substation, upgrade wave traps 213WT and 225WT, line leads, and circuit breaker leads to 4000A. Upgrade CB switches 22565 and 22564 to 4000A double-end break switches. Replace CCVTs 225P1, 225P2, and 225P3 due to aging. | Baseline | 230 | 1.72 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Lakeview |  | Upgrade | EP | 1.72 |  | 5/26/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.314 | PJM SOUTH | Reconductor 230kV Line #2003 Chesterfield – Tyler segment. New conductor has a summer rating of 1573 MVA. | Baseline | 230 | 3.16 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Chesterfield, Tyler |  | Reconductor | EP | 3.16 |  | 4/22/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.315 | PJM SOUTH | Reconductor 230kV Line #2003 Tyler – Poe segment. New conductor has a summer rating of 1573 MVA. | Baseline | 230 | 20.61 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Tyler, Poe |  | Reconductor | EP | 20.61 |  | 4/22/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.316 | PJM SOUTH | At Poe substation, uprate all Line #2003 terminal equipment, line leads, and bus to be rated to 4000A. | Baseline | 230 | 1.79 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Poe |  | Uprate | EP | 1.79 |  | 4/22/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.317 | PJM SOUTH | At Tyler substation, upgrade the necessary line terminal equipment to maintain 4000A at Tyler substation. | Baseline | 230 | 0.54 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Tyler |  | Upgrade | EP | 0.54 |  | 4/22/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.318 | PJM SOUTH | Revise relay settings at Chesterfield substation. | Baseline | 230 | 0.02 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Chesterfield |  | Revise | EP | 0.02 |  | 4/22/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.319 | PJM SOUTH | Reconductor 230kV Line #2002 Carson – Poe. New conductor has a summer rating of 1573 MVA. | Baseline | 230 | 30.29 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Carson, Poe |  | Reconductor | EP | 30.29 |  | 3/20/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.320 | PJM SOUTH | At Carson substation, upgrade all line #2002 terminal equipment at Carson to 4000A. CCVTs will also be replaced due to aging. | Baseline | 230 | 0.89 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Carson |  | Upgrade | EP | 0.89 |  | 3/20/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.321 | PJM SOUTH | At Poe substation, upgrade all line #2002 terminal equipment at Carson to 4000A. CCVTs will also be replaced due to aging. | Baseline | 230 | 0.81 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Poe |  | Upgrade | EP | 0.81 |  | 3/20/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.322 | PJM SOUTH | Build a new 230kV Line from Nokesville – Hornbaker using the vacant arms of the double circuit monopole structures installed as part of previous project 993027. New conductor has a summer rating of 1573 MVA. | Baseline | 230 | 15.28 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Nokeville, Hornbaker |  | Build | EP | 15.28 |  | 7/9/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.323 | PJM SOUTH | Upgrade terminal equipment at Nokesville substation. The project adds one more line to Nokesville, including the installation of one 230kV breaker and two 230kV switches. | Baseline | 230 | 1.43 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Nokesville |  | Upgrade | EP | 1.43 |  | 7/9/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.324 | PJM SOUTH | Upgrade terminal equipment at Hornbaker substation. This project provides for installing a new 230kV 4000A rated line terminal at Hornbaker to accommodate the new line to Nokesville. | Baseline | 230 | 1.43 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Hornbaker |  | Upgrade | EP | 1.43 |  | 7/9/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.325 | PJM SOUTH | Build a new 26.38mi 230kV Line from Elmont – Ladysmith on the existing 5-2 structures between the two stations. New conductor has a summer rating of 1573 MVA. | Baseline | 230 | 26.09 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Elmont, Ladysmith |  | Build | EP | 26.09 |  | 2/24/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.326 | PJM SOUTH | At Elmont substation, install/upgrade associated equipment to accommodate a 4000A line rating for the new 230kV line between Elmont - Ladysmith. | Baseline | 230 | 2.19 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Elmont |  | Upgrade | EP | 2.19 |  | 2/24/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.327 | PJM SOUTH | Upgrade/install equipment at Ladysmith substation to 4000A. Expansion will be required to accommodate a total of three (3) new 230kV strings of breaker and a half scheme. | Baseline | 230 | 8.72 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Ladysmith |  | Upgrade | EP | 8.72 |  | 2/24/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.328 | PJM SOUTH | Construct a new 24.5-mile 230 kV line 9482 from Cloverhill substation to Ox substation. | Baseline | 230 | 287.54 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Cloverhill, Ox |  | Build | EP | 287.54 |  | 4/28/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.329 | PJM SOUTH | At Ox substation, install the necessary associated equipment to accomdate the new line between Cloverhill - Ox. This project also includes expanding the substation with associated security level 1 fencing and super post structure needed. | Baseline | 230 | 6.37 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Ox |  | Install | EP | 6.37 |  | 4/28/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.330 | PJM SOUTH | At Cloverhill substation, install the necessary associated equipment to accomdate the new line between Cloverhill - Ox. This project also includes demolishing and reconstructing the existing bus system and roadway. | Baseline | 230 | 2.27 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Cloverhill |  | Install | EP | 2.27 |  | 4/28/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.331 | PJM SOUTH | Construct a new 230kV single circuit line from Raines substation to Cloud substation to solve electrical violations cause by the significant load growth in South Hill, Virginia. The scope also includes an idle 230kV circuit being installed between these stations. | Baseline | 230 | 77.5 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Raines, Cloud |  | Build | EP | 77.5 |  | 11/8/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.332 | PJM SOUTH | At Cloud substation, upgrade substation terminal equipment to 4000A. | Baseline | 230 | 1.43 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Cloud |  | Upgrade | EP | 1.43 |  | 11/8/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.333 | PJM SOUTH | At Raines substation, upgrade substation terminal equipment to 4000A. | Baseline | 230 | 1.32 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Raines |  | Upgrade | EP | 1.32 |  | 11/8/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.334 | PJM SOUTH | Reconductor 115kV line #121 from Poe - Prince George. Specifically, line #121 will be reconductored and converted to 230kV from Poe substation to Prince George substation. | Baseline | 230 | 14.62 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Poe, Prince George |  | Reconductor | EP | 14.62 |  | 1/10/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.335 | PJM SOUTH | At Poe substation, install a new 230kV six breaker ultimate ring bus which will fit the station to current 230kV standards. The substation scope includes the installation of 230kV breaker and half GIS bus. Work at Poe subsation is associated with line #121 reconductor. | Baseline | 230 | 38.28 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Poe |  | Install | EP | 38.28 |  | 1/10/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.336 | PJM SOUTH | Build a new 230-115kV Prince George substation along the existing 115 or 230kV corridor. The substation scope includes the installation of 230kV breakers & 1-115kV breaker along with its associated terminal equipment initially but will have provision for making it a 6-breaker ring (both 230 & 115kV) in future. The existing 230-115kV transformer at Prince George will be relocated to serve this new substation. | Baseline | 230 | 26.62 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Prince George |  | Build | EP | 26.62 |  | 1/10/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.337 | PJM SOUTH | Extend a new 230 kV line approximately 7.85 miles between the existing Morrisville and Anderson Branch substations. The existing tower structures currently supporting the Bristers to Morrisville 500 kV Line #545 will be used to support this new line as shared tower structures. | Baseline | 230 | 5.26 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Morrisville, Anderson Branch |  | Build | EP | 5.26 |  | 6/14/2028 |  | No | 1/7/2025 | 1/7/2025 | 5 |  |  |  | 2025-01-07
b4000.338 | PJM SOUTH | At Morrisville substation, install/upgrade substation terminal equipment to 4000A. | Baseline | 230 | 0.95 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Morrisville |  | Install | EP | 0.95 |  | 6/14/2028 |  | No | 1/7/2025 | 1/7/2025 | 5 |  |  |  | 2025-01-07
b4000.339 | PJM SOUTH | At Anderson Branch substation, install/upgrade substation terminal equipment to 4000A. | Baseline | 230 | 0.95 | 6/1/2029 | Dominion | 2024-W1-24 | Appendix A | Dominion:100 |  | VA | Anderson Branch |  | Install | EP | 0.95 |  | 6/14/2028 |  | No | 1/7/2025 | 1/7/2025 | 5 |  |  |  | 2025-01-07
b4000.340 | PJM SOUTH | Uprate existing Goose Creek 500/230kV transformer to 1440 MVA. | Baseline | 500/230 | 34.01 | 6/1/2029 | Dominion | 2024-W1-781 | Appendix A | Dominion:100 |  | VA | Goose Creek |  | Upgrade | EP | 34.01 |  | 9/15/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.341 | PJM SOUTH | Remove the 500 kV conductor previously planned to terminate into the Vint Hill 500 kV substation and extend approximately 0.2 miles of conductor to fly-over the site. | Baseline | 500 | 0 | 6/1/2029 | Dominion | 2024-W1-781 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Vint Hill |  | Remove | EP | 0 |  | 7/13/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.342 | PJM SOUTH | Remove the terminal equipment and substation work required for the termination of the Morrisville – Wishing Star 500 kV line into Vint Hill. | Baseline | 500 | 0 | 6/1/2029 | Dominion | 2024-W1-781 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Vint Hill |  | Remove | EP | 0 |  | 7/13/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.343 | PJM SOUTH | Uprate bus at Brambleton to support 500kV Line #558 (Aspen to Brambleton) uprate. | Baseline | 500 | 0 | 6/1/2029 | Dominion | 2024-W1-781 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Brambleton |  | Uprate | EP | 0 |  | 11/28/2025 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.344 | PJM SOUTH | Build a 500kV line from North Anna substation (bypassing Ladysmith Substation) to a new substation called Kraken. New conductor to have a minimum summer normal rating of 4357MVA. | Baseline | 500 | 186.67 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | Dominion:91.69,PEPCO:8.31 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | North Anna, Kraken |  | Build | EP | 186.67 |  | 9/16/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.345 | PJM SOUTH | Build a 500kV line from a new substatoon called Kraken to a new substation called Yeat. New conductor to have a minimum summer normal rating of 4357MVA. | Baseline | 500 | 394.71 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Kraken, Yeat |  | Build | EP | 394.71 |  | 9/16/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.346 | PJM SOUTH | Cut-in 500kV line from Kraken substation into Yeat substation | Baseline | 500 | 5 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | Dominion:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Kraken |  | Cut In | EP | 5 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.347 | PJM SOUTH | Upgrade/install equipment at North Anna substation to 5000A to support the new conductor rating. | Baseline | 500 | 9.12 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | Dominion:91.69,PEPCO:8.31 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | North Anna |  | Upgrade | EP | 9.12 |  | 9/16/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.348 | PJM SOUTH | Build a new 500/230kV substation called Kraken. The 500kV, 5000A ring bus will be set up for a redundant breaker configuration. Install (2) 1400MVA 500/230 kV transformers. A new redundant breaker ring will be added at Kraken to accommodate the new 500kV line from North Anna to Kraken. | Baseline | 500 | 84.41 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | Dominion:100 |  | VA | Kraken |  | Build | EP | 84.41 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.349 | PJM SOUTH | Update relay settings at Ladysmith to change the destination of 500kV line #568 from Possum Point to Kraken. | Baseline | 500 | 0.04 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | BGE:13.28,Dominion:64.48,PEPCO:22.24 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Ladysmith |  | Update | EP | 0.04 |  | 9/16/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.350 | PJM SOUTH | Update relay settings at Possum Point to change the destination of 500kV line #568 from Ladysmith to Kraken. | Baseline | 500 | 0.04 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | BGE:8.30,Dominion:78.64,PEPCO:13.06 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Possum Point |  | Update | EP | 0.04 |  | 9/16/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.351 | PJM SOUTH | Cut in Line #568 Ladysmith - Possum Point into Kraken, creating Line #9517 Ladysmith to Kraken. | Baseline | 500 | 3.6 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | BGE:8.30,Dominion:78.64,PEPCO:13.06 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Ladysmith, Kraken |  | Cut In | EP | 3.6 |  | 9/16/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.352 | PJM SOUTH | Cut in Line #568 Ladysmith - Possum Point into Kraken, creating new Line #568 Kraken to Possum Point. | Baseline | 500 | 3.6 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | BGE:13.28,Dominion:64.48,PEPCO:22.24 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Possum Point, Kraken |  | Cut In | EP | 3.6 |  | 9/16/2030 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.353 | PJM SOUTH | Upgrade 500kV terminal equipment at Elmont substation. | Baseline | 500 | 8.9 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | APS:9.79,BGE:6.14,Dominion:75.61,PEPCO:8.46 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Elmont |  | Upgrade | EP | 8.9 |  | 6/1/2028 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.354 | PJM SOUTH | Expand Ladysmith substation to a add redundant circuit breakers to the middle breakers on both 500kV strings (574T575 and 568T581). The equipment including switches 57518, 57515, H115 will be replaced with 5000A equipment. | Baseline | 500 | 8.24 | 6/1/2029 | Dominion | 2024-W1-967 | Appendix A | APS:9.79,BGE:6.14,Dominion:75.61,PEPCO:8.46 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Ladysmith |  | Expand | EP | 8.24 |  | 11/14/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.355 | PJM SOUTH | Build a new 156 mile 765kV line from Joshua Falls – Yeat. (Roughly 69.3 miles in AEP section). | Baseline | 765 | 341.17 | 6/1/2029 | AEP | 2024-W1-820 | Appendix A | APS:9.11,BGE:6.49,Dominion:75.72,PEPCO:8.68 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Joshua Falls, Yeat |  | Build | EP | 341.17 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.356 | PJM SOUTH | Build a new 156 mile 765kV line from Joshua Falls – Yeat. (Roughly 86.7 miles in Dominion section). | Baseline | 765 | 426.83 | 6/1/2029 | Dominion | 2024-W1-820 | Appendix A | APS:9.11,BGE:6.49,Dominion:75.72,PEPCO:8.68 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Joshua Falls, Yeat |  | Build | EP | 426.83 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.357 | PJM SOUTH | Build a new 765/500/230kV substation called Yeat. Install (2) 765/500 kV transformers. Cut in 500kV line Bristers – Ox and 500kV line Meadowbrook – Vint Hill into Yeat. | Baseline | 765 | 197.1 | 6/1/2029 | Dominion | 2024-W1-820 | Appendix A | Dominion:89.71,PEPCO:10.29 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Yeat |  | Build | EP | 197.1 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.358 | PJM SOUTH | Build a new 765/500/230kV substation called Yeat. Install (1) 500/230kV transformer. Cut in 230kV line Vint Hill – Elk Run into Yeat substation. | Baseline | 765 | 45.6 | 6/1/2029 | Dominion | 2024-W1-820 | Appendix A | Dominion:100 |  | VA | Yeat |  | Build | EP | 45.6 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.359 | PJM SOUTH | Add (2) 765kV breakers at Joshua Falls substation. Substation expansion is required to add the additional breakers. | Baseline | 765 | 99.19 | 6/1/2029 | AEP | 2024-W1-820 | Appendix A | APS:9.11,BGE:6.49,Dominion:75.72,PEPCO:8.68 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Joshua Falls |  | Add | EP | 99.19 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.360 | PJM SOUTH | Replace two switches, a wave trap and leads to upgrade all related substation equipment to 2000A at Altavista 138 kV substation. | Baseline | 138 | 1 | 6/1/2029 | Dominion |  |  |  |  | VA | Altavista |  | Replace | EP | 1 |  | 12/31/2031 |  | No | 5/6/2025 | 5/6/2025 | 0 |  |  |  | 2025-05-06
b4000.4 | PJM WEST | Construct a new 765 kV switchyard (Welton Spring) | Baseline | 765 | 92.28 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:14.67,BGE:8.11,Dominion:66.09,DPL:2.15,PEPCO:8.98 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | WV | Welton Springs |  | Build | EP | 92.28 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.5 | PJM WEST | Install four 250 MVAR shunt capacitors, and a +/-500 MVAR STATCOM at Welton Spring 765 kV substation | Baseline | 765 | 121.54 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:100 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | WV | Welton Springs |  | Install | EP | 121.54 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.6 | PJM WEST | Construct a new 86 miles Welton Spring to Rocky Point 765 kV line (Welton Spring to DVP local area, roughly 21 miles) (VA Portion) | Baseline | 765 | 353.5 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:14.67,BGE:8.11,Dominion:66.09,DPL:2.15,PEPCO:8.98 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | WV | Welton Springs - Rocky Point |  | Build | EP | 105 |  | 6/1/2029 |  | No | 1/7/2025 | 6/5/2025 | 0 |  |  |  | 2025-01-07
b4000.7 | PJM WEST | Construct a new 86 miles Welton Spring to Rocky Point 765 kV line (in DVP local area/Millville to Lovettsville section, roughly 10.5 miles) | Baseline | 765 | 52.5 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:14.67,BGE:8.11,Dominion:66.09,DPL:2.15,PEPCO:8.98 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | VA | Welton Springs - Rocky Point |  | Build | EP | 52.5 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.8 | PJM WEST | Construct a new 86 miles Welton Spring to Rocky Point 765 kV line (DVP local area to Rocky Point, roughly 4.8 miles) | Baseline | 765 | 24 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:14.67,BGE:8.11,Dominion:66.09,DPL:2.15,PEPCO:8.98 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Welton Springs - Rocky Point |  | Build | EP | 24 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b4000.9 | PJM WEST | Construct a new substation called Rocky Point with a 765 kV and a 500 kV yard. Loop in the Doubs-Goose Creek 500 kV line, the Doubs-Aspen 500 kV line, and the Woodside-Goose Creek 500 kV line. Install two 765/500 kV transformer at Rocky Point substation | Baseline | 765/500 | 254.7 | 6/1/2029 | APS | 2024-W1-708 | Appendix A | APS:14.99,BGE:8.29,Dominion:67.55,PEPCO:9.17 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Rocky Point |  | Build | EP | 254.7 |  | 6/1/2029 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07
b3863.1 | PJM MA | Change tap ratios on two (2) CTs at Schuylkill 230kV Substation | Baseline | 230 | 0.1 | 12/1/2029 | PECO |  | Appendix A | PECO:100 |  | PA | Schuylkill |  | Modify | EP | 0.1 |  | 12/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3865.1 | PJM MA | Upgrade 138/69kV autotransformer, a 69kV breaker, two disconnects and move a takeoff structure at Reybold Substation. These upgrades will require a substation expansion to move the takeoff structure and a control house expansion to move the 69kV breaker relays from the Delaware City control house to the Reybold control house. | Baseline | 138 | 9.48 | 12/1/2029 | DPL |  | Appendix A | DPL:100 |  | DE | Reybold |  | Upgrade | EP | 9.48 |  | 12/1/2029 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3869.1 | PJM MA | Relocate the Bergen Gen #1 point of interconnection from Bergen 138kV to Bergen 345kV GIS through the existing 345/138kV transformer. | Baseline | 345 | 6.8 | 12/1/2029 | PSEG |  | Appendix A | PSEG:100 |  | NJ | Bergen |  | Relocate | PL | 6.8 |  | 9/1/2027 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3869.2 | PJM MA | Remove and retire the two (2) existing Bergen 138kV Series Reactors and associated ancillary equipment. | Baseline | 138 | 5.7 | 12/1/2029 | PSEG |  | Appendix A | PSEG:100 |  | NJ | Bergen |  | Remove | PL | 5.7 |  | 9/1/2027 |  | No | 11/14/2024 | 11/14/2024 | 0 |  |  |  | 2024-11-14
b3876.1 | PJM WEST | Install a 69kV 11.5MVar capacitor bank at Richlands station with a circuit switcher. | Baseline | 138 | 1 | 12/1/2029 | AEP |  | Appendix A | AEP:100 |  | VA | Richlands |  | Install | EP | 1 |  | 12/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3883.1 | PJM WEST | 69 kV station equipment, including relays, conductor, and switches, will be replaced at Haviland station in order to address identified overloads on the lines to North Van Wert and Cavett. | Baseline | 138 | 0.8 | 12/1/2029 | AEP |  | Appendix A | AEP:100 |  | OH | Haviland |  | Replace | EP | 0.8 |  | 12/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3896.1 | PJM WEST | Adjust the capacitor bank voltage settings to allow the cap bank to operate as needed under N-1-1 scenarios. | Baseline | 115 | 0.1 | 12/1/2029 | AEP |  | Appendix A | AEP:100 |  | VA | Skimmer |  | Modify | EP | 0.1 |  | 6/1/2029 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3898.1 | PJM WEST | Upgrade the CT thermal limit at Buchanan station on the Buchanan-Keen Mountain 138 kV line. | Baseline | 138 | 0.1 | 12/1/2029 | AEP |  | Appendix A | AEP:100 |  | VA | Buchanan IPP |  | Upgrade | EP | 0.1 |  | 12/1/2025 |  | No | 11/15/2024 | 11/15/2024 | 0 |  |  |  | 2024-11-15
b3902.1 | PJM WEST | Replace the Wilton Center 345 kV BT 4-5 circuit breaker. | Baseline | 345 | 2.7 | 12/1/2029 | ComEd |  | Appendix A | ComEd:100 |  | IL | Wilton Ctr. |  | Replace | IS | 2.7 |  | 12/1/2029 | 12/3/2024 | No | 12/3/2024 | 12/3/2024 | 100 |  |  |  | 2024-12-03
b3866.1 | PJM MA | Adjust relay setting at Cedar Creek 230kV Substation. | Baseline | 230 | 0.1 | 12/31/2029 | DPL |  | Appendix A | DPL:100 |  | DE | Cedar Creek |  | Modify | EP | 0.1 |  | 12/31/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3866.2 | PJM MA | Change relay setting at Milford 230kV Substation | Baseline | 230 | 0.1 | 12/31/2029 | DPL |  | Appendix A | DPL:100 |  | DE | Milford |  | Modify | EP | 0.1 |  | 12/31/2029 |  | No | 12/3/2024 | 12/3/2024 | 0 |  |  |  | 2024-12-03
b3737.10 | PJM MA | Atlantic 230 kV substation – Convert to double-breaker double-bus. | Baseline | 230 | 31.47 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Atlantic |  | Modify | EP | 31.47 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.11 | PJM MA | Freneau substation – Update relay settings on the Atlantic 230 kV line. | Baseline | 230 | 0.03 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Freneau |  | Modify | EP | 0.03 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.12 | PJM MA | Smithburg substation – Update relay settings on the Atlantic 230 kV line. | Baseline | 230 | 0.03 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Smithburg |  | Modify | EP | 0.03 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.13 | PJM MA | Oceanview substation – Update relay settings on the Atlantic 230 kV lines. | Baseline | 230 | 0.04 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Oceanview |  | Modify | EP | 0.04 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.14 | PJM MA | Red Bank substation – Update relay settings on the Atlantic 230 kV lines. | Baseline | 230 | 0.04 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Red Bank |  | Modify | EP | 0.04 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.15 | PJM MA | South River substation – Update relay settings on the Atlantic 230 kV line. | Baseline | 230 | 0.03 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | South River |  | Modify | EP | 0.03 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.16 | PJM MA | Larrabee substation – Update relay settings on the Atlantic 230 kV line. | Baseline | 230 | 0.03 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee |  | Modify | EP | 0.03 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.17 | PJM MA | Atlantic substation – Construct a new 230 kV line terminal position to accept the generator lead line from the offshore wind Larrabee Collector station. | Baseline | 230 | 4.95 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Atlantic |  | Modify | EP | 4.95 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 4 |  |  |  | 2022-11-04
b3737.18 | PJM MA | G1021 (Atlantic-Smithburg) 230 kV upgrade. | Baseline | 230 | 9.68 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Atlantic-Smithburg, Larrabee Collector Substation |  | Upgrade | EP | 9.68 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 10 |  |  |  | 2022-11-04
b3737.19 | PJM MA | R1032 (Atlantic-Larrabee) 230 kV upgrade. | Baseline | 230 | 14.5 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Atlantic-Larrabee, Larrabee Collector Substation |  | Upgrade | EP | 14.5 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 10 |  |  |  | 2022-11-04
b3737.20 | PJM MA | New Larrabee Collector station-Atlantic 230 kV line. | Baseline | 230 | 17.07 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Atlantic-Larrabee Collector Station |  | Install | EP | 17.07 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 10 |  |  |  | 2022-11-04
b3737.21 | PJM MA | Larrabee-Oceanview 230 kV line upgrade. | Baseline | 230 | 6 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee-Oceanview, Larrabee Collector Station |  | Upgrade | EP | 6 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 10 |  |  |  | 2022-11-04
b3737.45 | PJM MA | Reconductor 0.33 miles of PPL’s portion of the Gilbert-Springfield 230 kV line. | Baseline | 230 | 0.38 | 6/1/2030 | PPL | 2021_SAA-330 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | PA | Gilbert-Springfield |  | Reconductor | IS | 0.38 |  | 3/28/2025 | 3/28/2025 | No | 11/4/2022 | 11/4/2022 | 100 |  |  |  | 2022-11-04
b3737.9 | PJM MA | Larrabee substation upgrades. | Baseline | 230 | 0.86 | 6/1/2030 | JCPL | 2021_SAA-453 | Appendix C | AEC:13.29,JCPL:32.03,PSEG:52.59,RE:2.09 |  | NJ | Larrabee |  | Upgrade | EP | 0.86 |  | 6/1/2030 |  | No | 11/4/2022 | 11/4/2022 | 10 |  |  |  | 2022-11-04
b4000.13 | PJM WEST | Terminate the Woodside - Goose Creek 500 kV Line into Doubs Substation, creating the Woodside - Doubs #2 500 kV Line Remove the Chanceford-Doubs and Rocky Point-Doubs line terminations at the Doubs substation and connects the two lines through a 0.6 mile 500 kV bypass line around the Doubs substation | Baseline | 500 | 13.97 | 6/1/2032 | APS | 2024-W1-551 | Appendix A | AEC:0.20,APS:0.06,BGE:0.71,Dominion:89.06,DPL:0.36,JCPL:0.33,ME:0.15,PECO:0.73,PEPCO:7.93,PSEG:0.42,RE:0.02,Neptune:0.03 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | MD | Doubs area |  | Build | PL | 13.97 |  | 6/1/2032 |  | No | 1/7/2025 | 1/7/2025 | 0 |  |  |  | 2025-01-07