## Sheet1
Upgrade Id | Region | Description | Project Type | Voltage | Cost Estimate | Required Date | Transmission Owner | Proposal IDs | Schedule12 Location | (Non-Load Ratio Share) Cost Allocation Percent | (Load Ratio Share) Cost Allocation Percent | State | Location | Equipment | Task | Status | TEAC Cost | Driver | Projected In Service Date | Actual In Service Date | Immediate Need | Initial TEAC Date | Latest TEAC Date | Percent Complete | ISA In-Service Date | Revised In-Service Date | TEAC Materials | __parsed_Initial TEAC Date__
b3326 | PJM MA | Rebuild the 13707 Vienna-Nelson 138 kV line | Baseline | 138 | 60.5 |  | DPL |  | Appendix A | DPL:100 |  | DE | Vienna - Nelson |  | Rebuild | IS | 38.5 |  | 12/18/2024 | 12/18/2024 | No | 8/10/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-10
b3327 | PJM MA | Upgrade the disconnect switch (6784-L1) at Kent | Baseline | 69 | 0.25 |  | DPL |  | Appendix A | DPL:100 |  | DE | Vaughn |  | Upgrade | IS | 0.25 |  | 12/8/2023 | 12/15/2023 | No | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3328 | PJM MA | Upgrade the disconnect switch (13710-L1) and CT at Vienna | Baseline | 138 | 0.08 |  | DPL |  | Appendix A | DPL:100 |  | MD | Vienna |  | Upgrade | IS | 0.25 |  | 11/17/2023 | 11/17/2023 | No | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3332 | PJM MA | Rerate the 23076 Steel-Milford 230 kV line | Baseline | 230 | 7.2 |  | DPL |  | Appendix A | DPL:100 |  | DE | Steel - Milford |  | Rebuild | IS | 0.6 |  | 7/31/2024 | 9/17/2024 | Yes | 8/31/2021 | 10/5/2021 | 100 |  |  |  | 2021-08-31
b3775.2 | PJM WEST | Reconductor NEET’s section of Crete(IN/IL border)-St. John 345 kV line (6.95 miles). | Baseline | 345 | 7.24 |  | NEET | 2022_MD-644 (modified) | Appendix A | Economic driver (52.75%):_x000D_ AEC:0.87,AEP:24.07,APS:3.95,BGE:4.30,Dayton:3.52,DEOK:5.35,Dominion:20.09,DPL:1.73,DL:2.11,ECP:0.17,EKPC:1.73,ATSI:11.04,HTP:0.07,JCPL:1.98,ME:1.63,Neptune:0.43,OVEC:0.07,PECO:3.59,PENELEC:1.68,PEPCO:3.91,PPL:3.64,PSEG:3.93,RE:0.14_x000D_ Reliability driver (47.25%):_x000D_ ComEd:100_x000D_ |  | IL | Crete-St. John |  | Reconductor | IS | 1.99 |  | 12/1/2026 | 5/9/2023 | No | 1/10/2023 | 1/10/2023 | 100 |  |  |  | 2023-01-10
b3702 | PJM SOUTH | Install one 13.5 Ohm series reactor to control the power flow on the 230 kV line #2054 from Charlottesville substation to Proffit Rd 230 kV line. | Baseline | 230 | 11.38 | 6/1/2023 | Dominion | 202021_1-651 | Appendix A | AEC:1.59,APS:8.85,ATSI:5.54,BGE:10.79,ComEd:1.86,Dayton:0.21,DEOK:1.16,DL:1.16,Dominion:18.99,DPL:3.68,ECP:0.27,HTP:0.22,JCPL:4.53,ME:1.73,Neptune:0.68,PECO:6.95,PENELEC:4.75,PEPCO:9.69,PPL:9.78,PSEG:7.28,RE:0.29 |  | VA | Charlottesville-Proffit |  | Install | Cancelled | 11.38 |  | 6/1/2025 |  | No | 11/30/2021 | 3/5/2024 | 30 |  |  |  | 2021-11-30
b3847.1 | PJM WEST | Add a 765 kV breaker at Baker station for the reactor on the Broadford 765 kV line. | Baseline | 765 | 23.36 | 6/1/2024 | AEP | Immediate Need | Appendix A | AEP:70.68,EKPC:8.12,PEPCO:21.20 | AEC:1.58 ,AEP:13.71 ,APS:5.49 ,ATSI:7.69 ,BGE:4.16 ,ComEd:13.25 ,Dayton:2.07 ,DEOK:3.18 ,Dominion:14.2 ,DPL:2.57 ,DL:1.65 ,EKPC:2.3 ,JCPL:3.8 ,ME:1.88 ,OVEC:0.06 ,PECO:5.32 ,PENELEC:1.81 ,PEPCO:3.79 ,PPL:4.58 ,PSEG:6.24 ,RE:0.25 ,Neptune:0.42 | KY | Baker |  | Install | EP | 23.36 |  | 6/25/2027 |  | Yes | 6/5/2024 | 6/5/2024 | 50 |  |  |  | 2024-06-05